## P2 - 2026 delet (hidden)
P2 2025 Planned Offline Mogas Production (KBD)
Sum of Capacity Offline for Area Chart (KBD) | Column Labels | [12 empty] | Column Labels
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Sep | Oct | Nov | Dec | Grand Total |  | Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 1Q25 Total | Aug-Nov Avg
Chalmette Refining LLC | 220.76 | 77.7457 | [7 empty] | 24.7686 | 323.2743
Chalmette Refinery | 220.76 | 77.7457 | [7 empty] | 24.7686 | 323.2743
Chevron Corporation |  |  |  | 43.2 | 86.4 | 43.2 |  |  |  |  | 172.8
Pasadena Refinery |  |  |  | 43.2 | 86.4 | 43.2 |  |  |  |  | 172.8
CITGO Petroleum Corporation | 19.9429 | 267.2 | 392.14 | 97.8 |  |  | 180.5143 | 187.2 | 33.4286 |  | 1178.2257
Corpus Christi Refinery - West (CITGO) |  |  | 83.7857 | 69.2143 | [6 empty] | 153
Corpus Christi Refinery-East |  |  | 194.3829 | 28.5857 | [6 empty] | 222.9686
Lake Charles Refinery (CITGO) | 19.9429 | 267.2 | 113.9714 |  |  |  | 180.5143 | 187.2 | 33.4286 |  | 802.2571
Deer Park Refining LP | [6 empty] | 27.8679 | 156.06 | 11.1471 |  | 195.075
Deer Park Refinery | [6 empty] | 27.8679 | 156.06 | 11.1471 |  | 195.075
Delek US Holdings | [7 empty] | 115.3286 | 76.8857 |  | 192.2143
Krotz Springs Refinery | [7 empty] | 115.3286 | 76.8857 |  | 192.2143
ExxonMobil Corporation | 433.6786 | 413.7357 | [7 empty] | 18.2286 | 865.6429
Baton Rouge Refinery | 255.2 | 45.5714 | [7 empty] | 18.2286 | 319
Baytown Refinery | 159.1929 | 117.6643 | [8 empty] | 276.8571
Beaumont Refinery | 19.2857 | 250.5 | [8 empty] | 269.7857
Flint Hills Resources LLC | 155.8143 | 155.8143 |  |  |  |  | 91.1429 | 68.3571 |  |  | 471.1286 | [16 empty] | Padd 2
Corpus Christi Refinery - East | [6 empty] | 91.1429 | 68.3571 |  |  | 159.5 | [17 empty] | 2024 | 2025 | 2026
Corpus Christi Refinery - West (Flint Hills) | 155.8143 | 155.8143 | [8 empty] | 311.6286 | [16 empty] | Jan |  | 8.6371
Marathon Petroleum Corporation | 160.8286 | 49.4857 | [8 empty] | 210.3143 |  | 2026 | Column Labels Jun: 97.5169; Column Labels Jul: 84.9839; Column Labels Aug: 119.1549; Column Labels Sep: 231.4272; Column Labels Oct: 165.6249; Column Labels Nov: 76.7683; Column Labels Dec: 30 |  |  | Feb | 13.6 | 36.4554 | 40.3464
Texas City Refinery (Bay Plant) | 160.8286 | 49.4857 | [8 empty] | 210.3143 |  | 2025 | Column Labels Jun: 36.5; Column Labels Jul: 131.6; Column Labels Aug: 97; Column Labels Sep: 203; Column Labels Oct: 280.8; Column Labels Nov: 132; Column Labels Dec: 2 |  |  | Mar | 134.0994 | 280.1621 | 89.5831
Phillips 66 |  | 9 | 157.5 | 22.5 |  |  | 76.56 | 107.184 | 45.936 |  | 418.68 | [16 empty] | Apr | 343.4723 | 383.5415 | 82.4467
Lake Charles Refinery (Phillips 66) | [6 empty] | 76.56 | 107.184 | 45.936 |  | 229.68 | [16 empty] | May | 148.0973 | 110.8806 | 12.0847
Sweeny Refinery |  | 9 | 157.5 | 22.5 | [6 empty] | 189 | [16 empty] | Jun |  | 45.25
Valero Refining Company | 374.16 | 319.5171 | 51.04 |  |  |  | 19.7943 | 277.12 | 98.9714 | 26.7257 | 1167.3286 | [16 empty] | Jul | 3.9167 | 36.1935
McKee Refinery | [6 empty] | 19.7943 | 277.12 | 98.9714 |  | 395.8857 | [16 empty] | Aug | 0 | 42.25
Port Arthur Refinery (Valero) | 170 | 115.3571 | [7 empty] | 12.1429 | 297.5 | [16 empty] | Sep | 212.3433 | 205.0983 | 53.9583
Texas City Refinery | 204.16 | 204.16 | 51.04 | [6 empty] | 14.5829 | 473.9429 | [16 empty] | Oct | 347.7645 | 110.3992 | 64.75
Vertex Energy | [6 empty] | 3.2786 | 45.9 | 8.1964 |  | 57.375 |  |  | 347.1826 | 441.122 | 724.3867 | 672.1815 | 233.3165 | 75.5092 | 52.5355 | 44.8242 | 490.2073 | 605.1776 | 201.0267 | 96.5261 |  |  | Nov | 43.5617 | 10.7683
Mobile Refinery (Vertex) | [6 empty] | 3.2786 | 45.9 | 8.1964 |  | 57.375 |  | Mobile Refinery (Vertex) | Column Labels Jul: 0; Column Labels Aug: 0
[12 empty] | ‘25, 24, '22 & '23 Planned & Unplanned | 2026 Plan + Unplanned | Column Labels Jun: -3.4104; Column Labels Jul: 84.9839; Column Labels Aug: 101.9113; Column Labels Sep: 216.295; Column Labels Oct: 128.7919; Column Labels Nov: 76.7683; Column Labels Dec: 30 |  | 90.7628
[13 empty] | 2025 Outages | Column Labels Jul: 131.6; Column Labels Aug: 97; Column Labels Sep: 203; Column Labels Oct: 280.8; Column Labels Nov: 132; Column Labels Dec: 2 |  | 141.0667
[13 empty] | vs 2026 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -35.42% | 5.063% | 6.549% | -54.13% | -41.84% | 1400% |  | -35.66%
[13 empty] | 2024 Outages | Column Labels Jul: 36.5; Column Labels Aug: 131.6; Column Labels Sep: 97; Column Labels Oct: 203; Column Labels Nov: 280.8; Column Labels Dec: 132 | 2 | 146.8167
[13 empty] | vs 2026 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 132.8% | -22.56% | 123% | -36.56% | -72.66% | -77.27% | #REF! | -38.18%
2026 | [12 empty] | 2023 Outages | 290.5531 | 234.397 | 282.9688 | 366 | 207.1753 | 86.4187 | 74.094 | 22.6677 | 242.7564 | 308.8098 | 71.48 | 15 | 183.5267 | 117.3181
Sum of Gasoline Production Offline (KBD) | Column Labels | [11 empty] | vs 2026 | -100% | -100% | -100% | -100% | -100% | -103.9% | 14.7% | 349.6% | -10.9% | -58.29% | 7.398% | 100% | #REF! | -22.64%
| Jan | Feb | Mar | Apr | May | Jun | Sep | Oct | Nov | Grand Total |  | ‘25 Planned vs'24, '23 & '22 Planned ONLY | 2026 Plan | 0 | 40.3464 | 89.5831 | 82.4467 | 12.0847 | 0 | 29.9839 | 53 | 198.015 | 99.9153 | 10.7683 | 0 | 43.4086 | 55.9546 |  | -2535.0235 | -92.0454
Row Labels | [12 empty] | 2025 Outages | 0 | 13.6 | 135.1494 | 343.6473 | 148.0973 | 0 | 4.0733 | 6.9194 | 199.5933 | 280.5645 | 44.4967 | 0 | 50.7826 | 76.521
1 |  |  |  | 32.3 | [5 empty] | 32.3 |  |  | vs 2026 |  | 196.7% | -33.72% | -76.01% | -91.84% |  | 636.1% | 666% | -0.7908% | -64.39% | -75.8% |  | -14.52% | -26.88%
Trainer Refinery |  |  |  | 32.3 | [5 empty] | 32.3 |  |  | 2024 Outages | 100.9257 | 91.3537 | 131.6945 | 199.056 | 55.6353 | 0 | 12.4747 | 0 | 224.6164 | 270.8811 | 31.5867 | 0 | 108.5459 | 77.0798
2 |  | 40.3464 | 89.5831 | 82.4467 | 12.0847 |  | 53.9583 | 64.75 |  | 343.1692 |  |  | vs 2026 | -100% | -55.83% | -31.98% | -58.58% | -78.28% |  | 140.4% |  | -11.84% | -63.11% | -65.91% |  | -60.01% | -27.41%
El Dorado Refinery (HF Sinclair) |  |  | 18.2903 | 40.5 | [5 empty] | 58.7903 |  |  | 2023 Outages | 0 | 9.83 | 153.454 | 122.558 | 102.2519 | 96.65 | 111.1768 | 97.6143 | 63.7067 | 154.5345 | 69.5303 | 0.66 | 55.9146 | 84.839
Lemont Refinery |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  | vs 2026 |  | 310.4% | -41.62% | -32.73% | -88.18% | -100% | -73.03% | -45.7% | 210.8% | -35.34% | -84.51% | -100% | -22.37% | -34.05%
Robinson Refinery |  |  | 25.5121 | 41.625 | 12.0847 |  |  |  |  | 79.2218
Toledo Refinery (PBF) |  | 40.3464 | 36.4419 | [6 empty] | 76.7884 | [16 empty] | 34.8082
VALERO - MEMPHIS |  |  | 9.3387 | 0.32167 | [5 empty] | 9.6604 |  |  | 2025 Unplanned Outages Estimate | Column Labels Jun: -3.4104; Column Labels Jul: 55; Column Labels Aug: 48.9113; Column Labels Sep: 18.28; Column Labels Oct: 28.8765; Column Labels Nov: 66; Column Labels Dec: 30 |  | 44.3933
Whiting Refinery | [6 empty] | 53.9583 | 64.75 |  | 118.7083 |  |  | 2024 Unplanned Outages | Column Labels Jun: 0; Column Labels Jul: 127.5267; Column Labels Aug: 90.0806; Column Labels Sep: 3.4067; Column Labels Oct: 0.23548; Column Labels Nov: 87.5033; Column Labels Dec: 2 | -50.7826 | 48.763
[13 empty] | 2023 Unplanned Outages | -100.9257 | -91.3537 | -131.6945 | -199.056 | -55.6353 | 0 | 24.0253 | 131.6 | -127.6164 | -67.8811 | 249.2133 | 132 | -19.777 | 32.4791
[13 empty] | 2022 Unplanned Outages | 290.5531 | 224.567 | 129.5148 | 243.442 | 104.9235 | -10.2313 | -37.0828 | -74.9467 | 179.0498 | 154.2753 | 1.9497 | 14.34 | 101.6962
[20 empty] | -88.3943 | -16.9275 | -114.3837 | 87.5031 | 52.0235 | 46.7683
[14 empty] | Column Labels Sep: -13.295; Column Labels Oct: 152.0081; Column Labels Nov: 55.2317; Column Labels Dec: -28 | 0
[14 empty] | Column Labels Sep: -119.295; Column Labels Oct: 74.2081; Column Labels Nov: 204.0317; Column Labels Dec: 102 | 2

## P1 - 2026
| 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
2026 Enhanced Golden Record | 8.853 | 2.1175 | 7.4293 | 1.87 | 5.395 | 37.726 | 0.5984 |  | 9.0475 | 13.09 | 0
2026-06-19 | 8.853 | 2.1175 | 7.4293 | 1.87 | 5.395 | 0.6171 |  |  | 9.0475 | 13.09 | 0
2026 Offline Outage file | 2026-01-01: 0; 2026-02-01: 0; 2026-04-01: 0; 2026-10-01: 7.975; 2026-11-01: 27.5; 2026-12-01: 12.375
m/m |  | 6.7355 | -5.3118 | 5.5593 | -3.525 | -32.331 | 37.1276 | #VALUE! | #VALUE! | -4.0425 | 13.09
changes vs previous | 0 | 0 | 0 | 0 | 0 | -37.1089 | #VALUE! | #VALUE! | 0 | 0 | 0 | #VALUE!

## P2 - 2026
2025 Offline Mogas Production (KBD)
Sum of Capacity Offline for Area Chart (KBD) | Column Labels | [10 empty] | Column Labels
[11 empty] | Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | 1H26 Avg | 2H25 Avg
[29 empty] | jan | feb | mar | apr | may | jun | jul
[28 empty] | 2025 | -47.4305 | -99.6125 | -210.3619 | -371.0731 | -244.7332 | -45.5213 | -38.1777
[29 empty] | 47.4305 | 99.6125 | 210.3619 | 371.0731 | 244.7332 | 45.5213 | 38.1777
[28 empty] | 2024 | -4.4839 | -280.5819 | -110.8161 | -276.655 | -126.3581
[29 empty] | 4.4839 | 280.5819 | 110.8161 | 276.655 | 126.3581
[12 empty] | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
[11 empty] | 2027 Planned outages | 0 | 41.276 | 88.6255 | 160.5717 | 106.838 | 0 | 0 | 0 | 288.9841 | 183.0754 | 1.53 | 0
[12 empty] | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
[11 empty] | 2026 Enhanced Golden Record | 29.843 | 148.1551 | 205.0135 | 234.5592 | 213.5886 | 57.7203 | 1.225 | 0 | 140.3942 | 176.5592 | 93.35 | 0 | [6 empty] | Padd 2 |  |  |  | Sum of [Selected_Measure_Yield] | Column Labels
[12 empty] | -0.44298 | -1.764 | -3.885 | -2.7157 | 0 | -5.5974 | -1.225 | 0 | 5.159 | 1.209 | -10.475 | 0 | [7 empty] | 2024 | 2025 | 2026 |  | 2023 | 2024 | 2025 | 2026
[11 empty] | Planned | 0 | 32.673 | 182.5408 | 178.009 | 74.821 | 0 | 0 | 0 | 140.3942 | 176.5592 | 93.35 | 0 | [6 empty] | Jan |  | 8.6371 |  | Row Labels
[12 empty] | 2026-01-01: 29.843; 2026-02-01: 115.4821; 2026-03-01: 22.4728; 2026-12-01: -116.58 | [6 empty] | Feb | 13.6 | 36.4554 | 146.7214 | Jan | 187.67 | 90 | 29.5063 | 0
[11 empty] | Padd 2 2026 Offline Mogas Production (KBD) | [18 empty] | Mar | 134.0994 | 280.1621 | 155.9282 | Feb | 194.4789 | 103.3662 | 64.859 | 137.8179 | 148.2929
[12 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | 1H26 Avg |  |  |  |  | Apr | 343.4723 | 383.5415 | 148.9717 | Mar | 225.1834 | 163.4002 | 190.2287 | 84.8032 | -8.5468
[9 empty] | 26 ‘25, 24, & '23 Planned & Unplanned |  | 2026 Plan + Unplanned | 29.4 | 146.3911 | 201.1285 | 231.8435 | 213.5886 | 52.1229 | 52.9997 | 54.2307 | 166.9089 | 233.3212 | 132.48 | 15.9 | 83.5948 | 145.7458 | 145.7458 | -23.9161 |  |  | May | 148.0973 | 110.8806 | 23.0298 | Apr | 276.396 | 226.5013 | 351.6278 | 56.0817 | 56.0817
[11 empty] | 2025 Outages | 47.4305 | 99.6125 | 210.3619 | 371.0731 | 244.7332 | 44.76 | 59.687 | 79.65 | 159.2175 | 313.0997 | 83.47 | 15.9 | 144.083 | 169.6619 | 169.6619 |  |  |  | Jun |  | 45.25 |  | May | 137.3374 | 113.0139 | 161.1481 | 11.4532 | 11.4532
El Dorado Refinery (HF Sinclair) | [10 empty] | vs 2026 | -38.01% | 46.96% | -4.389% | -37.52% | -12.73% | 16.45% | -11.2% | -31.91% | 4.831% | -25.48% | 58.72% | 0% | -2.858% | -4.873% | -14.1% |  |  |  | Jul | 3.9167 | 36.1935 |  | Jun | 90 | 45.8047 | 55.68 |  | #VALUE!
Lemont Refinery | [10 empty] | 2024 Outages | 90 | 280.5819 | 163 | 276.655 | 126.3581 | 45 | 131.6 | 97 | 203 | 280.8 | 132 | 2 | 152.3329 | 163.5992 | 163.5992 |  |  |  | Aug | 0 | 42.25 |  | Jul | 100.6787 | 35.7717 | 33.371 |  | -132.48
Ponca City Refinery | [10 empty] | vs 2026 | -67.33% | -47.83% | 23.39% | -16.2% | 69.03% | 15.83% | -59.73% | -44.09% | -17.78% | -16.91% | 0.3636% | 695% | 44.48% | -3.85% | -10.91% |  |  |  | Sep | 212.3433 | 177.5983 | 10.7917 | Aug | 91.4194 | 8.7345 | 41.38
Robinson Refinery | [10 empty] | 2023 Outages | 290.5531 | 234.397 | 282.9688 | 366 | 207.1753 | 86.4187 | 74.094 | 22.6677 | 242.7564 | 308.8098 | 71.48 | 15 | 183.5267 | 244.5855 | 117.3181 |  |  |  | Oct | 347.7645 | 105.9637 | 64.75 | Sep | 323.9498 | 164.105 | 199.916 | 53.9583
Toledo Refinery (PBF) | [10 empty] | vs 2026 | -89.88% | -37.55% | -28.92% | -36.65% | 3.096% | -39.69% | -28.47% | 139.2% | -31.24% | -24.45% | 85.34% | 6% | -6.931% | -38.27% | 24.23% |  |  |  | Nov | 43.5617 | 4.2933 | 6.475 | Oct | 406.7146 | 234.1444 | 131.221 | 64.75
[9 empty] | 26 ‘25, 24, & '23 Planned ONLY |  | 2026 Plan | 0 | 53.057 | 194.7723 | 178.609 | 54.3045 | 0 | 0 | 0 | 145.5532 | 177.7682 | 82.875 | 0 | 83.5948 | 80.1238 | 58.0281 | -5.3086 |  |  | Grand Total | 1246.8552 | 1231.2257 | 556.6678 | Nov | 135.9867 | 62.8742
[11 empty] | 2025 Outages | 8.6371 | 18.35 | 202.0081 | 278.099 | 122.1726 | 19.7 | 36.1935 | 42.5667 | 127.375 | 184.6048 | 32.9167 | 0 | 78.2644 | 108.1611 | 63.3367 | [7 empty] | Dec | 90
[11 empty] | vs 2026 | -100% | 189.1% | -3.582% | -35.78% | -55.55% | -100% | -100% | -100% | 14.27% | -3.703% | 151.8% | #DIV/0! | 6.811% | -17.63% | -8.382% | [7 empty] | Grand Total | 2259.8149 | 1247.716 | 1258.9379 | 290.156
[11 empty] | 2024 Outages | 1e-05 | 13.6 | 135.1494 | 343.6473 | 148.0973 | 0.01 | 4.0733 | 6.9194 | 199.5933 | 280.5645 | 44.4967 | 0.01 | 50.7826 | 106.7507 | 76.5239
[11 empty] | vs 2026 | -100% | 290.1% | 44.12% | -48.03% | -63.33% | -100% | -100% | -100% | -27.08% | -36.64% | 86.25% | -100% | 64.61% | 3.814% | -24.17%
[11 empty] | 2023 Outages | 100.9257 | 91.3537 | 131.6945 | 199.056 | 55.6353 | 0.1 | 12.4747 | 0 | 224.6164 | 270.8811 | 31.5867 | 0.01 | 108.5459 | 96.4609 | 77.0956
[11 empty] | vs 2026 | -100% | -41.92% | 47.9% | -10.27% | -2.392% | -100% | -100% | #DIV/0! | -35.2% | -34.37% | 162.4% | -100% | -22.99% | -34.45% | -24.73%
[11 empty] | 2025 Unplanned Outages | 38.7934 | 81.2625 | 8.3539 | 92.9741 | 122.5606 | 25.06 | 23.4935 | 37.0833 | 31.8425 | 128.4949 | 50.5533 | 15.9 |  | 61.5007 | 44.6325 |  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
[11 empty] | 2024 Unplanned Outages | 90 | 266.9819 | 27.8506 | -66.9923 | -21.7392 | 44.99 | 127.5267 | 90.0806 | 3.4067 | 0.23548 | 87.5033 | 1.99 | 65.8185 | 56.8485 | 54.3195 |  |  | 1 |  |  |  | 32.3
[11 empty] | 2023 Unplanned Outages | 189.6274 | 143.0433 | 151.2743 | 166.944 | 151.54 | 86.3187 | 61.6193 | 22.6677 | 18.14 | 37.9287 | 39.8933 | 14.99 | 90.3322 | 148.1246 | 40.2225 |  |  | 2 |  | 146.7214 | 155.9282 | 148.9717 | 23.0298 |  |  |  | 10.7917 | 64.75 | 6.475
[12 empty] | 106.1403 | 163.7626 | 62.4929 | 64.3086 | 84.1205 | 52.1229 | 70.8798 | 49.9439 | 17.7964 | 55.553 | 59.3167 | 10.96 | 66.4498 |  | 45.2247 |  |  | 3 | 246.1153 | 386.8268 | 206.4347 | 38.3858 | 9.9395 | 2.75 | 0.91935 | 1.1
[12 empty] | 29.4 | 93.3341 | 6.3563 | 53.2345 | 159.2841 | 52.1229 | 52.9997 | 54.2307 | 21.3557 | 55.553 | 49.605 | 15.9 | [5 empty] | 4 |  | 18.75 | 75.5898 | 64.991 | 3.0142 |  |  |  |  | 6.8871 | 15.25 | 2.9516
[29 empty] | 5 | 25.9097 | 8.3725 | 11.34 | 118.5393 | 129.5341 | 117.5567 | 103.05 | 103.05 | 103.05 | 103.05 | 103.05 | 103.05
[11 empty] | 22-23 avg | Jan: 110.6119; Feb: 86.7945; Mar: 86.9187; Apr: 98.4875; May: 88.493; Jun: 60
[12 empty] | Jan: 88.4895; Feb: 86.7945; Mar: 69.5349; Apr: 78.79; May: 70.7944; Jun: 48 | [6 empty] | 272.025 | 560.6707 | 449.2927 | 403.1879 | 165.5176 | 120.3067 | 103.9694 | 104.15 | 113.8417 | 174.6871 | 124.775 | 106.0016
confirm ho wmuch need to change in apr
[11 empty] | 2026-06-19 | 29.4 | 146.3911 | 201.1285 | 231.8435 | 213.5886 | 52.1229 | 52.9997 | 54.2307 | 166.9089 | 233.3212 | 132.48 | 15.9
[13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | mar | apr
[12 empty] | Mobile Refinery (Vertex) | [6 empty] | 0 | 0
[10 empty] | ‘25, 24, '22 & '23 Planned & Unplanned |  | Jan: 2024 Outages; Jul: 36.5; Aug: 131.6; Sep: 97; Oct: 203; Nov: 280.8; Dec: 132 | 2
[12 empty] | Jan: vs 2025; Jul: 36.5; Aug: 131.6; Sep: 97; Oct: 203; Nov: 280.8; Dec: 132 | 2
[12 empty] | Jan: 2023 Outages; Jul: 45.2%; Aug: -58.79%; Sep: 72.07%; Oct: 14.94%; Nov: -52.82%; Dec: -87.95% | 4080%
[12 empty] | vs 2024 | 290.5531 | 234.397 | 282.9688 | 366 | 207.1753 | 86.4187 | 74.094 | 22.6677 | 242.7564 | 308.8098 | 71.48 | 15
[12 empty] | 2022 Outages | -100% | -100% | -100% | -100% | -100% | -38.67% | 77.61% | 327.9% | -16.38% | -9.07% | 84.67% | -86.67%
[12 empty] | vs 2024 | 31.5963 | 40.3757 | 176.017 | 152.589 | 127.6979 | 130.532 | 161.1984 | 183.3307 | 142.3967 | 313.4992 | 236.42 | 214.3106
[12 empty] | 2025 Plan | -100% | -100% | -100% | -100% | -100% | -72.04% | -18.36% | -47.09% | 42.56% | -10.43% | -44.17% | -99.07%
[10 empty] | ‘25 Planned vs'24, '23 & '22 Planned ONLY |  | 2024 Outages | 0 | 13.6 | 135.1494 | 343.6473 | 148.0973 | 0 | 4.0733 | 6.9194 | 199.5933 | 280.5645 | 44.4967 | 0
[12 empty] | vs 2025 | 0 | 13.6 | 135.1494 | 343.6473 | 148.0973 | 0 | 4.0733 | 6.9194 | 199.5933 | 280.5645 | 44.4967 | 0
[12 empty] | 2023 Outages |  | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0%
[12 empty] | vs 2025 | 100.9257 | 91.3537 | 131.6945 | 199.056 | 55.6353 | 0 | 12.4747 | 0 | 224.6164 | 270.8811 | 31.5867 | 0
[12 empty] | 2022 Outages | -100% | -85.11% | 2.623% | 72.64% | 166.2% |  | -67.35% |  | -11.14% | 3.575% | 40.87%
[12 empty] | vs 2025 | 0 | 9.83 | 153.454 | 122.558 | 102.2519 | 96.65 | 111.1768 | 97.6143 | 63.7067 | 154.5345 | 69.5303 | 0.66
[12 empty] | vs 2025 |  | 38.35% | -11.93% | 180.4% | 44.84% | -100% | -96.34% | -92.91% | 213.3% | 81.55% | -36% | -100%
[12 empty] | Jan: 2025 Unplanned Outages Estimate; Jul: 52.2669; Aug: 55; Sep: 66.1549; Oct: 33.4122; Nov: 65.7096; Dec: 66 | 30
[12 empty] | Jan: 2024 Unplanned Outages; Jul: 36.5; Aug: 127.5267; Sep: 90.0806; Oct: 3.4067; Nov: 0.23548; Dec: 87.5033 | 2
[12 empty] | 2023 Unplanned Outages | 189.6274 | 143.0433 | 151.2743 | 166.944 | 151.54 | 86.4187 | 61.6193 | 22.6677 | 18.14 | 37.9287 | 39.8933 | 15
[12 empty] | 2022 Unplanned Outages | 31.5963 | 30.5457 | 22.563 | 30.031 | 25.446 | 33.882 | 50.0216 | 85.7163 | 78.69 | 158.9647 | 166.8897 | 213.6506
Years (Date*) | 2026
Sum of Gasoline Production Offline (KBD) | Column Labels
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Grand Total
1 | Column Labels Apr: 32.3 | 32.3
2 | Column Labels Feb: 146.7214; Column Labels Mar: 155.9282; Column Labels Apr: 148.9717; Column Labels May: 23.0298; Column Labels Sep: 10.7917; Column Labels Oct: 64.75; Column Labels Nov: 6.475 | 556.6678
El Dorado Refinery (HF Sinclair) | Column Labels Mar: 31.0145; Column Labels Apr: 68.675 | 99.6895
Lemont Refinery | Column Labels Mar: 12.1613; Column Labels Apr: 37.7; Column Labels May: 10.9452 | 60.8065
Ponca City Refinery | Column Labels Feb: 98.25; Column Labels Mar: 6.3387 | 104.5887
Robinson Refinery | Column Labels Mar: 25.5121; Column Labels Apr: 41.625; Column Labels May: 12.0847 | 79.2218
Toledo Refinery (PBF) | Column Labels Feb: 40.3464; Column Labels Mar: 36.4419 | 76.7884
Whiting Refinery | Column Labels Sep: 10.7917; Column Labels Oct: 64.75; Column Labels Nov: 6.475 | 82.0167
Wood River Refinery | Column Labels Feb: 8.125; Column Labels Mar: 16.25 | 24.375
VALERO - MEMPHIS | Column Labels Mar: 28.2097; Column Labels Apr: 0.97167 | 29.1813
3 | 246.1153 | 386.8268 | 206.4347 | 38.3858 | 9.9395 | 2.75 | 0.91935 | 1.1 |  |  |  |  | 892.4715
4 | Column Labels Feb: 18.75; Column Labels Mar: 75.5898; Column Labels Apr: 64.991; Column Labels May: 3.0142; Column Labels Oct: 6.8871; Column Labels Nov: 15.25; Column Labels Dec: 2.9516 | 187.4338
5 | 25.9097 | 8.3725 | 11.34 | 118.5393 | 129.5341 | 117.5567 | 103.05 | 103.05 | 103.05 | 103.05 | 103.05 | 103.05 | 1029.5523
Grand Total | 272.025 | 560.6707 | 449.2927 | 403.1879 | 165.5176 | 120.3067 | 103.9694 | 104.15 | 113.8417 | 174.6871 | 124.775 | 106.0016 | 2698.4253

## P3 - 2026
2025 Offline Mogas Production (KBD)
Sum of Capacity Offline for Area Chart (KBD) | Column Labels |  |  |  |  | Column Labels
[5 empty] | Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 1Q25 Total | 1H26 Avg | 2H25 Avg
| 2026-06-26 | 2026-07-03 | 2026-07-10
| 120 | 120
| 840 | 840
[24 empty] | jan | feb | mar | apr | may | jun
[23 empty] | 20205 | -487.3607 | -537.594 | -386.376 | -335.2273 | -215.9835 | -229.8919
[24 empty] | 487.3607 | 537.594 | 386.376 | 335.2273 | 215.9835 | 229.8919
[23 empty] | 2024 | -409.61 | -453.7881 | -496.328 | -262.8671 | -189.1524
[24 empty] | 409.61 | 453.7881 | 496.328 | 262.8671 | 189.1524
116.5
[11 empty] | 44 | 11.6129
*find the 40&20kbd more offline I have in our offline tool vs outages
2027 planned and unplanned outages
[5 empty] | 2027 Planned Outages withLyondell | 346.5679 | 467.3466 | 529.54 | 284.2738 | 139.28 | 189.84 | 189 | 145.69 | 330.3232 | 390.2783 | 214.0517 | 128
[6 empty] | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
[5 empty] | 2027 plan | 218.5679 | 339.3466 | 401.54 | 156.2738 | 11.28 | 61.84 | 61 | 17.69 | 202.3232 | 262.2783 | 86.0517 | 0
[6 empty] | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
[5 empty] | 2026 Enhanced Golden Record | 249.794 | 502.165 | 241.853 | 299.6126 | 192.9869 | 106.7523 | 25.3611 | 13.1595 | 92.5312 | 148.4129 | 36.7412 | 0 | [7 empty] | Sum of Gasoline Production Offline (KBD) | Column Labels
[5 empty] | 2026 Enhanced Golden Record (w. Lyondell) | 377.794 | 630.165 | 369.853 | 427.6126 | 320.9869 | 234.7523 | 153.3611 | 141.1595 | 220.5312 | 276.4129 | 164.7412 | 128 | [7 empty] | Row Labels | 2024 | 2025 | 2026 | Grand Total
[6 empty] | 19.1595 | 3.835 | -9.4005 | -20 | -15.9958 | -11.9031 | -24.2966 | -11.466 | -20.5312 | -23.4129 | -9.2705 | 0
[5 empty] | 2026 planned | 185.6145 | 329.6829 | 117.213 | 44.4987 | 40.3005 | 7.6212 | 17.7211 | 13.1595 | 92.5312 | 148.4129 | 36.7412 | 0 | [7 empty] | Jan | 343.1177 | 288.6903 | 246.1153 | 877.9234
[6 empty] | -95.4072 | 31.906 | -153.9235 | -55.6148 | -38.9924 | 0.84911 | -21.3949 | -79.6344 | -89.7512 | -381.4394 | -165.9042 | 48.2689 | [7 empty] | Feb | 604.0628 | 293.5411 | 386.8268 | 1284.4307
[6 empty] | -258.9535 | -237.0465 | 273.5475 | -47.1601 | 102.6214 | 82.142 | -8.756 | 3.1205 | -82.9502 | -70.6257 | 127.0348 | 68.7569 | [7 empty] | Mar | 235.2453 | 222.9802 | 206.4347 | 664.6602
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | [7 empty] | Apr | 78.8083 | 147.2267 | 38.3858 | 264.4208
|  |  |  | 26 ‘25, 24, & '23 Planned & Unplanned | 2026 Plan + Unplanned | 396.9535 | 634 | 360.4525 | 407.6125 | 304.9911 | 222.8491 | 231.6051 | 228.4846 | 311.4348 | 382.0606 | 255.0258 | 186.2689 | 381.2968 | 387.8098 | 259.6756 | 420.8019 | -62.4064 |  |  | May | 22.755 | 34.5559 | 9.9395 | 67.2504
[5 empty] | 2025 Outages | 492.3607 | 602.094 | 514.376 | 463.2273 | 343.9835 | 222 | 253 | 308.119 | 401.186 | 763.5 | 420.93 | 138 |  | 439.6736 | 358.105 | 483.2083 |  |  |  | Jun | 59.1567 | 17.9333 | 2.75 | 79.84
[5 empty] | vs 2026 | -19.38% | 5.299% | -29.92% | -12.01% | -11.34% | 0.3825% | -8.456% | -25.85% | -22.37% | -49.96% | -39.41% | 34.98% |  | -11.16% | -27.49% |  |  |  |  | Jul | 56.4597 | 1.8581 | 0.91935 | 59.2371
[5 empty] | 2024 Outages | 409.61 | 453.7881 | 496.328 | 262.8671 | 189.1524 | 157 | 229 | 200 | 319 | 349 | 267.4 | 12 | 278.7621 | 328.1243 | 219.0571 |  |  |  |  | Aug | 107.7579 |  | 1.1 | 108.8579
[5 empty] | vs 2026 | -3.09% | 39.71% | -27.38% | 55.06% | 61.24% | 41.94% | 1.138% | 14.24% | -2.372% | 9.473% | -4.628% | 1452% | #REF! | 27.92% | 18.54% |  |  |  |  | Sep | 178.73 | 195.6053 |  | 374.3353
[5 empty] | 2023 Outages | 453.4398 | 503.9216 | 462.3153 | 311.645 | 238.3647 | 246.243 | 142.3857 | 272.1597 | 347.0917 | 570.4327 | 254.687 | 57.1017 | 321.649 | 369.3216 | 270.0145 |  |  |  |  | Oct | 290.5279 | 321.9581 |  | 612.486
[5 empty] | vs 2026 | -12.46% | 25.81% | -22.03% | 30.79% | 27.95% | -9.5% | 62.66% | -16.05% | -10.27% | -33.02% | 0.133% | 226.2% | #REF! | 6.761% | -3.829% |  |  |  |  | Nov | 76.9545 | 40.3383 |  | 117.2928
|  |  |  | 26 ‘25, 24, & '23 Planned ONLY | 2026 Plan | 328.2415 | 558.5161 | 274.2831 | 207 | 193 | 133 | 129.0645 | 129.6935 | 200 | 253 | 155.4708 | 128 | 381.2968 | 282.3401 | 161.1755 |  | -67.6605 |  |  | Grand Total | 2053.5758 | 1564.6873 | 892.4715 | 4510.7346
[5 empty] | 2025 Outages | 251.3355 | 333.2768 | 254.8516 | 301.5283 | 184.6138 | 145.9333 | 129.8581 | 187.6624 | 324.902 | 437.5629 | 247.9333 | 128 | 278.0394 | 245.2566 | 228.836
[5 empty] | vs 2026 | 30.6% | 67.58% | 7.625% | -31.35% | 4.543% | -8.862% | -0.6111% | -30.89% | -38.44% | -42.18% | -37.29% | 0% | 37.14% | 11.69% | -29.57%
[5 empty] | 2024 Outages | 347.9765 | 495 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 158.9967 | 284.1085 | 76.5545 | 0 | 355.7886 | 207.3172 | 104.7996 |  |  |  |  | bi
[5 empty] | vs 2026 | -5.671% | 12.83% | 15.31% | 157.1% | 746.5% | 122.6% | 148.2% | 26.94% | 25.79% | -10.95% | 103.1% | #DIV/0! | 7.169% | 174.8% | 53.79% |  |  |  |  | Sum of [Selected_Measure_Yield] | Column Labels
[5 empty] | 2023 Outages | 238.0785 | 467.7776 | 370.2256 | 218.8543 | 116.5578 | 63.0057 | 1.7407 | 63.729 | 165.4983 | 445.019 | 196.645 | 29.1983 | 355.0578 | 245.7499 | 137.8337 | [5 empty] | 2023 | 2024 | 2025 | 2026
[5 empty] | vs 2026 | 37.87% | 19.4% | -25.91% | -5.417% | 65.58% | 111.1% | 7315% | 103.5% | 20.85% | -43.15% | -20.94% | 338.4% | 7.39% | 33.77% | 16.93% |  |  |  |  | Row Labels
[25 empty] | Jan | 420.2024 | 818.4146 | 288.479 | 182.7468
[5 empty] | 2025 Unplanned Outages | 241.0253 | 268.8172 | 259.5244 | 161.699 | 159.3697 | 76.0667 | 123.1419 | 120.4566 | 76.284 | 325.9371 | 172.9967 | 10 |  | 194.417 | 129.269 |  |  |  |  | Feb | 682.3299 | 1135.9814 | 713.3921 | 301.8155
[5 empty] | 2024 Unplanned Outages | 61.6335 | -41.2119 | 258.4666 | 182.3587 | 166.3523 | 97.2433 | 176.9903 | 97.8292 | 160.0033 | 64.8915 | 190.8455 | 12 | -278.0394 | 120.8071 | 118.9502 |  |  |  |  | Mar | 610.4161 | 587.1049 | 588.2358 | 156.0427
[5 empty] | 2023 Unplanned Outages | 215.3613 | 36.144 | 92.0897 | 92.7907 | 121.8068 | 183.2373 | 140.645 | 208.4307 | 181.5933 | 125.4137 | 58.042 | 27.9033 | 123.6215 | 123.5716 | 132.1808 |  |  |  |  | Apr | 446.3163 | 411.0082 | 78.7308 | 31.1884
[6 empty] | 172.6734 | 116.7892 | 203.3602 | 145.6161 | 149.1763 | 118.8491 | 146.9258 | 142.2388 | 139.2936 | 172.0807 | 124.4437 | 16.6344 | 137.3401 |  | 122.9237 |  |  |  |  | May | 301.5005 | 244.8268 | 6.4919 | 14.5616
[6 empty] | 68.712 | 75.4839 | 86.1694 | 200.6125 | 111.9911 | 89.8491 | 102.5406 | 98.7911 | 111.4348 | 129.0606 | 99.555 | 58.2689 | [7 empty] | Jun | 302.9123 | 184.1195 | 1.6333 | 8.25
[6 empty] | Dec: 93 | [7 empty] | Jul | 259.1439 | 30.4476 | 8.9806
[5 empty] | 22-23 avg | Jan: 169.186; Feb: 114.8116; Mar: 60.9865; Apr: 71.8113; May: 104.6083; Jun: 122; Dec: -34.7311 | [7 empty] | Aug | 278.361 | 69.4065 | 9.6
[6 empty] | Jan: 169.186; Feb: 114.8116; Mar: 60.9865; Apr: 71.8113; May: 104.6083; Jun: 97.6 | [7 empty] | Sep | 528.285 | 113.3707 | 122.007
[25 empty] | Oct | 1096.9484 | 329.23 | 322.8029
[6 empty] | Jan: 524.9535; Feb: 762; Mar: 488.4525; Apr: 535.6126; May: 432.9911; Jun: 350.8491 | [7 empty] | Nov | 620.05 | 166.4423 | 57.4647
[25 empty] | Dec | 230.5596 | 14.501 | 4.6452
[6 empty] | 200.2415 | 430.5161 | 146.2831 | 79 | 65 | 5 | 1.0645 | 1.6935 | 132.0388 | 94.6519 | 27.4708 | 0 | 34.6 | 5.7667 | [5 empty] | Grand Total | 5777.0254 | 4104.8533 | 2202.4635 | 694.605
[6 empty] | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128
[6 empty] | 328.2415 | 558.5161 | 274.2831 | 207 | 193 | 133 | 129.0645 | 129.6935 | 260.0388 | 222.6519 | 155.4708 | 128
[6 empty] | 487.3607 | 537.594 | 386.376 | 335.2273 | 215.9835 | 94.06 | 125.695 | 0 | 0 | 0 | -13 | 0 | 4.8571 | 0 | 25.7486
[6 empty] | 246.3355 | 268.7768 | 126.8516 | 173.5283 | 56.6138 | 17.9333 | 1.8581
[6 empty] | 241.0253 | 268.8172 | 259.5244 | 161.699 | 159.3697 | 76.1267 | 123.8369
[5 empty] | 2026-06-19 | 396.9535 | 634 | 360.4525 | 407.6125 | 304.9911 | 222.8491 | 231.6051 | 228.4846 | 311.4348 | 382.0606 | 255.0258 | 186.2689
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 4240 | 4192.8399
[9 empty] | 4250 | 4352.6214
[10 empty] | 4232.9243 | 4315.0663 | 4306.3103 | 4309.4308 | 4226.4806
[14 empty] | 4318.0102 | 4247.3845
[15 empty] | 4356.5691 | 4483.6039
[16 empty] | 4537.4072 | 4606.164
[6 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
|  |  |  | 26 ‘25, 24, & '23 Planned ONLY | 2026 Plan | 200.2415 | 430.5161 | 146.2831 | 79 | 65 | 5 | 1.0645 | 1.6935 | 132.0388 | 94.6519 | 27.4708 | 0
[5 empty] | 2025 Outages | 246.3355 | 268.7768 | 126.8516 | 173.5283 | 56.6138 | 17.9333 | 1.8581 | 59.6624 | 196.902 | 309.5629 | 119.9333 | 0
[5 empty] | vs 2026 | -18.71% | 60.18% | 15.32% | -54.47% | 14.81% | -72.12% | -42.71% | -97.16% | -32.94% | -69.42% | -77.09% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
[5 empty] | 2024 Outages | 347.9765 | 495 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 158.9967 | 284.1085 | 76.5545 | 0
[5 empty] | vs 2026 | Jan: -42.46%; Feb: -13.03%; Mar: -38.5%; Apr: -1.874%; May: 185.1%; Jun: -91.63%; Jul: -97.95%
[5 empty] | 2023 Outages | 238.0785 | 467.7776 | 370.2256 | 218.8543 | 116.5578 | 63.0057 | 1.7407 | 63.729 | 165.4983 | 445.019 | 196.645 | 29.1983
[5 empty] | vs 2026 | -15.89% | -7.966% | -60.49% | -63.9% | -44.23% | -92.06% | -38.84% | -97.34% | -20.22% | -78.73% | -86.03% | -100% | #DIV/0! | #DIV/0! | #DIV/0!
Note on R55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decreased unplanned layer by 30-35kbd due to preventative maintenance getting pushed due to strong margins

## P4 - 2026
| 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
2026 Enhanced Golden Record | 2026-02-01: 7.3586; 2026-03-01: 26.8152; 2026-04-01: 65.6752; 2026-05-01: 31.8876; 2026-06-01: 2.925; 2026-10-01: 3.3536
2026-06-19 | 2026-02-01: 7.3586; 2026-03-01: 26.8152; 2026-04-01: 65.6752; 2026-05-01: 31.8876; 2026-06-01: 2.925; 2026-10-01: 3.3536
2026 Offline Outage file | 2026-02-01: 18.75; 2026-03-01: 54.9285; 2026-04-01: 50.5308; 2026-05-01: 3.0142; 2026-10-01: 8.1026; 2026-11-01: 2.6101
delta between outage dashboard and manual process | 2026-02-01: 11.3914; 2026-03-01: 28.1134; 2026-04-01: -15.1444; 2026-05-01: -28.8734; 2026-10-01: 4.7489; 2026-11-01: #VALUE!
delta between outage dashboard and previous dashboard |  | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE! | #VALUE! | 0 | #VALUE! | #VALUE!
|  |  | -19.4565 | -38.8601 | 33.7876

## P5 - 2026
P5 2025 Planned Offline Mogas Production (KBD)
|  | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
| 2027 Planned | 62.325 | 74.5459 | 32.1112 | 0.80588 | 8.372 | 0 | 0 | 0 | 42.3095 | 95.1 | 17.7705 | 0
| 2027 Planned with rationalizations | 249.325 | 261.5459 | 219.1112 | 187.8059 | 195.372 | 187 | 187 | 187 | 229.3095 | 282.1 | 204.7705 | 187
| 2026 Planned | 18.624 | 32.3515 | 24.8035 | 45.9172 | 41.4345 | 15.3453 | 24.7857 | 3.5328 | 27.175 | 67.8193 | 59.7753 | 3.12
|  | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
| 2026 Enhanced Golden Record | 90.652 | 130.5155 | 90.9398 | 200.1033 | 94.5135 | 20.3925 | 19.7385 | 3.5328 | 27.175 | 67.8193 | 59.7753 | 3.12 |  |  |  | jan | feb | mar | apr | may | jun
|  | 174.652 | 281.7155 | 277.9398 | 387.1033 | 281.5135 | 207.3925 | 206.7385 | 190.5327 | 214.175 | 254.8193 | 246.7753 | 190.12
|  | 7.3435 | 4.0963 | 16.1612 | 0 | -1.9605 | 21.6313 | 13.844 | -3.5327 | -12.175 | 15.1807 | 12.2247 | 0
|  |  | -103.8164 | 5.7108 | -107.0023 | 107.5503 | 50.5292 | -23.7573 | 34.1383 | -42.1155 | -63.1277 | 10.7628 | 69.8955 |  |  |  | -107.5115 | -160.533 | -206.7556 | -256.9617 | -181.4102 | -102.6137
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |  | 2025 | 107.5115 | 160.533 | 206.7556 | 256.9617 | 181.4102 | 102.6137
26 ‘25, 24, & '23 Planned & Unplanned | 2026 Plan + Unplanned | 181.9955 | 285.8118 | 280.101 | 387.1033 | 279.553 | 229.0238 | 252.7811 | 218.6428 | 260.7583 | 323.886 | 313.1232 | 243.2277 | 374.4063
| 2025 Outages | 107.5115 | 160.533 | 206.7556 | 256.9617 | 181.4102 | 102.614 | 66.1371 | 74.2575 | 103.175 | 322.5731 | 355.53 | 159.79 | 0
| vs 2026 | 69.28% | 78.04% | 35.47% | 50.65% | 54.1% | 123.2% | 282.2% | 194.4% | 152.7% | 0.407% | -11.93% | 52.22% | #DIV/0! |  |  | -76.529 | -123.2759 | -98.3161 | -103.9483 | -100.9484
| 2024 Outages | 76.529 | 123.2759 | 98.3161 | 103.9483 | 100.9484 | 185.8 | 4.2 | 20.7 | 108.1 | 135.2 | 75.9 | 40.5 | 37.6 |  | 2024 | 76.529 | 123.2759 | 98.3161 | 103.9483 | 100.9484
| vs 2026 | 137.8% | 131.8% | 184.9% | 272.4% | 176.9% | 23.26% | 5919% | 956.2% | 141.2% | 139.6% | 312.5% | 500.6% | 895.8%
| 2023 Outages | 125.1 | 118.5 | 126.3 | 17.7 | 93.3 | 30.6 | 20.5 | 30.5 | 37.3 | 156 | 151.7 | 42.5 | 136.6
| vs 2026 | 45.48% | 141.2% | 121.8% | 2087% | 199.6% | 648.4% | 1133% | 616.9% | 599.1% | 107.6% | 106.4% | 472.3% | 174.1%
26 ‘25, 24, & '23 Planned ONLY | 2026 Plan | 110.0842 | 186.08 | 216.8635 | 212.5922 | 210.9683 | 206.9203 | 220.5825 | 187 | 202 | 270 | 259 | 190.12 | 404.6772 | #REF! | #REF!
| 2025 Outages | 67.5194 | 70.9931 | 89.1968 | 102.4 | 41.5323 | 19.7 | 0.77419 | 0.92903 | 38 | 177.1524 | 192.3823 | 93.5745 | 74.5128
| vs 2026 | 63.04% | 162.1% | 143.1% | 107.6% | 408% | 950.4% | 28392% | 20028% | 431.6% | 52.41% | 34.63% | 103.2% | 443.1% |  |  | 25.9097 | 8.3725 | 11.34 | 118.5393 | 129.5341 | 117.5567 | 103.05 | 103.05 | 103.05 | 103.05 | 103.05 | 103.05
| 2024 Outages | 33.1887 | 51.1034 | 71.5433 | 107.3433 | 163.2745 | 151.4 | 3.6 | 1.7 | 6.6 | 8.6 | 2.5 | 0.5 | 158.4 |  |  | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84
| vs 2026 | 231.7% | 264.1% | 203.1% | 98.05% | 29.21% | 36.67% | 6027% | 10900% | 2961% | 3040% | 10260% | 37924% | 155.5% |  |  | 109.9097 | 92.3725 | 95.34 | 202.5393 | 213.5341 | 201.5567 | 187.05 | 187.05 | 187.05 | 187.05 | 187.05 | 187.05
| 2023 Outages | 80.9 | 150.8 | 65 | 132.5 | 93 | 25.1 | 0 | 27.9 | 27.7 | 149.3 | 108.3 | 27 | 32.1
| vs 2026 | 36.07% | 23.4% | 233.6% | 60.45% | 126.8% | 724.4% | #DIV/0! | 570.3% | 629.2% | 80.84% | 139.2% | 604.1% | 1161%
| 2026 Unplanned Outages Estimate | 71.9112 | 99.7318 | 63.2375 | 174.5111 | 68.5847 | 22.1035 | 32.1986 | 31.6428 | 58.7583 | 53.886 | 54.1232 | 53.1077 | -30.2709
| 2025 Unplanned Outages | 39.9921 | 89.5399 | 117.5589 | 154.5617 | 139.8779 | 82.914 | 65.3629 | 73.3285 | 65.175 | 145.4207 | 163.1477 | 66.2155 | -74.5128
| 2024 Unplanned Outages | 43.3403 | 72.1724 | 26.7728 | -3.395 | -62.3261 | 34.4 | 0.6 | 19 | 101.5 | 126.6 | 73.4 | 40 | -120.8
| 2023 Unplanned Outages | 44.2 | -32.3 | 61.3 | -114.8 | 0.3 | 5.5 | 20.5 | 2.6 | 9.6 | 6.7 | 43.4 | 15.5 | 104.5
| 3yr avg | 42.5108 | 43.1375 | 44.0364 | 75.5833 | 139.8779 | 44.207 | 42.9315 | 31.6428 | 58.7583 | 92.9069 | 93.3159 | 53.1077 | -30.2709
|  | 34.0086 | 12.9412 | 44.0364 | 60.4667 | 55.9512 | 22.1035 | 32.1986 | 31.6428 | 58.7583 | 53.886 | 54.1232 | 53.1077 | -30.2709
|  | 107.5115 | 160.533 | 206.7556 | 256.9617 | 181.4102 | 102.6137 | 66.137 | 0 | 0 | 0 | 0 | 0 | 0
|  | -107.5115 | -160.533 | -206.7556 | -256.9617 | -181.4102 | -102.6137 | -66.137
|  | 25.9097 | 8.3725 | 11.34 | 118.5393 | 129.5341 | 117.5567 | 103.05 | -6.6471 | -13.932 | 118.5393 | 105.5792 | 93.6018 | -21.2168
|  | 26.0843 | 34.88 | 29.8635 | 25.5922 | 23.9682 | 19.9202 | 33.5825 |  | 15 | 83 | 72 | 3.12 | 320.6772
| p66 wilimington | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65 | 65
| carson | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19
|  | 110.0842 | 118.88 | 113.8635 | 109.5922 | 107.9682 | 103.9202 | 117.5825 | 84 | 99 | 167 | 156 | 87.12 | 404.6772
| Benicia | 0 | 67.2 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103 | 103
| 2026-06-19 | 181.9955 | 285.8118 | 280.101 | 387.1033 | 279.553 | 229.0238 | 252.7811 | 218.6428 | 260.7583 | 323.886 | 313.1232 | 243.2277
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 958 | -37 |  | 38
|  |  |  | 938.84 | 901.84 |  | 1024
[5 empty] | 944 | 970 | 1025
[5 empty] | 934.56 | 960.3 | 1035 | 998.0438 | 996 | 988 | 910 | 936.3 | 1018.3
[6 empty] | 980 | 1010.02 | 1009 |  | 980 | 937.3
1017
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
26 ‘25, 24, & '23 Planned ONLY | 2026 Plan | 26.0843 | 34.88 | 29.8635 | 25.5922 | 23.9682 | 19.9202 | 33.5825 | 0 | 15 | 83 | 72 | 3.12
| 2025 Outages | Jan: 67.5194; Feb: 70.9931; Mar: 89.1968; Apr: 102.4; May: 41.5323; Jun: 0.77419; Jul: 1.7741935483871=
| vs 2026 | Jan: -61.37%; Feb: -50.87%; Mar: -66.52%; Apr: -75.01%; May: -42.29%; Jun: 2473%
| 2024 Outages | Jan: 61.5; Feb: 72.1; Mar: 72; Apr: 59; May: 119.9; Jun: 151.4; Jul: 3.6
| vs 2026 | -57.59% | -51.62% | -58.52% | -56.62% | -80.01% | -86.84% | 832.8% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| 2023 Outages | Jan: 80.9; Feb: 150.8; Mar: 65; Apr: 132.5; May: 93; Jun: 25.1; Jul: 0
| vs 2026 | Jan: -67.76%; Feb: -76.87%; Mar: -54.06%; Apr: -80.69%; May: -74.23%; Jun: -20.64%; Jul: #DIV/0!
Note on R30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added in 61 kbd from PBF Martinez FCC issue extended through Jan Reply: 3Q25 earning call said SU by end of year ‘25 Reply: IIR updated that Martinez is now starting up through the first 3 weeks in Mar
Note on U30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added 20kbd due to Martinez extending into 4/16 SU Reply: Add 24 more duet o Martinez now on 4/24

## US
2024 Planned Offline Mogas Production
Sum of Capacity Offline for Area Chart (KBD) | Column Labels | [11 empty] | Sum of Capacity Offline for Area Chart (KBD) | Column Labels
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Sep | Oct | Nov | Dec | Grand Total |  | Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Chalmette Refining LLC | 220.76 | 77.7457 | [7 empty] | 24.7686 | 323.2743 |  | Chalmette Refining LLC | 55.19 | 19.4364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1921
Chalmette Refinery | 220.76 | 77.7457 | [7 empty] | 24.7686 | 323.2743 |  | Chalmette Refinery | 55.19 | 19.4364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1921
Chevron Corporation |  |  |  | 43.2 | 86.4 | 43.2 |  |  |  |  | 172.8 |  | Chevron Corporation | 0 | 0 | 0 | 10.8 | 21.6 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0
Pasadena Refinery |  |  |  | 43.2 | 86.4 | 43.2 |  |  |  |  | 172.8 |  | Pasadena Refinery | 0 | 0 | 0 | 10.8 | 21.6 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0
CITGO Petroleum Corporation | 19.9429 | 267.2 | 392.14 | 97.8 |  |  | 180.5143 | 187.2 | 33.4286 |  | 1178.2257 |  | CITGO Petroleum Corporation | 4.9857 | 66.8 | 98.035 | 24.45 | 0 | 0 | 0 | 0 | 45.1286 | 46.8 | 8.3571 | 0
Corpus Christi Refinery - West (CITGO) |  |  | 83.7857 | 69.2143 | [6 empty] | 153 |  | Corpus Christi Refinery - West (CITGO) | 0 | 0 | 20.9464 | 17.3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corpus Christi Refinery-East |  |  | 194.3829 | 28.5857 | [6 empty] | 222.9686 |  | Corpus Christi Refinery-East | 0 | 0 | 48.5957 | 7.1464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lake Charles Refinery (CITGO) | 19.9429 | 267.2 | 113.9714 |  |  |  | 180.5143 | 187.2 | 33.4286 |  | 802.2571 |  | Lake Charles Refinery (CITGO) | 4.9857 | 66.8 | 28.4929 | 0 | 0 | 0 | 0 | 0 | 45.1286 | 46.8 | 8.3571 | 0
Deer Park Refining LP | [6 empty] | 27.8679 | 156.06 | 11.1471 |  | 195.075 |  | Deer Park Refining LP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.967 | 39.015 | 2.7868 | 0
Deer Park Refinery | [6 empty] | 27.8679 | 156.06 | 11.1471 |  | 195.075 |  | Deer Park Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.967 | 39.015 | 2.7868 | 0
Delek US Holdings | [7 empty] | 115.3286 | 76.8857 |  | 192.2143 |  | Delek US Holdings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8321 | 19.2214 | 0
Krotz Springs Refinery | [7 empty] | 115.3286 | 76.8857 |  | 192.2143 |  | Krotz Springs Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8321 | 19.2214 | 0
ExxonMobil Corporation | 433.6786 | 413.7357 | [7 empty] | 18.2286 | 865.6429 |  | ExxonMobil Corporation | 108.4196 | 103.4339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5571
Baton Rouge Refinery | 255.2 | 45.5714 | [7 empty] | 18.2286 | 319 |  | Baton Rouge Refinery | 63.8 | 11.3929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5571
Baytown Refinery | 159.1929 | 117.6643 | [8 empty] | 276.8571 |  | Baytown Refinery | 39.7982 | 29.4161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beaumont Refinery | 19.2857 | 250.5 | [8 empty] | 269.7857 |  | Beaumont Refinery | 4.8214 | 62.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flint Hills Resources LLC | 155.8143 | 155.8143 |  |  |  |  | 91.1429 | 68.3571 |  |  | 471.1286 |  | Flint Hills Resources LLC | 38.9536 | 38.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7857 | 17.0893 | 0 | 0
Corpus Christi Refinery - East | [6 empty] | 91.1429 | 68.3571 |  |  | 159.5 |  | Corpus Christi Refinery - East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7857 | 17.0893 | 0 | 0
Corpus Christi Refinery - West (Flint Hills) | 155.8143 | 155.8143 | [8 empty] | 311.6286 |  | Corpus Christi Refinery - West (Flint Hills) | 38.9536 | 38.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marathon Petroleum Corporation | 160.8286 | 49.4857 | [8 empty] | 210.3143 |  | Marathon Petroleum Corporation | 40.2071 | 12.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Texas City Refinery (Bay Plant) | 160.8286 | 49.4857 | [8 empty] | 210.3143 |  | Texas City Refinery (Bay Plant) | 40.2071 | 12.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phillips 66 |  | 9 | 157.5 | 22.5 |  |  | 76.56 | 107.184 | 45.936 |  | 418.68 |  | Phillips 66 | 0 | 2.25 | 39.375 | 5.625 | 0 | 0 | 0 | 0 | 19.14 | 26.796 | 11.484 | 0
Lake Charles Refinery (Phillips 66) | [6 empty] | 76.56 | 107.184 | 45.936 |  | 229.68 |  | Lake Charles Refinery (Phillips 66) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.14 | 26.796 | 11.484 | 0
Sweeny Refinery |  | 9 | 157.5 | 22.5 | [6 empty] | 189 |  | Sweeny Refinery | 0 | 2.25 | 39.375 | 5.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Valero Refining Company | 374.16 | 319.5171 | 51.04 |  |  |  | 19.7943 | 277.12 | 98.9714 | 26.7257 | 1167.3286 |  | Valero Refining Company | 93.54 | 79.8793 | 12.76 | 0 | 0 | 0 | 0 | 0 | 4.9486 | 69.28 | 24.7429 | 6.6814
McKee Refinery | [6 empty] | 19.7943 | 277.12 | 98.9714 |  | 395.8857 |  | McKee Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9486 | 69.28 | 24.7429 | 0
Port Arthur Refinery (Valero) | 170 | 115.3571 | [7 empty] | 12.1429 | 297.5 |  | Port Arthur Refinery (Valero) | 42.5 | 28.8393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0357
Texas City Refinery | 204.16 | 204.16 | 51.04 | [6 empty] | 14.5829 | 473.9429 |  | Texas City Refinery | 51.04 | 51.04 | 12.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6457
Vertex Energy | [6 empty] | 3.2786 | 45.9 | 8.1964 |  | 57.375 |  | Vertex Energy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.81964 | 11.475 | 2.0491 | 0
Mobile Refinery (Vertex) | [6 empty] | 3.2786 | 45.9 | 8.1964 |  | 57.375 |  | Mobile Refinery (Vertex) | Column Labels Jul: 0; Column Labels Aug: 0
Grand Total | 1365.1843 | 1292.4986 | 600.68 | 163.5 | 86.4 | 43.2 | 399.1579 | 957.1497 | 274.5653 | 69.7229 | 5252.0586 | Mogas Offline [kbd] | 2025 Planned Outages | 347.1826 | 442.0932 | 732.1788 | 711.2982 | 257.0359 | 67.1758 | 46.3258 | 89.7355 | 381.6687 | 515.256 | 124.0017 | 96.5261 | 188.6699
[13 empty] | 2024 planned & unplanned Outages | [5 empty] | 379 | 417 | 327.4 | 654 | 824 | 518 | 77 | 456.6286
[13 empty] | vs 2025 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -82.28% | -88.89% | -72.59% | -41.64% | -37.47% | -76.06% | 25.36% | -58.68%
[13 empty] | 2023 Outages | 948.1503 | 1121.3121 | 1072.6636 | 895.0944 | 581.0282 | 434.4383 | 321.7008 | 341.9938 | 690.8528 | 1141.718 | 496.2403 | 82.5067 | 501.3501
[13 empty] | vs 2025 | -63.38% | -60.57% | -31.74% | -20.53% | -55.76% | -84.54% | -85.6% | -73.76% | -44.75% | -54.87% | -75.01% | 16.99% | -62.37%
[13 empty] | 2022 Outages | 537.7172 | 707.753 | 660.1337 | 645.6753 | 497.8115 | 342.5815 | 348.0777 | 258.9008 | 337.782 | 870.2553 | 488.5903 | 623.9185 | 467.158
[13 empty] | vs 2025 | -35.43% | -37.54% | 10.91% | 10.16% | -48.37% | -80.39% | -86.69% | -65.34% | 12.99% | -40.79% | -74.62% | -84.53% | -59.61%
Grand Total | 169.6695 | 421.0645 | 381.8834 | 352.3235 | 53.7197 | 16.67 |  |  | 53.9583 | 71.6371 | 15.25 | 1536.176
Jun
[13 empty] | 2025 Planned+Unplanned | Column Labels Jun: 153

## US (2026 planned and unplanned) (hidden)
2024 Planned Offline Mogas Production
[16 empty] | Sum of Capacity Offline for Area Chart (KBD) | Column Labels
[16 empty] | Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
[16 empty] | Chalmette Refining LLC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Chalmette Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Chevron Corporation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Pasadena Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | CITGO Petroleum Corporation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Corpus Christi Refinery - West (CITGO) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Corpus Christi Refinery-East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Lake Charles Refinery (CITGO) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Deer Park Refining LP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Deer Park Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Delek US Holdings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Krotz Springs Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | ExxonMobil Corporation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Baton Rouge Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Baytown Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Beaumont Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Flint Hills Resources LLC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Corpus Christi Refinery - East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Corpus Christi Refinery - West (Flint Hills) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Marathon Petroleum Corporation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Texas City Refinery (Bay Plant) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Phillips 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Lake Charles Refinery (Phillips 66) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Sweeny Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Valero Refining Company | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | McKee Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Port Arthur Refinery (Valero) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Texas City Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Vertex Energy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Mobile Refinery (Vertex) | Column Labels Jul: 0; Column Labels Aug: 0
[14 empty] | Mogas Offline [kbd] |  | 2025 Planned Outages | 347.1826 | 442.0932 | 732.1788 | 711.2982 | 257.0359 | 67.1758 | 46.3258 | 89.7355 | 381.6687 | 515.256 | 124.0017 | 96.5261 | 188.6699
[16 empty] | 2024 planned & unplanned Outages | 581 | 905 | 815 | 696 | 460 | 379 | 417 | 327.4 | 654 | 824 | 518 | 77 | 456.6286
[16 empty] | vs 2025 | -40.24% | -51.15% | -10.16% | 2.198% | -44.12% | -82.28% | -88.89% | -72.59% | -41.64% | -37.47% | -76.06% | 25.36% | -58.68%
[16 empty] | 2023 Outages | 948.1503 | 1121.3121 | 1072.6636 | 895.0944 | 581.0282 | 434.4383 | 321.7008 | 341.9938 | 690.8528 | 1141.718 | 496.2403 | 82.5067 | 501.3501
[16 empty] | vs 2025 | -63.38% | -60.57% | -31.74% | -20.53% | -55.76% | -84.54% | -85.6% | -73.76% | -44.75% | -54.87% | -75.01% | 16.99% | -62.37%
[16 empty] | 2022 Outages | 537.7172 | 707.753 | 660.1337 | 645.6753 | 497.8115 | 342.5815 | 348.0777 | 258.9008 | 337.782 | 870.2553 | 488.5903 | 623.9185 | 467.158
[16 empty] | vs 2025 | -35.43% | -37.54% | 10.91% | 10.16% | -48.37% | -80.39% | -86.69% | -65.34% | 12.99% | -40.79% | -74.62% | -84.53% | -59.61%
[16 empty] | 2024 Plan | 347.9765 | 594.7178 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 231.3717 | 310.0705 | 68.0012
[16 empty] | 2024 Plan + Unplanned | 877.8921 | 1086.9943 | 629.3749 | 500.5928 | 225.1081 | 227.2842 | 211.1127 | 122.9935 | 205.6643 | 381.2633 | 74.4243
[17 empty] | 347.1826 | 441.122 | 724.3867 | 672.1815 | 233.3165 | 75.5092 | 52.5355 | 44.8242 | 462.7073 | 600.7421 | 194.5517 | 96.5261
[31 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
[17 empty] | Jan | Feb | Mar | Apr | May | Jun | [7 empty] | 2026 plan | 272.025 | 560.6707 | 449.2927 | 403.1879 | 165.5176 | 120.3067 | 103.9694 | 104.15 | 113.8417 | 174.6871 | 124.775 | 106.0016
[16 empty] | 2025 Planned+Unplanned | 689 | 871 | 871 | 803 | 571 | 305 | 417 | 327.4 | 654 | 824 | 518 | 77 |  | 2025 Planned+Unplanned | -689.2269 | -871.3363 | -931.764 | -1037.8529 | -699.3289 | -432.8089 | -368.5853 | 206.7094 | 511.6953 | 597.1443 | 210.6508 | 146.5261
[16 empty] | 2024 Planned | -689.2269 | -871.3363 | -931.764 | -1037.8529 | -699.3289 | -432.8089 | 417 | 327.4 | 654 | 824 | 518 | 77 |  | 2025 Planned Outages | 347.1826 | 442.0932 | 732.1788 | 711.2982 | 257.0359 | 67.1758 | 46.3258 | 89.7355 | 381.6687 | 515.256 | 124.0017 | 96.5261
[30 empty] | 2024 Plan | 347.9765 | 594.7178 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 231.3717 | 310.0705 | 68.0012 | 0
[16 empty] | 2023 planned and unplaned | -518.5352 | -905.1734 | -815.41 | -696.6437 | -460.2605 | [8 empty] | 2024 Plan + Unplanned | 877.8921 | 1086.9943 | 629.3749 | 500.5928 | 225.1081 | 227.2842 | 211.1127 | 122.9935 | 205.6643 | 381.2633 | 74.4243
[17 empty] | 518.5352 | 905.1734 | 815.41 | 696.6437 | 460.2605 | [8 empty] | 2025 Unplanned Outages Estimate | Jun: 114; Jul: 115.1891; Aug: 116.9739; Sep: 130.0267; Oct: 81.8884; Nov: 86.6491; Dec: 50
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 1Q AVG
|  | 2026 Plan as of Jul'26 | 272.025 | 560.6707 | 449.2927 | 403.1879 | 165.5176 | 120.3067 | 103.9694 | 104.15 | 113.8417 | 174.6871 | 124.775 | 106.0016
26 ‘25, 24, & '23 Planned & Unplanned |  | 2026 Plan + Unplanned Estimate | 668.6844 | 981.8006 | 880.5488 | 883.8361 | 639.2312 | 520.6261 | 477.8932 | 401.4375 | 395.7286 | 450.2785 | 373.0588 | 339.0156 | 843.6779
|  | 2025 Outages | 689.2269 | 871.3363 | 931.764 | 1037.8529 | 699.3289 | 432.8089 | 368.5853 | 206.7094 | 511.6953 | 597.1443 | 210.6508 | 146.5261 | 830.7757
|  | vs 2026 | -2.981% | 12.68% | -5.497% | -14.84% | -8.594% | 20.29% | 29.66% | 94.2% | -22.66% | -24.59% | 77.1% | 131.4% | 1.4% |  |  | april 2025 note: |  | BP Whiting | Cenex McPherson | P66 Wood River | Flint Hills Pine Bend | Cenovus Toledo
|  | 2024 Outages | 518.5352 | 905.1734 | 815.41 | 696.6437 | 460.2605 | 227.2842 | 211.1127 | 122.9935 | 205.6643 | 381.2633 | 74.4243 | 0 | 746.3729
|  | vs 2026 | 28.96% | 8.465% | 7.988% | 26.87% | 38.88% | 129.1% | 126.4% | 226.4% | 92.41% | 18.1% | 401.3% | #DIV/0! | 15.14%
|  | 2023 Outages | 417.9482 | 512.316 | 415.3019 | 283.595 | 218.2303 | 236.043 | 127.5926 | 245.7606 | 323.255 | 530.4058 | 239.637 | 58.0006 | 448.522
|  | vs 2026 | 59.99% | 91.64% | 112% | 211.7% | 192.9% | 120.6% | 274.5% | 63.34% | 22.42% | -15.11% | 55.68% | 484.5% | 87.89%
26 ‘25, 24, & '23 Planned ONLY |  | 2026 Plan | 484.025 | 772.6707 | 661.2927 | 615.1879 | 377.5176 | 332.3067 | 315.9694 | 316.15 | 325.8417 | 386.6871 | 336.775 | 318.0016 | 639.3295
|  | 2025 Outages | 347.1826 | 442.0932 | 732.1788 | 711.2982 | 257.0359 | 67.1758 | 46.3258 | 89.7355 | 381.6687 | 515.256 | 124.0017 | 96.5261 | 507.1515
|  | vs 2026 | 39.42% | 74.78% | -9.682% | -13.51% | 46.87% | 394.7% | 582.1% | 252.3% | -14.63% | -24.95% | 171.6% | 229.4% | 34.84%
|  | 2024 Outages | 347.9765 | 594.7178 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 231.3717 | 310.0705 | 68.0012 | 0 | 393.5185
|  | vs 2026 | 39.1% | 29.92% | 178% | 664.1% | 1556% | 456.1% | 507.5% | 209.4% | 40.83% | 24.71% | 395.2% | #DIV/0! | 82.35%
|  | 2023 Outages | 238.0785 | 467.7776 | 370.2256 | 218.8543 | 116.5578 | 63.0057 | 1.7407 | 63.729 | 165.4983 | 445.019 | 196.645 | 29.1983 | 358.6939
|  | vs 2026 | 103.3% | 65.18% | 78.62% | 181.1% | 223.9% | 427.4% | 18052% | 396.1% | 96.89% | -13.11% | 71.26% | 989.1% | 82.37% | plan+unplan | 584.6844 | 897.8006 | 796.5488 | 799.8361 | 555.2312 | 436.6261 | 393.8932 | 317.4375 | 311.7286 | 366.2785 | 289.0588 | 255.0156
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | plan | 400.025 | 688.6707 | 577.2927 | 531.1879 | 293.5176 | 248.3067 | 231.9694 | 232.15 | 241.8417 | 302.6871 | 252.775 | 234.0016
| 2026 Unplanned estimate 3yr avg |  | 200 | 230 | 230 | 200 | 150 | 230 | 200 | 100 | 80 | 80 | 50 | 25
| 2025 Unplanned |  | 342.0443 | 429.2431 | 199.5852 | 326.5548 | 442.293 | 365.633 | 322.2595 | 116.9739 | 130.0267 | 81.8884 | 86.6491 | 50
| 2024 Unplanned |  | 170.5587 | 310.4556 | 577.5486 | 616.1354 | 437.4603 | 167.5275 | 159.1031 | 20.8227 | -25.7073 | 71.1927 | 6.4231 | 0 |  | adding Lyondell | 584.6844 | 897.8006 | 796.5488 | 799.8361 | 555.2312 | 436.6261 | 393.8932 | 317.4375 | 311.7286 | 366.2785 | 289.0588 | 255.0156
| 2023 Unplanned |  | 179.8697 | 44.5384 | 45.0763 | 64.7407 | 101.6725 | 173.0373 | 125.8519 | 182.0316 | 157.7567 | 85.3868 | 42.992 | 28.8023 |  | adding Lyondell | 400.025 | 688.6707 | 577.2927 | 531.1879 | 293.5176 | 248.3067 | 231.9694 | 232.15 | 241.8417 | 302.6871 | 252.775 | 234.0016
| avg |  | 230.8242 | 261.4124 | 274.07 | 335.8103 | 327.1419 | 235.3993 | 202.4048 | 106.6094 | 87.3587 | 79.4893 | 45.3547 | 26.2674
| 80% avg |  | 184.6594 | 209.1299 | 219.256 | 268.6482 | 261.7136 | 188.3194 | 161.9239 | 85.2875 | 69.8869 | 63.5914 | 36.2838 | 21.0139 |  | without | 456.6844 | 769.8006 | 668.5488 | 671.8361 | 427.2312 | 308.6261 | 265.8932 | 189.4375 | 183.7286 | 238.2785 | 161.0588 | 127.0156
[17 empty] | 272.025 | 560.6707 | 449.2927 | 403.1879 | 165.5176 | 120.3067 | 103.9694 | 104.15 | 113.8417 | 174.6871 | 124.775 | 106.0016
Add lyondell and p66 wilmington and carson
[17 empty] | 668.6844 | 981.8006 | 880.5488 | 883.8361 | 639.2312 | 520.6261 | 477.8932 | 401.4375 | 395.7286 | 450.2785 | 373.0588 | 339.0156
[17 empty] | 484.025 | 772.6707 | 661.2927 | 615.1879 | 377.5176 | 332.3067 | 315.9694 | 316.15 | 325.8417 | 386.6871 | 336.775 | 318.0016

## 1h26 US & PADD (hidden)
Years (Date*) | 2024 | 2025 | 2026 |  | Power BI Dump | [5 empty] | Manual vs Power BI |  | Puwer
|  |  |  | Sum of Gasoline Production Offline (KBD) | [7 empty] | planned
Month | 2024 | 2025 | 2026 |  |  | Sum of [Selected_Measure_Yield] | Column Labels
Jan | 376.3065 | 347.1826 | 272.025 |  |  | Month | 2023 | 2024 | 2025 | 2026
Feb | 706.9118 | 441.122 | 560.6707
Mar | 527.9323 | 724.3867 | 449.2927 |  |  | Jan | 713.5805 | 971.7386 | 372.2221 | 294.7461 | 22.7211
Apr | 572.5773 | 672.1815 | 403.1879 |  |  | Feb | 1128.2901 | 1337.8524 | 839.7221 | 468.1188 | -92.552
May | 346.6386 | 233.3165 | 165.5176 |  |  | Mar | 1003.2088 | 915.4166 | 865.886 | 527.3745 | 78.0818
Jun | 107.33 | 75.5092 | 120.3067 |  |  | Apr | 918.9397 | 771.2802 | 562.4442 | 274.5395 | -128.6483
Jul | 60.3763 | 52.5355 | 103.9694 |  |  | May | 604.21 | 477.8011 | 278.0742 | 61.0961 | -104.4216
Aug | 132.1869 | 44.8242 | 104.15 |  |  | Jun | 424.2943 | 372.3035 | 69.5495 | 18.6567 | -101.65
Sep | 443.1947 | 462.7073 | 113.8417 |  |  | Jul | 388.189 | 69.6193 | 42.8529 |  | -103.9694
Oct | 662.2044 | 600.7421 | 174.6871 |  |  | Aug | 536.0863 | 81.141 | 50.98 |  | -104.15
Nov | 122.8495 | 194.5517 | 124.775 |  |  | Sep | 928.4328 | 327.857 | 343.231 |  | -113.8417
Dec | 6.4581 | 96.5261 | 106.0016 |  |  | Oct | 1775.1201 | 593.5463 | 566.1884 |  | -174.6871
Grand Total |  |  | 2698.4253 |  |  | Nov | 913.2073 | 231.7915 | 130.427 |  | -124.775
[6 empty] | Dec | 348.5878 | 14.98 | 4.6452 |  | -106.0016
[6 empty] | Grand Total | 9682.1468 | 6165.3275 | 4126.2226 | 1644.5317 | -1053.8937
Padd 3
Jan | 343.1177 | 288.6903 | 246.1153 |  |  | Sum of [Selected_Measure_Yield] | Column Labels
Feb | 604.0628 | 293.5411 | 386.8268 |  |  |  | 2023 | 2024 | 2025 | 2026
Mar | 235.2453 | 222.9802 | 206.4347 |  |  | Row Labels
Apr | 78.8083 | 147.2267 | 38.3858 |  |  | Jan | 420.2024 | 818.4146 | 288.479 | 182.7468 | -63.3685
May | 22.755 | 34.5559 | 9.9395 |  |  | Feb | 682.3299 | 1135.9814 | 713.3921 | 301.8155 | -85.0113
Jun | 59.1567 | 17.9333 | 2.75 |  |  | Mar | 610.4161 | 587.1049 | 588.2358 | 156.0427 | -50.392
Jul | 56.4597 | 1.8581 | 0.91935 |  |  | Apr | 446.3163 | 411.0082 | 78.7308 | 31.1884 | -7.1974
Aug | 107.7579 |  |  |  |  | May | 301.5005 | 244.8268 | 6.4919 | 14.5616 | 4.6221
Sep | 178.73 | 195.6053 |  |  |  | Jun | 302.9123 | 184.1195 | 1.6333 | 8.25 | 5.5
Oct | 290.5279 | 321.9581 |  |  |  | Jul | 259.1439 | 30.4476 | 8.9806 |  | -0.91935
Nov | 76.9545 | 40.3383 |  |  |  | Aug | 278.361 | 69.4065 | 9.6
[6 empty] | Sep | 528.285 | 113.3707 | 122.007
[6 empty] | Oct | 1096.9484 | 329.23 | 322.8029
[6 empty] | Nov | 620.05 | 166.4423 | 57.4647
[6 empty] | Dec | 230.5596 | 14.501 | 4.6452
[6 empty] | Grand Total | 5777.0254 | 4104.8533 | 2202.4635 | 694.605
Padd 2
| 2024 | 2025 | 2026
Jan |  | 8.6371 |  |  |  | Sum of [Selected_Measure_Yield] | Column Labels
Feb | 13.6 | 36.4554 | 146.7214 |  |  |  | 2023 | 2024 | 2025 | 2026
Mar | 134.0994 | 280.1621 | 155.9282 |  |  | Row Labels
Apr | 343.4723 | 383.5415 | 148.9717 |  |  | Jan | 187.67 | 90 | 29.5063 | 0
May | 148.0973 | 110.8806 | 23.0298 |  |  | Feb | 194.4789 | 103.3662 | 64.859 | 137.8179 | -8.9036
Jun |  | 45.25 |  |  |  | Mar | 225.1834 | 163.4002 | 190.2287 | 84.8032 | -71.125
Jul | 3.9167 | 36.1935 |  |  |  | Apr | 276.396 | 226.5013 | 351.6278 | 56.0817 | -92.89
Aug | 0 | 42.25 |  |  |  | May | 137.3374 | 113.0139 | 161.1481 | 11.4532 | -11.5766
Sep | 212.3433 | 177.5983 | 10.7917 |  |  | Jun | 90 | 45.8047 | 55.68 |  | 0
Oct | 347.7645 | 105.9637 | 64.75 |  |  | Jul | 100.6787 | 35.7717 | 33.371 |  | 0
Nov | 43.5617 | 4.2933 | 6.475 |  |  | Aug | 91.4194 | 8.7345 | 41.38
Grand Total | 1246.8552 | 1231.2257 | 556.6678 |  |  | Sep | 323.9498 | 164.105 | 199.916 | 53.9583
[6 empty] | Oct | 406.7146 | 234.1444 | 131.221 | 64.75
[6 empty] | Nov | 135.9867 | 62.8742
[6 empty] | Dec | 90
[6 empty] | Grand Total | 2259.8149 | 1247.716 | 1258.9379 | 290.156
Padd 5
Jan | 33.1887 | 38.5258 | 25.9097
Feb | 51.1034 | 67.8286 | 8.3725 |  |  | Sum of [Selected_Measure_Yield] | Column Labels
Mar | 71.5433 | 180.2065 | 11.34 |  |  |  | 2023 | 2024 | 2025 | 2026
Apr | 105.2433 | 109.6483 | 118.5393 |  |  | Row Labels
May | 161.9584 | 72.7323 | 129.5341 |  |  | Jan | 64.6148 | 57.7355 | 54.2368 | 111.9994
Jun | 48.1733 |  | 117.5567 |  |  | Feb | 121.1325 | 59.781 | 34.6703 | 23.0064
Jul |  | 14.4839 | 103.05 |  |  | Mar | 48.76 | 48.5739 | 41.1097 | 54.32
Aug | 21.429 | 2.5742 | 103.05 |  |  | Apr | 122.6148 | 54.3384 | 91.32 | 21.5423
Sep | 4.95 | 82.6033 | 103.05 |  |  | May | 99.7547 | 110.4329 | 75.1935 | 32.5145
Oct | 4.0806 | 167.3852 | 103.05 |  |  | Jun | 25.1317 | 142.3793 | 0.26 | 10.4067
Nov |  | 149.92 | 103.05 |  |  | Jul |  | 2.7226 | 0
Dec | 6.4581 | 93.5745 | 103.05 |  |  | Aug | 27.871 |  | 0
[6 empty] | Sep | 20.0633 | 6.6 | 18.2313
[6 empty] | Oct | 149.2665 | 8.6226 | 105.7623
[6 empty] | Nov | 108.3173 | 2.475 | 72.9623
[6 empty] | Dec | 24.8944 | 0.47903
[6 empty] | Grand Total | 812.421 | 494.1402 | 493.7462 | 253.7893

## June Monthly updated 725 (hidden)
P3 / Other | PADD | Gas Production Offline (kbd) | % Gas Prod offline vs PADD Gas Prod | Planned Start | Planned End | Units |  | Notes | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 1900-01-30 | Missing data check | time axis 2023-11-03 to 2026-07-17
CVR Coffeyville | 2 |  | 0% | 2024-01-02 | 2024-01-05 | Coker (26) |  |  | 0 | [12 empty] | Missing
Pemex Deer Park | 3 |  | 0% | 2024-01-05 | 2024-01-07 | HCC (67) |  |  | 0 | [12 empty] | Missing
El Segundo | 5 |  | 0% | 2023-12-26 | 2024-01-08 | HCC (45), FCC (73), Alky (33), hydrogen plant | [15 empty] | OK | 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Houston | 3 |  | 0% | 2024-01-06 | 2024-01-08 | DC 736 (42) |  |  | 0 | [12 empty] | Missing
Monroe Trainer | 1 | 100 | 20.83% | 2024-01-09 | 2024-01-11 | CDU(x2)/FCC/Alky/Reformer/HDC | Unplanned - Up Updated gas offline from 30kbd to 100 | Whole refinery down due to power outage, then slow restart on 1/11 until 1/17 | -6.4516 | [12 empty] | OK | 2024-01-12: -57.1429; 2024-01-26: 57.1429
Total Port Arthur | 3 | 30 | 0.6522% | 2024-01-11 | 2024-01-12 | FCC (80), CDU (60) | Unplanned - Up, cut back until 1/16 when it SD for freeze | was Assuming full rate 1/18 then SD for freeze | -0.96774 | [12 empty] | OK | 2024-01-12: -4.2857; 2024-01-19: -12.8571
Cenex McPherson | 2 |  | 0% | 2024-01-13 | 2024-01-15 | CR (24) | removed |  | 0 | [12 empty] | Missing
Houston | 3 |  | 0% | 2024-01-06 | 2024-01-16 | Coker (57) |  |  | 0 | [12 empty] | Missing
Valero Houston | 3 | 10 | 0.2174% | 2024-01-16 | 2024-01-18 | Reduced rate. Assuming crude shed 45kbd | vs original |  | -0.64516 | [12 empty] | OK | 2024-01-19: -4.2857; 2024-01-26: 4.2857
Corpus Christi (West) | 3 |  | 0% | 2024-01-07 | 2024-01-19 | HCC (49) |  |  | 0 | [12 empty] | Missing
Marathon Garyville | 3 | 45 | 0.9783% | 2024-01-15 | 2024-01-19 | CDU/VDU | Freeze. Same Crude unit that has planned TA on 1/19, Updating outage to 9/17 based on flaring on 9/16 |  | -5.8065 | [12 empty] | OK | 2024-01-19: -25.7143
HF Sinclair Anacortes | 5 | 17 | 1.259% | 2024-01-15 | 2024-01-19 | SD Coker and reduce crude 45kbd | Freeze. Up |  | -2.1935 | [12 empty] | OK | 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
FH Corpus West | 3 | 54.995 | 1.196% | 2024-01-15 | 2024-01-19 | CDU SD / Reduced rate at the FCC | Freeze. Up. Updated from 1/16-1/23 |  | -7.0961 | [12 empty] | OK | 2024-01-19: -31.4257; 2024-01-26: 20.9505; 2024-02-02: 10.4752
XOM Baytown | 3 | 15 | 0.3261% | 2024-01-16 | 2024-01-19 | Crude shed of 70kbd | Freeze. |  | -1.4516 | [12 empty] | OK | 2024-01-19: -6.4286; 2024-01-26: 6.4286
XOM Baton Rouge | 3 | 10 | 0.2174% | 2024-01-16 | 2024-01-19 | Crude shed of 45kbd | Freeze. |  | -0.96774 | [12 empty] | OK | 2024-01-19: -4.2857; 2024-01-26: 4.2857
Valero Texas City | 3 | 10 | 0.2174% | 2024-01-16 | 2024-01-19 | Complex 4 reduced rate. Assuming crde shed 50kbd | Freeze. |  | -0.96774 | [12 empty] | OK | 2024-01-19: -4.2857; 2024-01-26: 4.2857
P66 Wood River | 2 | 23 | 0.9583% | 2024-01-16 | 2024-01-19 | Upset assuming reduced crude ~115kbd | Freeze. |  | -2.2258 | [12 empty] | OK | 2024-01-19: -9.8571; 2024-01-26: 9.8571
Marathon Galveston Bay | 3 |  | 0% | 2024-01-18 | 2024-01-19 | CDU (50) |  |  | 0 | [12 empty] | OK | 2024-02-02: 1.8571; 2024-03-29: -16; 2024-04-05: -4; 2024-04-12: 8; 2024-04-19: 2.5
El Paso | 3 |  | 0% | 2024-01-23 | 2024-01-25 | FCCU (29.5) |  |  | 0 | [12 empty] | OK | 2024-02-02: 5.4786
Citgo Lake Charles | 3 | 45 | 0.9783% | 2024-01-08 | 2024-01-26 | Ref | Down - Unplanned. Assuming SU by 1/26 | Only from Genscape | -26.129 | [12 empty] | OK | 2024-01-12: #REF!; 2024-01-19: #REF!; 2024-01-26: #REF!; 2024-02-02: #REF!
Lake Charles | 3 |  | 0% | 2024-01-17 | 2024-01-26 | HCC (50) |  |  | 0 | [12 empty] | OK | 2024-02-02: 2.5
Cenovus Lima | 2 | 7 | 0.2917% | 2024-01-19 | 2024-01-29 | Coker SD due to instrument issue due to cold | Freeze. Assuming up 1/29 |  | -2.2581 | [12 empty] | OK | 2024-01-26: -7; 2024-02-02: -10; 2024-02-09: 17
Port Allen | 3 |  | 0% | 2024-01-12 | 2024-01-30 | lone crude, CCR (11), Rose unit |  |  | 0 | [12 empty] | OK | 2024-02-02: 17.6
Delek Big Spring | 3 | 18 | 0.3913% | 2024-01-15 | 2024-01-30 | Reduced rate at the 73kbd Ref | Freeze. |  | -8.7097 | [12 empty] | OK | 2024-01-19: -38.5714; 2024-02-09: 38.5714
Denver | 4 |  | 0% | 2024-01-16 | 2024-01-30 | CDU 1 (32) |  |  | 0 | [12 empty] | OK | 2024-02-02: 7.1314
Benicia | 5 |  | 0% | 2024-01-28 | 2024-02-01 | CR (40) |  |  | 0 | 0 | [11 empty] | OK | 2024-02-02: -24.2857; 2024-02-09: 24.2857; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Salt Lake City | 4 |  | 0% | 2024-01-30 | 2024-02-01 | CDU (57.6), VDU (27.5) |  |  | 0 | 0 | [11 empty] | OK | 2024-02-02: -6.1714; 2024-02-09: 6.1714
Denver | 4 |  | 0% | 2024-01-16 | 2024-02-05 | CDU 1 (32) |  |  | 0 | 0 | [11 empty] | OK | 2024-02-09: 4.7543; 2024-02-16: 3.5657
Chevron Pascagoula | 3 | 45 | 0.9783% | 2024-02-04 | 2024-02-09 | Reformer (55) | Up per genscape - Unplanned outage. |  |  | -7.7586 | [11 empty] | OK | 2024-02-09: -38.5714; 2024-02-16: 19.2857; 2024-02-23: 19.2857
Corpus Christi (West) | 3 |  | 0% | 2024-02-08 | 2024-02-09 | CDU (75), VDU (23) |  |  |  | 0 | [11 empty] | OK | 2024-02-09: -2.1429; 2024-02-16: 2.1429
Suncor Commerce City | 4 | 7 | 2.059% | 2024-01-16 | 2024-02-14 | SD CDU | Freeze. Up |  | -3.3871 | -3.1379 | [11 empty] | OK | 2024-01-19: -29; 2024-01-26: 22; 2024-02-23: 7
PBF Paulsboro | 1 |  | 0% | 2024-02-06 | 2024-02-14 | CR (32) |  |  |  | 0 | [11 empty] | OK | 2024-02-09: -11.6571; 2024-02-16: -3.8857; 2024-02-23: 15.5429
Lake Charles | 3 |  | 0% | 2024-01-08 | 2024-02-17 | CR (53.2) |  |  | 0 | 0 | [11 empty] | Missing
Total Port Arthur | 3 | 117 | 2.543% | 2024-01-16 | 2024-02-17 | CDU/Coker/FCC/Reformer (all) | Up 7/17 & FCC up 2/15. Unplanned Freeze. |  | -56.6129 | -64.5517 | [11 empty] | OK | 2024-01-19: -534.8571; 2024-01-26: 417.8571; 2024-02-16: 4.9524; 2024-02-23: 18.6083; 2024-03-01: 2.2643; 2024-03-08: 91.175
PBF Chalmette | 3 | 17.325 | 0.3766% | 2024-01-15 | 2024-02-18 | VDU | Up. Delayed SU vs 2/4 |  | -8.9419 | -10.156 | [11 empty] | OK | 2024-01-19: 112132.35; 2024-01-26: -112149.675; 2024-02-23: -112216.5; 2024-03-01: 112233.825
XOM Baton Rouge | 3 | 50 | 1.087% | 2024-02-11 | 2024-02-20 | Reformer | Up 2/18. Planned SD added to reapair leak. |  |  | -15.5172 | [11 empty] | Missing
Billings | 4 |  | 0% | 2024-02-09 | 2024-02-22 | Coker (16), Crude (35) |  |  |  | 0 | [11 empty] | OK | 2024-02-16: -15.3; 2024-03-01: 7; 2024-03-22: 4.1; 2024-03-29: 4.2
Richmond | 5 |  | 0% | 2024-02-17 | 2024-02-23 | FCCU (80) |  |  |  | 0 | [11 empty] | OK | 2024-02-23: -13; 2024-03-01: -13; 2024-03-08: 13; 2024-03-15: 13; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Baton Rouge | 3 | 70 | 1.522% | 2024-01-22 | 2024-02-24 | FCC/HDC | HDC up 2/24 and FCC up 2/29 |  | -20.3226 | -55.5172 | [11 empty] | OK | 2024-01-26: #REF!; 2024-02-02: #REF!; 2024-03-01: 1.35; 2024-03-08: 35; 2024-03-15: 33.65
Marathon Garyville | 3 | 65 | 1.413% | 2024-01-19 | 2024-02-25 | CDU/Coker/HDC | Up on 2/25 vs 3/1 |  | -25.1613 | -53.7931 | [11 empty] | OK | 2024-01-26: -65; 2024-03-01: -210539.6429; 2024-03-08: -210539.6429; 2024-03-15: 421144.2857
Marathon Carson | 5 | 105 | 7.778% | 2024-01-12 | 2024-02-26 | CDU/HDC/Reformer/FCC | Up per genscape |  | -64.3548 | -90.5172 | [11 empty] | OK | 2024-01-19: -52.5; 2024-01-26: -52.5; 2024-03-01: 35; 2024-03-08: 48; 2024-03-15: 22; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Sweeny | 3 |  | 0% | 2024-02-09 | 2024-02-26 | Heavy Oil Cracker 27.1 (78) |  |  |  | 0 | [11 empty] | OK | 2024-02-16: -3.9; 2024-03-01: 2.2286; 2024-03-08: 1.6714
PBF Torrance | 5 |  | 0% | 2024-02-10 | 2024-02-26 | CDU (155), FCC (100), HF Alky (25.5)FCCU (105), HCC (24), Vac (98) |  |  |  | 0 | [11 empty] | OK | 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Carson | 5 |  | 0% | 2024-01-16 | 2024-02-27 | HCC (55) |  |  | 0 | 0 | [11 empty] | OK | 2024-03-01: 1.1786; 2024-03-08: 1.5714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Baytown | 3 | 55.25 | 1.201% | 2024-01-17 | 2024-02-27 | Reformer | Up |  | -24.9516 | -49.5345 | [11 empty] | OK | 2024-01-19: 357687.3724; 2024-01-26: -357742.6224; 2024-03-01: -238622.119; 2024-03-08: 238667.369; 2024-03-15: 10
Houston Refinery | 3 | 17.1 | 0.3717% | 2024-02-02 | 2024-02-28 | Coker | Up 2/28 vs 3/1 |  |  | -15.8786 | [11 empty] | OK | 2024-02-09: -17.1; 2024-03-01: 2.4429; 2024-03-08: 9.6571; 2024-03-15: 5
Houston | 3 |  | 0% | 2024-02-03 | 2024-02-28 | Heavy crude (147), DC (42) |  |  |  | 0 | [11 empty] | Missing
P66 Sweeny | 3 | 50 | 1.087% | 2024-02-09 | 2024-02-28 | FCC | Up. Unplanned SD |  |  | -32.7586 | [11 empty] | OK | 2024-02-16: -25; 2024-02-23: -25; 2024-03-01: 9.5238; 2024-03-08: 25; 2024-03-15: 15.4762
Valero Ardmore | 2 |  | 0% | 2024-02-26 | 2024-02-28 | Gas oil HT (32), HCC (12) |  |  |  | 0 | [11 empty] | Missing
Motiva Port Arthur | 3 | 100 | 2.174% | 2024-01-08 | 2024-02-29 | CDU/coker/HDS | CDU up on 2/16 Coker Up on 2/29 |  | -74.1935 | -96.5517 | [11 empty] | OK | 2024-01-12: #REF!; 2024-01-19: #REF!; 2024-02-23: 43.55; 2024-03-01: #REF!; 2024-03-08: #REF!; 2024-03-15: #REF!
XOM Baton Rouge | 3 |  | 0% | 2024-01-24 | 2024-03-01 | PCLA 2 FCCU (110) |  |  | 0 |  | 0 | [10 empty] | Missing
HF Tulsa East | 2 | 27.3 | 1.137% | 2024-02-11 | 2024-03-01 | CDU,FCC, alky, Reformer & coker from West | Up |  |  | -16.9448 | 0 | [10 empty] | OK | 2024-02-16: 176798.7; 2024-02-23: -7.8; 2024-03-08: 19.5; 2024-03-15: 7.8
XOM Joliet | 2 | 60 | 2.5% | 2024-02-25 | 2024-03-01 | FCC/alky | Unplanned SD. SU 3/1 |  |  | -8.2759 | 0 | [10 empty] | OK | 2024-03-01: #REF!; 2024-03-15: 21
Valero Ardmore | 2 |  | 0% | 2024-02-26 | 2024-03-02 | HC (14), ULSD HT (32) |  |  |  | 0 | 0 | [10 empty] | Missing
Tulsa West | 2 |  | 0% | 2024-02-27 | 2024-03-02 | CDU (91), VDU |  |  |  | 0 | 0 | [10 empty] | Missing
BP Whiting | 2 |  | 0% | 2024-02-01 | 2024-03-03 | CR (70) |  |  |  | 0 | 0 | [10 empty] | Missing
P66 Ponca City | 2 | 14 | 0.5833% | 2024-02-05 | 2024-03-03 | Reformer | Up | updated Sd from 2/1 to 2/5 |  | -11.5862 | -0.90323 | [10 empty] | OK | 2024-02-09: -22.95; 2024-03-08: 14.3438; 2024-03-15: 8.6062
Tulsa (East) | 2 |  | 0% | 2024-02-11 | 2024-03-03 | CDU (75.5), Naphtha HT (15.5) |  |  |  | 0 | 0 | [10 empty] | Missing
P66 Borger | 3 | 20 | 0.4348% | 2023-09-29 | 2024-03-04 | FCC 29 | Up | 41.6 |  |  | -1.9355 | [10 empty] | OK | 2024-03-08: 12.5714; 2024-03-15: 7.4286
Citgo Lake Charles | 3 | 20 | 0.4348% | 2024-01-19 | 2024-03-04 | Reformer A then B | Up. Genscape reported SU 2/18. delayaed from 2/24 Sd |  | -7.7419 |  | -1.9355 | [10 empty] | OK | 2024-01-26: -20; 2024-03-08: -129585.7143; 2024-03-15: 129605.7143
BP Whiting | 2 |  | 0% | 2024-02-01 | 2024-03-04 | cat feed HT (100) |  |  |  | 0 | 0 | [10 empty] | Missing
Valero McKee | 3 |  | 0% | 2024-03-01 | 2024-03-04 | CR (28.9), HC (29.5) |  |  |  |  | 0 | [10 empty] | OK | 2024-03-08: -10.5279; 2024-03-15: 10.5279
BP Whiting | 2 | 240.45 | 10.02% | 2024-02-01 | 2024-03-05 | Refinery Wide Outage | Up |  |  | -232.1586 | -31.0258 | [10 empty] | OK | 2024-02-02: -51.525; 2024-02-09: -188.925; 2024-03-08: #REF!; 2024-03-15: #REF!; 2024-03-22: #REF!; 2024-03-29: #REF!
PBF Martinez | 5 |  | 0% | 2024-02-12 | 2024-03-06 | Flexicoker (22.5) |  |  |  | 0 | 0 | [10 empty] | OK | 2024-03-08: 3.375; 2024-03-15: 3.375; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Galv Bay | 3 | 120 | 2.609% | 2024-02-27 | 2024-03-06 | Ref 3/Ref 4 | Up |  |  | -8.2759 | -19.3548 | [10 empty] | OK | 2024-03-01: #REF!; 2024-03-08: #REF!; 2024-03-15: 55.25; 2024-03-22: 34.75; 2024-03-29: 30
P66 Sweeny | 3 | 30 | 0.6522% | 2024-01-26 | 2024-03-07 | Reformer | Came up on Mar 7 |  | -4.8387 |  | -5.8065 | [10 empty] | OK | 2024-03-22: -20; 2024-03-29: -10
P66 Bayway | 1 | 35.0175 | 7.295% | 2024-01-15 | 2024-03-08 | VDU down/FCC cut 35-45% |  |  | -18.0735 |  | -7.9072 | [10 empty] | OK | 2024-03-15: 17.5088
North Salt Lake | 4 |  | 0% | 2024-02-08 | 2024-03-08 | CCR Reformer (10), CDU (31), HF Alky (2.8), MSCC (11.5) |  |  |  | 0 | 0 | [10 empty] | Missing
Big West North Salt Lake | 4 | 20 | 5.882% | 2024-02-08 | 2024-03-08 | CDU/Ref/FCC/alky | Down. |  |  | -14.4828 | -4.5161 | [10 empty] | OK | 2024-02-16: -10; 2024-02-23: -10; 2024-03-15: 13.3333; 2024-03-22: 6.6667
P66 Borger | 3 | 17 | 0.3696% | 2024-02-25 | 2024-03-08 | FCCU 29 (30) |  |  |  | -2.3448 | -3.8387 | [10 empty] | Missing
Whiting | 2 |  | 0% | 2024-02-01 | 2024-03-09 | CDU 12 (250), Pipestill 11A (90), Pipestill 11C |  |  |  | 0 | 0 | [10 empty] | Missing
Valero St Charles | 3 | 68 | 1.478% | 2024-01-24 | 2024-03-10 | CDU/Coker/HDC | Up now . Delayed Su vs early Feb |  | -15.3548 |  | -19.7419 | [10 empty] | OK | 2024-01-26: -446.8571; 2024-02-02: 189.4286; 2024-02-09: 189.4286; 2024-03-15: 24.2857; 2024-03-22: 23.7143; 2024-03-29: 20
Valero Corpus Christi | 3 | 10.45 | 0.2272% | 2024-01-14 | 2024-03-12 | CDU (40)/HDC | Up |  | -5.7306 |  | -3.7081 | [10 empty] | OK | 2024-01-19: #REF!; 2024-01-26: #REF!; 2024-03-15: 4.4786; 2024-03-22: 5.9714
Marathon El Paso | 3 | 30.05 | 0.6533% | 2024-02-12 | 2024-03-12 | CDU/FCC/alky | Up now |  |  | -17.6155 | -10.6629 | [10 empty] | OK | 2024-02-16: 194612.3857; 2024-02-23: -194642.4357; 2024-03-15: 12.8786; 2024-03-22: 17.1714
FH Corpus West | 3 | 30 | 0.6522% | 2024-02-28 | 2024-03-12 | FCC | Up |  |  | -1.0345 | -10.6452 | [10 empty] | OK | 2024-03-01: -12.8571; 2024-03-08: -17.1429; 2024-03-15: 8.5714; 2024-03-22: 21.4286
Placid Port Allen | 3 |  | 0% | 2024-03-05 | 2024-03-12 | [5 empty] | 0 | [10 empty] | Missing
Cenovus Lima | 2 |  | 0% | 2024-03-06 | 2024-03-13 | Coker (31) | TBD on return…assuming one week outage |  |  |  | 0 | [10 empty] | OK | 2024-03-08: -2.6829; 2024-03-15: -4.0243; 2024-03-22: 6.7071
Warren | 1 |  | 0% | 2024-03-05 | 2024-03-14 | FCC (25) |  |  |  |  | 0 | [10 empty] | OK | 2024-03-08: -6.9643; 2024-03-15: 6.9643
Marathon Garyville | 3 | 35 | 0.7609% | 2024-03-08 | 2024-03-15 | Alkylation Unit (38 kbd) | Genscape is only publication with this down |  |  |  | -7.9032 | [10 empty] | OK | 2024-03-15: -35; 2024-03-22: 35
Valero Port Arthur | 3 | 75 | 1.63% | 2024-01-15 | 2024-03-16 | CDU/Coker/Reformer/HDC | Genscape has full site up |  | -38.7097 |  | -36.2903 | [10 empty] | OK | 2024-01-19: 485421.4286; 2024-01-26: -485496.4286; 2024-03-22: 40; 2024-03-29: 20; 2024-04-05: 15
Marathon Carson | 5 |  | 0% | 2024-02-29 | 2024-03-16 | HCC (65) | Assum Mar 16. |  |  | 0 | 0 | [10 empty] | OK | 2024-03-22: 11.375; 2024-03-29: 11.375; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Chevron Richmond | 5 | 23.8 | 1.763% | 2024-01-18 | 2024-03-17 | CR (28) |  |  | -9.9806 |  | -12.2839 | [10 empty] | OK | 2024-03-22: 15.8667; 2024-03-29: 7.9333; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
FH Corpus East | 3 | 49.92 | 1.085% | 2024-01-12 | 2024-03-19 | CDU, FCC | Up | 67 | -30.5961 |  | -28.9858 | [10 empty] | OK | 2024-01-19: -49.92; 2024-01-26: 0; 2024-03-22: -323383.7976; 2024-03-29: 323418.7176; 2024-04-05: 15
Marathon Texas City | 3 | 60.3 | 1.311% | 2024-01-14 | 2024-03-19 | CDU/Reformer/FCC/alky | Up |  | -33.0677 |  | -35.0129 | [10 empty] | OK | 2024-01-19: #REF!; 2024-01-26: #REF!; 2024-03-22: 15.075; 2024-03-29: 15.225; 2024-04-05: 30
Valero Texas City | 3 | 55 | 1.196% | 2024-01-25 | 2024-03-19 | FCC/Alky | Up |  | -10.6452 |  | -31.9355 | [10 empty] | OK | 2024-01-26: 356054.2857; 2024-02-02: -356109.2857; 2024-03-22: 23.5714; 2024-03-29: 21.4286; 2024-04-05: 10
Motiva Port Arthur | 3 |  | 0% | 2024-03-06 | 2024-03-19 | VDU (210) | IIR confirmed this is a two week outage |  |  |  | 0 | [10 empty] | OK | 2024-03-08: -15; 2024-03-15: -22.5; 2024-03-22: 37.5
XOM Beaumont | 3 | 65.25 | 1.418% | 2024-02-19 | 2024-03-20 | Reformer/HDC | Up |  |  | -22.5 | -39.9919 | [10 empty] | OK | 2024-02-23: #REF!; 2024-03-08: #REF!; 2024-03-22: 5; 2024-03-29: 40; 2024-04-05: 20
Marathon Galv Bay | 3 | 14 | 0.3043% | 2024-03-14 | 2024-03-21 | Hydrocracker (85 kbd) | Assuming 1 week outage. Not confirmed yet |  |  |  | -3.1613 | [10 empty] | OK | 2024-03-15: -5.6; 2024-03-22: 5.6
Woods Cross Refinery | 4 | 13 | 3.824% | 2024-03-09 | 2024-03-22 | CDU (26) - HDC, FCC | Down |  |  |  | -5.4516 | [10 empty] | OK | 2024-03-15: -8.6667; 2024-03-22: -4.3333; 2024-03-29: 8.6667; 2024-04-05: 4.3333
P66 Wood River | 2 | 16.875 | 0.7031% | 2024-02-28 | 2024-03-23 | CDU (67) | Up |  |  | -0.5819 | -11.9758 | [10 empty] | OK | 2024-03-01: #REF!; 2024-03-08: #REF!; 2024-04-05: 8.4375; 2024-04-12: 8.4375
Mobile | 3 |  | 0% | 2024-03-15 | 2024-03-23 | CDU 1 (40) |  |  |  |  | 0 | [10 empty] | OK | 2024-03-22: -4; 2024-03-29: 4
P66 Wood River | 2 | 16.875 | 0.7031% | 2024-06-05 | 2024-03-23 | CDU (67) | Up |  |  |  | -11.9758 | [10 empty] | Missing
P66 Lake Charles | 3 | 19.5 | 0.4239% | 2024-03-16 | 2024-03-24 | CDU (65), VDU (53.1) | Up |  |  |  | -5.0323 | [10 empty] | OK | 2024-03-22: -11.7; 2024-04-05: 11.7
Mobile | 3 |  | 0% | 2024-03-01 | 2024-03-25 | Ref 1 (13.5), HDS Ref (25) |  |  |  |  | 0 | [10 empty] | OK | 2024-03-08: -5.7375; 2024-03-15: -5.7375; 2024-04-12: 5.7375; 2024-04-19: 5.7375
Total Port Arthur | 3 | 30 | 0.6522% | 2024-03-10 | 2024-03-25 | FCC (80), CDU (60) | IIR confirmed coming up on 3/25 |  |  |  | -14.5161 | [10 empty] | OK | 2024-03-15: -21.4286; 2024-03-22: -8.5714; 2024-03-29: 10.7143; 2024-04-05: 19.2857
Suncor Commerce City | 4 |  | 0% | 2024-03-04 | 2024-03-26 | CDU (39), VDU (8.375) |  |  |  |  | 0 | [10 empty] | OK | 2024-03-08: -6.6857; 2024-03-29: 3.3429; 2024-04-05: 3.3429
PBF Chalmette | 3 | 16.15 | 0.3511% | 2024-03-25 | 2024-03-26 | CR (19) |  |  |  |  | -0.52097 | [10 empty] | OK | 2024-03-29: -4.6143; 2024-04-05: 4.6143
Marathon Salt Lake | 4 | 30 | 8.824% | 2024-02-12 | 2024-03-27 | CDU/Reformer/FCC/alky | Down | there was an update of 2/29, pulled up on 2/16 |  | -17.5862 | -25.1613 | [10 empty] | OK | 2024-02-16: -15; 2024-02-23: -15; 2024-03-29: -194477.1429; 2024-04-05: 194507.1429
Marathon Salt Lake City | 4 | 23.82 | 7.006% | 2024-02-14 | 2024-03-27 | FCC(26.4) / CDU (66.5) |  |  |  | -12.3207 | -19.9781 | [10 empty] | OK | 2024-03-29: 4.764; 2024-04-05: 16.674; 2024-04-12: 2.382
CVR Wynnewood | 2 | 35 | 1.458% | 2024-02-21 | 2024-03-27 | CDU/FCC/Alky/Reformer | Pulled up from strating 3/1 to 2/21 |  |  | -9.6552 | -29.3548 | [10 empty] | OK | 2024-03-01: -15; 2024-03-08: -20; 2024-03-29: 5; 2024-04-05: 25; 2024-04-12: 5
United Warren | 1 |  | 0% | 2024-03-22 | 2024-03-27 | FCC (25) |  |  |  |  | 0 | [10 empty] | OK | 2024-03-22: -11.6071; 2024-03-29: 5; 2024-04-05: 6.6071
Corpus Christi (East) | 3 | 8.5 | 0.1848% | 2024-03-14 | 2024-03-29 | CR (10), HDA (7) |  |  |  |  | -4.1129 | [10 empty] | OK | 2024-03-22: -5.6667; 2024-03-29: -2.8333; 2024-04-05: 8.5
Smackover | 3 |  | 0% | 2024-03-04 | 2024-03-30 | Crude (7), VDU (3), Lube oil HT (4.5), Asphalt (1.5), Lube oil HT (5), Sulfur recovery unit |  |  |  |  | 0 | [10 empty] | Missing
Citgo Corpus Christi | 3 | 8.8 | 0.1913% | 2024-03-17 | 2024-03-30 | Coker (44) |  |  |  |  | -3.6903 | [10 empty] | OK | 2024-03-22: -7.5429; 2024-03-29: -1.2571; 2024-04-05: 8.8
P66 LA/Wilmington | 5 | 50 | 3.704% | 2024-02-10 | 2024-03-31 | FCC/Alky/Ref | Down |  |  | -32.7586 | -48.3871 | [10 empty] | OK | 2024-02-16: -25; 2024-02-23: -25; 2024-04-05: 16.6667; 2024-04-12: 23.3333; 2024-04-19: 10; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Citgo Lake Charles | 3 | 30 | 0.6522% | 2024-03-01 | 2024-03-31 | FCC | Down. Had it down Mid-Apr |  |  |  | -29.0323 | [10 empty] | Missing
P66 Wood River | 2 |  | 0% | 2024-03-04 | 2024-03-31 | HC (52.2) |  |  |  |  | 0 | [10 empty] | OK | 2024-03-08: -2.61; 2024-04-05: 2.61
PBF Torrance | 5 | 28.5 | 2.111% | 2024-03-27 | 2024-04-01 | Alkylation Unit (30 kbd) |  |  |  |  | -3.6774 | -0.95 | [9 empty] | OK | 2024-03-29: -4.8857; 2024-04-05: -8.55; 2024-04-12: 4; 2024-04-19: 8.55; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon El Paso | 3 | 15.3 | 0.3326% | 2024-03-19 | 2024-04-02 | Reformer (18) | Up now |  |  |  | -5.9226 | -1.02 | [9 empty] | OK | 2024-03-22: -6.12; 2024-03-29: -7.8686; 2024-04-05: 13.9886; 2024-04-12: 0
Valero Meraux | 3 | 27.2 | 0.5913% | 2024-03-26 | 2024-04-02 | CR (32) |  |  |  |  | -4.3871 | -1.8133 | [9 empty] | OK | 2024-03-29: -10.3619; 2024-04-05: -16.8381; 2024-04-12: 19.04; 2024-04-19: 8.16
FH Corpus (West) | 3 | 35.75 | 0.7772% | 2024-03-27 | 2024-04-02 | FCC (55) | SU |  |  |  | -4.6129 | -2.3833 | [9 empty] | OK | 2024-03-29: -21.45; 2024-04-12: 21.45
Calcasieu - Lake Charles | 3 | 40.5 | 0.8804% | 2024-03-12 | 2024-04-03 | Genscape has half the site up. IIR has report saying full plant up 4/2 | Genscape has half the site up. IIR has report saying full plant up 4/2 |  |  |  | -24.8226 | -4.05 | [9 empty] | OK | 2024-03-15: -17.3571; 2024-03-22: -23.1429; 2024-03-29: 8.1; 2024-04-05: 32.15; 2024-04-12: 0.25
Shell Norco | 3 | 5.25 | 0.1141% | 2024-03-27 | 2024-04-03 | Coker (21) |  | Assuming 4/3 |  |  | -0.67742 | -0.525 | [9 empty] | Missing
GCC Galveston Bunkers | 3 | 10.5 | 0.2283% | 2024-03-21 | 2024-04-04 | CDU (50) |  |  |  |  | -3.3871 | -1.4 | [9 empty] | Missing
P66 Wilmington | 5 | 17 | 1.259% | 2024-03-22 | 2024-04-05 | CR (20) | Added SD 4/22 |  |  |  | -4.9355 | -2.8333 | [9 empty] | OK | 2024-03-29: -11.9; 2024-04-05: -5.1; 2024-04-12: 5.1; 2024-04-19: 11.9; 2024-04-26: -7.2857; 2024-05-03: -9.7143; 2024-05-10: 7.2857; 2024-05-17: 9.7143; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Chalmette | 3 | 16.15 | 0.3511% | 2024-04-03 | 2024-04-05 | CR (19) | Assume SU 4/19 |  |  |  |  | -1.0767 | [9 empty] | OK | 2024-04-12: -6.9214; 2024-04-19: 6.9214
XOM Baytown | 3 | 55.25 | 1.201% | 2024-03-17 | 2024-04-06 | Reformer | Went down 3/17 |  |  |  | -24.9516 | -11.05 | [9 empty] | OK | 2024-03-22: -23.6786; 2024-03-29: -31.5714; 2024-04-12: 31.5714; 2024-04-19: 23.6786
Chevron Pasadena | 3 | 13.884 | 0.3018% | 2024-03-19 | 2024-04-08 | CDU down (115 kbd feed) | Up from unplanned outage |  |  |  | -5.3745 | -3.7024 | [9 empty] | OK | 2024-03-22: -3; 2024-03-29: -10.884
Toledo | 2 |  | 0% | 2024-02-23 | 2024-04-10 | CR (30) |  |  |  | 0 |  | 0 | [9 empty] | OK | 2024-04-19: 3.75; 2024-04-26: 3.75
XOM Beaumont | 3 | 13.8 | 0.3% | 2024-03-29 | 2024-04-12 | Vdu plugging - 60kbd of Crude | Up |  |  |  | -0.89032 | -5.52 | [9 empty] | OK | 2024-04-05: -6.9; 2024-04-12: -6.9; 2024-04-19: 6.9; 2024-04-26: 6.9
XOM Baton Rouge | 3 | 23.28 | 0.5061% | 2024-04-02 | 2024-04-12 | CDU | Up |  |  |  |  | -7.76 | [9 empty] | OK | 2024-04-12: -11.64; 2024-04-19: -11.64; 2024-04-26: 11.64; 2024-05-03: 11.64
Marathon Wilmington | 5 |  | 0% | 2024-04-03 | 2024-04-12 | HDC (33) | Assume SU 4/12 |  |  |  |  | 0 | [9 empty] | OK | 2024-04-12: -1.65; 2024-04-19: 1.65; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Benicia | 5 |  | 0% | 2024-02-23 | 2024-04-13 | FCCU (77) | Su moved backa week |  |  | 0 |  | 0 | [9 empty] | OK | 2024-03-01: -25.025; 2024-03-08: -25.025; 2024-03-29: 5; 2024-04-19: 40.025; 2024-04-26: 10.025; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Puget Sound | 5 |  | 0% | 2024-03-01 | 2024-04-14 | SF alky 1 (4), FCCU (50),Poly, SF alky 2 (7), SRU 4, |  |  |  |  | 0 | 0 | [9 empty] | Missing
HF Sinclair Puget/Anacortes | 5 | 30 | 2.222% | 2024-03-01 | 2024-04-14 | FCC/Alky | Up |  |  |  | -29.0323 | -14 | [9 empty] | OK | 2024-03-08: -15; 2024-03-15: -15; 2024-04-19: #REF!; 2024-04-26: #REF!; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero Meraux | 3 | 65 | 1.413% | 2024-04-12 | 2024-04-14 | Entire site (130 kbd) | Appeared to come back up on 4/14 |  |  |  |  | -4.3333 | [9 empty] | OK | 2024-04-19: -11.1429; 2024-04-26: 11.1429
Marathon Texas City | 3 | 15 | 0.3261% | 2024-04-08 | 2024-04-15 | CDU | [5 empty] | -3.5 | [9 empty] | OK | 2024-04-12: -15; 2024-04-19: 15
Motiva Port Arthur | 3 | 58.5 | 1.272% | 2024-04-10 | 2024-04-15 | FCC SD due to Storm | Up after unplanned SD |  |  |  |  | -9.75 | [9 empty] | OK | 2024-04-19: -20.8929; 2024-04-26: 20.8929
PBF Toledo | 2 | 40 | 1.667% | 2024-02-28 | 2024-04-16 | CDU/Alky/Reformer/HDC | CDU Up 4/16, Ref up 5/11 |  |  | -1.3793 |  | -21.3333 | [9 empty] | OK | 2024-03-08: -20; 2024-03-15: -20; 2024-04-19: 5.3714; 2024-04-26: 22.6286; 2024-05-03: 12
Chevron Richmond | 5 | 82.3 | 6.096% | 2024-04-09 | 2024-04-16 | FCC (90) & Cr (28) | [5 empty] | -19.2033 | [9 empty] | OK | 2024-04-12: -20.2171; 2024-04-19: -20.9329; 2024-04-26: 41.15; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Chevron Pascagoula | 3 | 50 | 1.087% | 2024-03-02 | 2024-04-17 | CDU | Up |  |  |  | -46.7742 | -28.3333 | [9 empty] | Missing
P66 Carson | 5 | 13.25 | 0.9815% | 2024-04-11 | 2024-04-19 | Coker | [5 empty] | -3.5333 | [9 empty] | OK | 2024-04-19: -13.25; 2024-04-26: 13.25; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Galv Bay | 3 | 55.25 | 1.201% | 2024-04-16 | 2024-04-21 | Reformer 2 (Ultraformer) | Up |  |  |  |  | -9.2083 | [9 empty] | OK | 2024-04-19: -15.6279; 2024-04-26: 15.6279
Marathon Catlettsburg | 2 | 46.93 | 1.955% | 2024-04-07 | 2024-04-22 | FCCU (24.5), CDU 3 (40), VDU (23.75) Amine 2 MDEA, HF Alky (4.75) | increase in rate predicted for 4/19 vs 4/14 |  |  |  |  | -23.465 | [9 empty] | OK | 2024-02-02: 5.2214; 2024-04-12: -16.7607; 2024-04-26: 9; 2024-05-03: 7.7607
Citgo Lake Charles | 3 | 36 | 0.7826% | 2024-04-08 | 2024-04-23 | CDU (120) | [5 empty] | -18 | [9 empty] | OK | 2024-04-12: -15; 2024-04-19: -21; 2024-04-26: 15; 2024-05-03: 21
Citgo Lake Charles | 3 |  | 0% | 2024-07-04 | 2024-04-23 | Coker | [15 empty] | OK | 2024-05-03: 6.8
Total Port Arthur | 3 | 34 | 0.7391% | 2024-03-22 | 2024-04-24 | Reformer (40) | Up |  |  |  | -9.871 | -27.2 | [9 empty] | OK | 2024-03-29: -25.5; 2024-04-05: -8.5; 2024-05-03: 19.2667; 2024-05-10: 14.7333
BP Cherry Point | 5 | 70 | 5.185% | 2024-04-12 | 2024-04-24 | CDU/Coker | Planned TA |  |  |  |  | -28 | [9 empty] | OK | 2024-04-19: -32.5; 2024-04-26: -53.8571; 2024-05-03: 32.5; 2024-05-10: 37.5; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
El Segundo | 5 | 47.45 | 3.515% | 2024-04-22 | 2024-04-25 | FCC | Need to confirm the timing |  |  |  |  | -4.745 | [9 empty] | OK | 2024-04-26: -15; 2024-05-03: -12.1143; 2024-05-10: 15; 2024-05-17: 12.1143; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Delek Big Spring | 3 | 8.125 | 0.1766% | 2024-04-18 | 2024-04-26 | FCC | Reduced rates for 4 days |  |  |  |  | -2.1667 | [9 empty] | OK | 2024-10-04: -4.6429; 2024-10-11: 4.6429
Delek Big Spring | 3 | 16.25 | 0.3533% | 2024-04-18 | 2024-04-26 | FCC | Assuming SU 4/25 |  |  |  |  | -4.3333 | [9 empty] | OK | 2024-04-26: -16.25; 2024-05-03: 16.25
Monroe Trainer | 1 | 34.45 | 7.177% | 2024-04-24 | 2024-04-26 |  | Up after SD unplanned |  |  |  |  | -2.2967 | [9 empty] | OK | 2024-04-26: -9.8429; 2024-05-03: -4.9214; 2024-05-10: 9.8429; 2024-05-17: 4.9214
Marathon Robinson | 2 | 61 | 2.542% | 2024-03-18 | 2024-04-27 | CDU/Coker/ Ref/HDC | Up |  |  |  | -25.5806 | -54.9 | [9 empty] | OK | 2024-03-22: 395358.4286; 2024-03-29: -395419.4286; 2024-04-12: 12.8571; 2024-04-19: 15; 2024-04-26: 33.1429
Chevron Salt Lake | 4 | 15 | 4.412% | 2024-03-24 | 2024-04-30 | CDU | Up |  |  |  | -3.3871 | -15 | [9 empty] | OK | 2024-03-29: #REF!; 2024-04-05: #REF!; 2024-05-03: #REF!; 2024-05-10: #REF!
Citgo Lemont | 2 | 25.5 | 1.062% | 2024-04-01 | 2024-04-30 | CDU @ 120kbd/FCC @ 40kbd | Up as of 4/30 vs 5/21 | 4/11: ENT reported no FCC reduction in rate |  |  |  | -24.65 | [9 empty] | OK | 2024-04-05: #REF!; 2024-04-12: #REF!; 2024-05-10: 18.2143; 2024-05-17: 7.2857
P66 Lake Charles | 3 | 30.16 | 0.6557% | 2024-04-26 | 2024-04-30 | FCC (46.4) | Up |  |  |  |  | -4.0213 | [9 empty] | Missing
XOM Baytown | 3 | 27.6 | 0.6% | 2024-04-19 | 2024-05-02 | Planned Decoke - CDU 120kbd cut | Up after planned decoke |  |  |  |  | -10.12 | -1.7806 | [8 empty] | OK | 2024-04-26: -13.8; 2024-05-03: -13.8; 2024-05-10: 20.8; 2024-05-17: 6.8
Citgo Lake Charles | 3 | 32.5 | 0.7065% | 2024-03-06 | 2024-05-03 | Cat A FCC (50) |  |  |  |  | -26.2097 |  | -3.1452 | [8 empty] | OK | 2024-03-08: -9.2857; 2024-03-15: -23.2143; 2024-05-10: 21.6667; 2024-05-17: 10.8333
Valero Meraux | 3 | 27.2 | 0.5913% | 2024-04-27 | 2024-05-04 | CR (32) | Up after Sd unplanned |  |  |  |  | -2.72 | -3.5097 | [8 empty] | OK | 2024-05-03: -13.6; 2024-05-10: -13.6; 2024-05-17: 13.6; 2024-05-24: 13.6
Pemex Deer Park | 3 | 59.8 | 1.3% | 2024-03-29 | 2024-05-05 | CDU/HDC /Ref | Up. Ref up 4/21. CDU/HDC Up 5/5 |  |  |  | -3.8581 |  | -9.6452 | [8 empty] | OK | 2024-04-05: -59.8; 2024-04-26: 19.125; 2024-05-03: 19.125; 2024-05-10: 11.55; 2024-05-17: 11.55
PBF Chalmette | 3 | 44.2 | 0.9609% | 2024-04-13 | 2024-05-05 | FCC | Up. Delayed from 4/20 SU |  |  |  |  | -25.0467 | -7.129 | [8 empty] | OK | 2024-04-19: -22.1; 2024-04-26: -22.1; 2024-05-03: 22.1; 2024-05-10: 22.1
KM Galena | 3 | 30 | 0.6522% | 2024-04-22 | 2024-05-05 | CDU | [5 empty] | -8 | -4.8387 | [8 empty] | OK | 2024-04-26: -15; 2024-05-03: -15; 2024-05-10: 15; 2024-05-17: 15
PBF Martinez | 5 | 39.5 | 2.926% | 2024-04-28 | 2024-05-05 | CDU (158 kbd) | Up |  |  |  |  | -2.6333 | -6.371 | [8 empty] | OK | 2024-05-03: -16.9286; 2024-05-17: 16.9286; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Chalmette | 3 | 11.875 | 0.2582% | 2024-04-30 | 2024-05-05 | Alky (12.5) | [5 empty] | 0 | -1.9153 | [8 empty] | OK | 2024-05-03: -5.9375; 2024-05-17: 5.9375
Valero Memphis | 2 | 38.6 | 1.608% | 2024-04-15 | 2024-05-06 | CDU/Ref | Up |  |  |  |  | -19.3 | -7.471 | [8 empty] | OK | 2024-04-19: -27.5714; 2024-04-26: -11.0286; 2024-05-10: 22.0571; 2024-05-17: 16.5429
Marathon Carson | 5 | 17 | 1.259% | 2024-05-01 | 2024-05-08 | CR (20) | [6 empty] | -3.8387 | [8 empty] | OK | 2024-05-10: -10.2; 2024-05-17: 0; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Delaware City | 1 | 45 | 9.375% | 2024-03-01 | 2024-05-09 | FCC/Alky | Genscape still has some units cold |  |  |  | -43.5484 |  | -13.0645 | [8 empty] | OK | 2024-03-08: -22.5; 2024-03-15: -22.5; 2024-05-17: #REF!; 2024-05-24: #REF!
XOM Beaumont | 3 | 68 | 1.478% | 2024-04-19 | 2024-05-09 | Ref (80kbd) | Up after unplanned SD. Delayed from 5/3 SU |  |  |  |  | -24.9333 | -19.7419 | [8 empty] | OK | 2024-04-26: -34; 2024-05-03: -34; 2024-05-17: 68
Irving St John | Canada | 85.6 | #N/A | 2024-04-22 | 2024-05-09 | CDU (150), FCC (74) | Up | Gas offline from 40 to 80kbd |  |  |  | -22.8267 | -24.8516 | [8 empty] | Missing
Par Billings | 4 | 14.5 | 4.265% | 2024-04-03 | 2024-05-12 | CDU | [5 empty] | -13.05 | -5.6129 | [8 empty] | OK | 2024-04-05: -7.25; 2024-04-12: -7.25; 2024-05-17: 7.25; 2024-05-24: 7.25
Delek Big Spring | 3 | 16.25 | 0.3533% | 2024-05-11 | 2024-05-14 | FCC | Weather caused the FCC to trip | [5 empty] | -1.5726 | [8 empty] | OK | 2024-05-17: -6.9643; 2024-05-24: 6.9643
P66 Borger | 3 | 17 | 0.3696% | 2024-04-19 | 2024-05-15 | Reformer | Up |  |  |  |  | -6.2333 | -8.2258 | [8 empty] | OK | 2024-05-24: 11.9; 2024-05-31: 5.1
CVR Wynnewood | 2 | 37.6 | 1.567% | 2024-04-28 | 2024-05-15 | CDU (78), FCC (21), Ref (19) | All fully up now (6/16) |  |  |  |  | -2.5067 | -18.1935 | [8 empty] | OK | 2024-05-03: -26.8571; 2024-05-10: -10.7429; 2024-05-17: 11.2; 2024-05-24: 11.2; 2024-06-14: 10; 2024-06-21: 16.4
Chevron Pasadena | 3 | 20 | 0.4348% | 2024-03-05 | 2024-05-17 | Reformer | Up after planned maintenance |  |  |  | -16.7742 |  | -10.9677 | [8 empty] | OK | 2024-03-08: #REF!; 2024-03-15: #REF!; 2024-05-24: #REF!; 2024-05-31: #REF!
El Segundo | 5 | 39.1 | 2.896% | 2024-04-15 | 2024-05-17 | Crude 4 (170) | Up |  |  |  |  | -19.55 | -21.4419 | [8 empty] | OK | 2024-04-19: -16.7571; 2024-04-26: -22.2429; 2024-05-24: 16.7571; 2024-05-31: 22.2429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Martinez | 5 | 30 | 2.222% | 2024-04-22 | 2024-05-17 | Ref/Coker/HDC | Up |  |  |  |  | -8 | -16.4516 | [8 empty] | OK | 2024-05-31: 21.4286; 2024-06-07: 8.5714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Baton Rouge | 3 | 25 | 0.5435% | 2024-05-06 | 2024-05-18 | PS9 Decoke | Up after planned decoke | [5 empty] | -9.6774 | [8 empty] | OK | 2024-05-10: -14.2857; 2024-05-17: -10.7143; 2024-05-24: 14.2857; 2024-05-31: 10.7143
XOM Beaumont | 3 | 7.5 | 0.163% | 2024-05-17 | 2024-05-18 | Cut 70 kbd to CDU-C due to the weather/power issues | Down for 36 hours | [5 empty] | -0.24194 | [8 empty] | OK | 2024-05-24: -1.0714; 2024-05-31: 1.0714
P66 Ponca City | 2 | 25.25 | 1.052% | 2024-05-13 | 2024-05-19 | CR (27), Coker (23.1) | Up after planned maintenace | updated Sd from 2/1 to 2/5 |  |  |  |  | -4.8871 | [8 empty] | OK | 2024-05-17: -12.625; 2024-05-31: 12.625
Lazarus Nixon | 3 | 4.5 | 0.09783% | 2024-05-11 | 2024-05-20 | CDU (15 kbd) | IIR/Genscape saying they moved this 10 day outage from Aug to May | [5 empty] | -1.3065 | [8 empty] | OK | 2024-05-17: -4.5; 2024-05-24: 2.25; 2024-05-31: 2.25
XOM Joliet | 2 | 135 | 5.625% | 2024-04-01 | 2024-05-22 | CDU/Coker/ Ref/FCC/Alky | All units up except FCC. FCC ontest 5/22. Market: know we are Su and expect all units up 5/21 |  |  |  |  | -130.5 | -95.8065 | [8 empty] | OK | 2024-04-05: #REF!; 2024-04-12: #REF!; 2024-04-19: #REF!; 2024-05-24: 77.7143; 2024-05-31: 57.2857
GCC Galveston Bunkers | 3 | 10.5 | 0.2283% | 2024-05-19 | 2024-05-23 | CDU (50) - TBD on actual date coming back up | [6 empty] | -1.3548 | [8 empty] | OK | 2024-05-24: -5.25; 2024-05-31: 5.25
Big West North Salt Lake | 4 | 8.45 | 2.485% | 2024-05-22 | 2024-05-23 | FCC | [6 empty] | -0.27258 | [8 empty] | OK | 2024-05-31: -2.1125; 2024-06-07: 2.1125
XOM Baytown | 3 | 55.25 | 1.201% | 2024-05-05 | 2024-05-27 | Reformer repair from Feb outage | SU after repairs | [5 empty] | -39.2097 | [8 empty] | OK | 2024-05-10: -27.625; 2024-05-17: -27.625; 2024-05-31: 55
Valero McKee | 3 | 35.75 | 0.7772% | 2024-05-17 | 2024-05-27 | FCC | Up after unplanned Sd | [5 empty] | -11.5323 | [8 empty] | OK | 2024-05-24: -28.6; 2024-05-31: 29
Valero Corpus Christi | 3 | 62.4 | 1.357% | 2024-05-24 | 2024-05-28 | FCC | Up after SD that was reported by Genscape | [5 empty] | -8.0516 | [8 empty] | OK | 2024-05-31: -17.8286; 2024-06-14: 17.8286
P66 Borger | 3 | 20 | 0.4348% | 2024-04-01 | 2024-05-30 | FCC 29 | Up |  |  |  |  | -19.3333 | -19.3548 | [8 empty] | OK | 2024-04-12: -10; 2024-04-19: -10; 2024-06-07: 10; 2024-06-14: 10
XOM Baytown | 3 | 20 | 0.4348% | 2024-04-07 | 2024-05-31 | Reformer (Cutback only) | Assuming Reformer at reduced rates through end of May |  |  |  |  | -15.3333 | -20 | [8 empty] | OK | 2024-04-12: -13.3333; 2024-04-19: -6.6667; 2024-06-07: 13.3333; 2024-06-14: 6.6667
Marathon El Paso | 3 | 19.5 | 0.4239% | 2024-06-03 | 2024-06-04 | FCC (29.5) | Up now | [14 empty] | OK | 2024-06-07: -5.5714; 2024-06-14: 5.5714
Valero Meraux | 3 | 40 | 0.8696% | 2024-06-03 | 2024-06-06 | CDU/Ref | Up after leak repair | [14 empty] | OK | 2024-06-07: -13.3333; 2024-06-21: 13.3333
Petro Star Valdez | 5 | 15 | 1.111% | 2024-04-29 | 2024-06-07 | CDU (60 kbd) | Up |  |  |  |  | -0.5 | [9 empty] | OK | 2024-06-14: 10.5; 2024-06-21: 4.5; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Sweeny | 3 | 111.63 | 2.427% | 2024-05-31 | 2024-06-07 | CDU / Reformer / Coker / FCC / Alky | TBD on return. Assuming a week | [5 empty] | 0 | [8 empty] | OK | 2024-06-07: -27.9075; 2024-06-21: 27.9075
Calcasieu - Lake Charles | 3 | 21.9 | 0.4761% | 2024-05-31 | 2024-06-07 | Can see the CDU stack go out around 0400 | Genscape has the stack on the CDU cold. Estimating will be down for 1 wk | [5 empty] | 0 | [8 empty] | OK | 2024-06-07: -15.33; 2024-06-14: 4.599; 2024-06-21: 10.731
Marathon Anacortes | 5 | 33.8 | 2.504% | 2024-06-05 | 2024-06-10 | FCC (52) | Up | [14 empty] | OK | 2024-06-14: -24.1429; 2024-06-21: 24.1429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Galveston Bay | 3 | 94.25 | 2.049% | 2024-06-03 | 2024-06-11 | FCC | Up after Unplanned SD. | [14 empty] | OK | 2024-06-07: -31.4167; 2024-06-14: 5; 2024-06-21: 15; 2024-06-28: 11.4167
XOM Baton Rouge | 3 | 20.5 | 0.4457% | 2024-05-22 | 2024-06-12 | FCC(partly - only 20 kbd of FCC Feed/West Coker (25 kbd feed) | Steam Cracker Issue - anticipating 3 week outage | [5 empty] | -5.9516 | [8 empty] | OK | 2024-02-16: -20.5; 2024-02-23: 6.8333; 2024-03-01: 13.6667; 2024-05-24: -2.9286; 2024-05-31: -13.1786; 2024-06-07: -4.3929; 2024-06-14: 2.9286; 2024-06-21: 13.1786; 2024-06-28: 4.3929
Chevron Pascagoula | 3 | 45 | 0.9783% | 2024-06-03 | 2024-06-14 | Reformer (55) | Upafter planned maintenance | [14 empty] | OK | 2024-06-14: -36; 2024-06-28: 36
Lyondell Houston | 3 | 54.35 | 1.182% | 2024-06-09 | 2024-06-14 | CDU/VDU/Coker | UP after unplanned outage | [14 empty] | OK | 2024-06-14: -27.175; 2024-06-28: 27.175
Pemex Deer Park | 3 | 5.36 | 0.1165% | 2024-06-12 | 2024-06-14 | HDC | Up after Sd unplanned | [14 empty] | OK | 2024-06-14: -2.68; 2024-06-28: 2.68
Motiva Port Arthur | 3 | 36.125 | 0.7853% | 2024-06-07 | 2024-06-16 | Ref cut back to min | UP after unplanned outage | [14 empty] | OK | 2024-06-14: -18.0625; 2024-06-28: 18.0625
BP Whiting | 2 | 55.25 | 2.302% | 2024-06-14 | 2024-06-16 | Ref (70) | Up after unplanned SD | [14 empty] | OK | 2024-06-21: -15.7857; 2024-06-28: 15.7857
PBF Torrance | 5 | 0 | 0% | 2024-05-30 | 2024-06-18 | FCC (90 kbd) and crude cut rates for CO boiler | Up after unplalned SD | [5 empty] | 0 | [8 empty] | OK | 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Torrance | 5 | 43.2 | 3.2% | 2024-05-30 | 2024-06-18 | FCC (90 kbd) and crude cut rates for CO boiler | Up after unplalned SD | [5 empty] | -1.3935 | [8 empty] | OK | 2024-06-07: -32.4; 2024-06-14: -10.8; 2024-06-21: 43.2; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Wilmington | 5 | 12.75 | 0.9444% | 2024-06-09 | 2024-06-18 | Ref | Up | [14 empty] | OK | 2024-06-14: -8.5; 2024-06-21: 8.5; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Chevron Richmond | 5 | 23.8 | 1.763% | 2024-06-12 | 2024-06-20 | Reformer (28 kbd feed) | Up- after unplanned SD | [14 empty] | OK | 2024-06-14: -4.76; 2024-06-21: -11; 2024-06-28: 11; 2024-07-05: 4.76; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
GCC Galveston Bunkers | 3 | 10.5 | 0.2283% | 2024-06-16 | 2024-06-20 | CDU (50) | Up after unplanned SD | [14 empty] | OK | 2024-06-21: -6; 2024-06-28: 6
Marathon Carson | 5 | 43.75 | 3.241% | 2024-06-17 | 2024-06-22 | CDU/VDU | Up afetr Sd due to leak | [14 empty] | OK | 2024-06-21: -25; 2024-06-28: 10; 2024-07-05: 15; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Citgo Corpus West | 3 | 30 | 0.6522% | 2024-04-30 | 2024-06-23 | Reformer (30), Diesel HDT, Coker (44) | Up- after planned TA |  |  |  |  | 0 | [9 empty] | OK | 2024-05-03: -12.8571; 2024-05-10: -17.1429; 2024-06-28: 12.8571; 2024-07-05: 17.1429
Marathon Anacortes | 5 | 27.2 | 2.015% | 2024-06-07 | 2024-06-25 | Ref (32) | up after leak | [14 empty] | OK | 2024-06-14: -27.2; 2024-07-05: 15.2; 2024-07-12: 12; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
HF Sinclair El Dorado | 2 | 6 | 0.25% | 2024-06-22 | 2024-06-26 | Coker | Su aftre unplanned SD | [14 empty] | OK | 2024-06-28: -2.5714; 2024-07-05: 2.5714
Marathon GalvBay | 3 | 66.3 | 1.441% | 2024-06-21 | 2024-06-28 | Ref (80) | Sd unplanned | [14 empty] | OK | 2024-06-28: -33.15; 2024-07-12: 33.15
XOM Baytown | 3 | 3 | 0.06522% | 2024-06-03 | 2024-06-30 | HDC | Planned TA | [14 empty] | OK | 2024-06-07: -3; 2024-07-05: 3
Valero Corpus Christi | 3 | 33.2 | 0.7217% | 2024-06-23 | 2024-06-30 | CDU/Coker | Back up | [14 empty] | OK | 2024-06-28: -23.24; 2024-07-12: 23.24
Chevron Richmond | 5 | 55 | 4.074% | 2024-05-02 | 2024-07-01 | FCC (80)/ alk | Up after planned TA. S | [5 empty] | -51.4516 | [8 empty] | OK | 2024-05-03: -7.8571; 2024-05-10: -47.5; 2024-07-05: 47.5; 2024-07-12: 47.5; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 LA/Wilmington | 5 | 32.5 | 2.407% | 2024-06-03 | 2024-07-01 | FCC | Up after planned TA. SU delayed from 6/16 | [14 empty] | OK | 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Total Port Arthur | 3 | 10 | 0.2174% | 2024-06-27 | 2024-07-01 | CDU | SU after SD unplanned | [14 empty] | OK | 2024-07-05: -10; 2024-07-12: 10
CVR Wynnewood | 2 | 9.75 | 0.4062% | 2024-07-01 | 2024-07-03 | CDU/VDU | Sd unplanned for 2 days | [14 empty] | OK | 2024-07-05: -4.1786; 2024-07-12: 4.1786
HF Sinclair Tulsa | 2 | 2.55 | 0.1062% | 2024-06-03 | 2024-07-04 | Coker | Up afetr unplanned Sd | [14 empty] | OK | 2024-06-07: -1.275; 2024-06-14: -1.275; 2024-07-12: 2.55
Marathon Carson | 5 | 17 | 1.259% | 2024-06-29 | 2024-07-04 | Reformer | up after unplaned SD | [14 empty] | OK | 2024-07-05: -13.6; 2024-07-12: 13.6; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Robinson | 2 | 3.6 | 0.15% | 2024-07-01 | 2024-07-04 | Coker | [15 empty] | OK | 2024-07-05: -2.0571; 2024-07-12: 2.0571
Marathon Canton | 2 | 31.9 | 1.329% | 2024-07-06 | 2024-07-07 | Cdu & FCC | up after unplanned SD | [14 empty] | OK | 2024-07-12: -4.5571; 2024-07-19: 4.5571
Citgo Corpus Christi | 3 | 140 | 3.043% | 2024-07-05 | 2024-07-08 | Cut to min as prep for hurricane Beryl | recovered | [14 empty] | OK | 2024-07-12: -40; 2024-07-19: 40
PBF Martinez | 5 | 7.5 | 0.5556% | 2024-07-05 | 2024-07-09 | Coker | up after unaplanned outage | [14 empty] | OK | 2024-07-12: -4.2857; 2024-07-19: 4.2857; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Beryl Other Refineries cut back | 3 | 16 | 0.3478% | 2024-07-07 | 2024-07-09 | Refineries in the region cut back as prep for Hurricane Beryl | recovered | [14 empty] | OK | 2024-07-12: -4.5714; 2024-07-19: 4.5714
XOM Baytown | 3 | 26 | 0.5652% | 2024-07-08 | 2024-07-09 | Reduced crude rate as prep for hurricane Beryl | recovred | [14 empty] | OK | 2024-07-12: -7.4286; 2024-07-19: 7.4286
Valero Port Arthur | 3 | 127.05 | 2.762% | 2024-07-09 | 2024-07-10 | FCC, CDU and Ref | up after SD unplanned due to power blib | [14 empty] | OK | 2024-07-12: -18.15; 2024-07-19: 18.15
Marathon Galveston Bay | 3 | 234.1 | 5.089% | 2024-07-09 | 2024-07-16 | All units down except for runnign 170kbd of crude | CDU/Ref/Coker SU 7/16. FCC SU 8/6 | [14 empty] | OK | 2024-07-12: -133.7714; 2024-07-19: -7.2714; 2024-07-26: 69.7929; 2024-08-09: 31.4167; 2024-08-16: 62.8333
GCC Galveston Bunkers | 3 | 12.5 | 0.2717% | 2024-07-09 | 2024-07-16 |  | Up | [14 empty] | OK | 2024-07-12: -7.1429; 2024-07-26: 7.1429
Total Port Arthur | 3 | 48 | 1.043% | 2024-07-13 | 2024-07-16 | CDU1 (80) / CR (40) / Coker (60) | Lost steam on 7/13. SU on 7/16 | [14 empty] | OK | 2024-07-19: -27.4286; 2024-07-26: 16.8; 2024-08-02: 10.6286
Lyondell Houston | 3 | 63.05 | 1.371% | 2024-07-16 | 2024-07-17 | FCC | Per Genscape - came up in 1.5 days | [14 empty] | OK | 2024-07-19: -18.0143; 2024-07-26: 18.0143
Monroe Trainer | 1 | 34.45 | 7.177% | 2024-07-16 | 2024-07-18 | FCC (53 kbd) | Up after unaplanned SD | [14 empty] | OK | 2024-07-19: -14.7643; 2024-07-26: 4.7643; 2024-08-02: 10
HF Artesia | 3 | 20.4 | 0.4435% | 2024-07-16 | 2024-07-18 | Reformer | Up after unplanned Sd | [14 empty] | OK | 2024-07-19: -5.8286; 2024-07-26: 5.8286
CVR Wynnewood | 2 | 13.65 | 0.5687% | 2024-07-09 | 2024-07-19 | FCC | Up after unaplanned outage | [14 empty] | OK | 2024-07-12: -7.8; 2024-07-26: 7.8
XOM Baton Rouge | 3 | 90.4 | 1.965% | 2024-07-17 | 2024-07-21 | CDU to min, Coker/FCC/HDC cut back and Ref down | Up after unplanned outage | [14 empty] | OK | 2024-07-19: -38.7429; 2024-07-26: 30; 2024-08-02: 8.7429
Marathon Salt Lake City | 4 | 16.9 | 4.971% | 2024-07-15 | 2024-07-23 | FCC | Up after Sd unplanned | [14 empty] | OK | 2024-07-19: -9.6571; 2024-08-02: 9.6571
Calcasieu - Lake Charles | 3 | 40.5 | 0.8804% | 2024-07-18 | 2024-07-25 | Big flaring. Genscape has site as down. | Up after unaplanned outage | [14 empty] | OK | 2024-07-19: -2.9857; 2024-07-26: -37.5143; 2024-08-02: 37.5143; 2024-08-09: 2.9857
P66 Borger | 3 | 19.5 | 0.4239% | 2024-07-23 | 2024-07-25 | FCC (30) | Genscape reporting down starting 7/23 | [14 empty] | OK | 2024-07-26: -5.5714; 2024-08-02: 5.5714
Chevron Pasadena | 3 | 34.55 | 0.7511% | 2024-07-18 | 2024-07-26 | CDU/Ref/alky | SU after unplaneed. CDU SU 8/6 | [14 empty] | OK | 2024-07-26: -23.0333; 2024-08-09: 23.0333
XOM Beaumont | 3 | 58.5 | 1.272% | 2024-07-06 | 2024-07-30 | HDC | Could potentially pull up SU | [14 empty] | Missing
XOM Beaumont | 3 | 58.5 | 1.272% | 2024-07-06 | 2024-07-30 | CDU B (top off) /coker | Could potentially pull up SU | [14 empty] | OK | 2024-07-12: -29.25; 2024-07-19: -29.25; 2024-08-09: 29.25; 2024-08-16: 29.25
Citgo Lemont | 2 | 1.25 | 0.05208% | 2024-07-24 | 2024-07-30 | Coker | up aftre planned decoke | [14 empty] | OK | 2024-07-26: -1.25; 2024-08-09: 1.25
Calcasieu - Lake Charles | 3 | 40.5 | 0.8804% | 2024-07-29 | 2024-07-31 | site down again | SU aftrer another unaplanned SD | [14 empty] | OK | 2024-08-02: -17.3571; 2024-08-09: 17.3571
PBF Delaware City | 1 | 45 | 9.375% | 2024-07-01 | 2024-08-02 | FCC | Del City FCC had been down (which explains the P1 production numbers in Jul). On its way back up | [14 empty] | OK | 2024-07-19: -20; 2024-07-26: -5; 2024-08-09: 10; 2024-08-16: 15
Delek El Dorado | 3 | 13 | 0.2826% | 2024-07-17 | 2024-08-02 | FCC | Su after SD unplanned | [14 empty] | OK | 2024-07-26: -13; 2024-08-09: 13
Flint Hills Pine Bend | 2 | 2.4 | 0.1% | 2024-07-22 | 2024-08-02 | Coker | up after unplanned SD. Added 8/7 | [14 empty] | OK | 2024-07-26: -1.7143; 2024-08-02: -0.68571; 2024-08-09: 2.4
Marathon Mandan | 2 | 40 | 1.667% | 2024-06-08 | 2024-08-05 | CDU/Ref/FCC/Alky | Up after planned TA | formula was incorrect | [13 empty] | OK | 2024-06-14: -40; 2024-06-21: 0; 2024-08-16: 40
Chevron Richmond | 5 | 3 | 0.2222% | 2024-08-02 | 2024-08-07 | HDC | SU after Sd unplanned | [14 empty] | OK | 2024-08-09: -3; 2024-08-16: 3; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Beaumont | 3 | 11.75 | 0.2554% | 2024-08-01 | 2024-08-08 | HDC Issue (65 kbd)/ Reformer issues (10 kbd cut on reformer feed) | Up | [14 empty] | OK | 2024-08-02: -1.6786; 2024-08-09: -10.0714; 2024-08-16: 8.8125; 2024-08-23: 2.9375
XOM Joliet | 2 | 129.85 | 5.41% | 2024-07-16 | 2024-08-09 | All units down due to Power Outage caused by storm | Internal only. Only ENT reporting on it | [14 empty] | OK | 2024-07-19: -98.2; 2024-07-26: -31.65; 2024-08-09: 12.3429; 2024-08-16: 43.6857; 2024-08-23: 73.8214
CVR Coffeyville | 2 | 15 | 0.625% | 2024-08-07 | 2024-08-09 | CDU | Upafter unplanned outage | [14 empty] | OK | 2024-08-09: -4.2857; 2024-08-16: 1.2245
Valero Bill Greenhey | 3 | 9.35 | 0.2033% | 2024-07-21 | 2024-08-10 | Ref | Su after planned TA | [14 empty] | OK | 2024-07-26: -6.6786; 2024-08-02: -2.6714; 2024-08-09: 6.6786; 2024-08-16: 2.6714
Cenovus Lima | 2 | 52 | 2.167% | 2024-07-30 | 2024-08-11 | CDU/VDU/Ref | SU after unplanned outage. CDU up 8/9, ref SU 8/11 | [14 empty] | OK | 2024-08-02: -29.7143; 2024-08-09: -22.2857; 2024-08-16: 42.5714; 2024-08-23: 9.4286
Cenovus Toledo | 2 | 46.5 | 1.938% | 2024-07-22 | 2024-08-12 | FCC/coker/cdu | Su after unplanned outage. FCC SU 8/5 | [14 empty] | OK | 2024-07-26: -33.2143; 2024-08-02: -13.2857; 2024-08-09: 13.9286; 2024-08-16: 27.5714; 2024-08-23: 5
Delek El Dorado | 3 | 2.4 | 0.05217% | 2024-08-06 | 2024-08-12 | CDU/ISO | Su after unplanned SD | [14 empty] | OK | 2024-08-09: -1.0286; 2024-08-23: 1.0286
P66 Borger | 3 | 17 | 0.3696% | 2024-08-07 | 2024-08-13 | Ref | Su after unplanned outage | [14 empty] | OK | 2024-08-09: -4.8571
P66 Lake Charles | 3 | 29.9 | 0.65% | 2024-08-11 | 2024-08-14 | FCC | S/U on 8/14 after unplanned S/D | [14 empty] | OK | 2024-08-16: -17.0857; 2024-08-23: 10; 2024-08-30: 7.0857
CVR Coffeyville | 2 | 63.1 | 2.629% | 2024-08-13 | 2024-08-15 | CDU/FCC/Ref/Coker | SU after unplanned SD | [14 empty] | OK | 2024-08-16: -9.0143; 2024-08-23: 9.0143
Motiva Port Arthur | 3 | 52.65 | 1.145% | 2024-07-25 | 2024-08-16 | FCC | SU after unplanned SD | [14 empty] | OK | 2024-08-02: -26.325; 2024-08-09: -26.325; 2024-08-23: 0.85714; 2024-08-30: 2.1429
El Segundo | 5 | 47.125 | 3.491% | 2024-08-03 | 2024-08-16 | FCC (72.5) | Appears to be up in Genscape | [14 empty] | OK | 2024-08-09: -37.7; 2024-08-16: -9.425; 2024-08-30: 32.9875; 2024-09-06: 14.1375; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero Port Arthur | 3 | 45.05 | 0.9793% | 2024-08-15 | 2024-08-16 | Ref | Su after unplanned SD | [14 empty] | OK | 2024-08-16: -6.4357; 2024-08-23: 6.4357
Marathon Garyville | 3 |  | 0% | 2024-08-10 | 2024-08-17 | HDT | No mogas impact | [14 empty] | Missing
Marathon Garyville | 3 |  | 0% | 2024-08-10 | 2024-08-17 | HDT | SD unplanned assuming 1 wk | [14 empty] | Missing
P66 Lake Charles | 3 | 28.9 | 0.6283% | 2024-08-17 | 2024-08-18 | Ref | SU after unplanned SD | [14 empty] | OK | 2024-08-23: -4.1286; 2024-08-30: 4.1286
Marathon Canton | 2 | 43.1 | 1.796% | 2024-08-21 | 2024-08-23 | CDU, FCC, Ref, HDT | Restarted 8/23 after unplanned sd | [14 empty] | OK | 2024-08-23: -18.4714; 2024-08-30: 18.4714
Marathon robinson | 2 | 3.6 | 0.15% | 2024-08-20 | 2024-08-25 | Coker | SU after unplanned sd | [14 empty] | OK | 2024-08-23: -1.0286; 2024-09-06: 1.0286
P66 Borger | 3 | 17 | 0.3696% | 2024-08-15 | 2024-08-27 | Ref | SU after SD unplanned | [14 empty] | OK | 2023-11-24: -4.8571; 2023-12-08: 4.8571; 2024-08-16: -17; 2024-08-30: 9.7143; 2024-09-06: 7.2857
Marathon Wilmington | 5 | 12.75 | 0.9444% | 2024-08-26 | 2024-08-27 | Ref | Sd unplanned for 2 days | [14 empty] | OK | 2024-08-30: -3.6429; 2024-09-06: 3.6429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Big West North Salt Lake | 4 |  | 0% | 2024-08-23 | 2024-08-29 | Diesle HDT | [15 empty] | Missing
Irving St John | Canada | 16.25 | #N/A | 2024-08-21 | 2024-08-30 | FCC (25) | SD unplanned. Irving planning on permanently SD FCC in Sep, so questions on whether this is it. Genscape has this up | [14 empty] | Missing
Flint Hills Pine Bend | 2 | 21.45 | 0.8937% | 2024-08-22 | 2024-08-31 | CDU (82.5) at 50% capacity | outage was cancelled | [14 empty] | Missing
PBF Delaware City | 1 | 53.3 | 11.1% | 2024-08-29 | 2024-09-01 | FCC | Su after SD | [14 empty] | OK | 2024-09-06: 0; 2024-09-13: 0
Valero Port Arthur | 3 | 52.5 | 1.141% | 2024-08-12 | 2024-09-04 | CDU | SD unplanned- Assuming down until 9/11 (delayed). Only coming back at 200 kbd (vs 250 kbd max). IIR confirmed coming back up 9/9 | [14 empty] | OK | 2024-08-16: -22.5; 2024-08-23: -30; 2024-09-13: 26.25; 2024-09-20: 26.25
P66 Borger | 3 | 39 | 0.8478% | 2024-09-02 | 2024-09-04 | FCCs (60) | SU after SD unplanned / Not accounting for any downtime as it was only 1-2 days and underprojected production w/e 9/6 | [14 empty] | OK | 2024-09-06: 0; 2024-09-13: 0
Citgo Corpus Christi | 3 | 25.5 | 0.5543% | 2024-08-21 | 2024-09-07 | Ref | Su after unplanned SD | [14 empty] | OK | 2024-08-23: -3.6429; 2024-08-30: -21.8571; 2024-09-13: 21.8571; 2024-09-20: 3.6429
Marathon Wilmington | 5 | 12.75 | 0.9444% | 2024-09-05 | 2024-09-07 | Ref | Down for 2 days | [14 empty] | OK | 2024-09-06: -3.6429; 2024-09-13: 3.6429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero McKee | 3 | 23 | 0.5% | 2024-08-02 | 2024-09-08 | CDU | CDU restarted 9/5 (20 days early) per IIR, Genscape showing 9/8 S/U | [14 empty] | OK | 2024-08-09: -11.5; 2024-08-16: -11.5; 2024-09-13: 15.3333; 2024-09-20: 7.6667
Marathon St. Paul Park | 2 | 14.3 | 0.5958% | 2024-09-04 | 2024-09-09 | CDU (55 kbd) | up after unplanned SD | [14 empty] | OK | 2024-09-13: -7.15; 2024-09-20: 7.15
PBF Torrance | 5 | 102.45 | 7.589% | 2024-09-07 | 2024-09-09 | CDU (155), FCC (100), HF Alky (25.5)FCCU (105), HCC (24), Vac (98) | Up after unplanned SD/power outage | [14 empty] | OK | 2024-09-13: -14.6357; 2024-09-20: 14.6357; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Flint Hills Corpus Christi | 3 | 15 | 0.3261% | 2024-09-04 | 2024-09-11 | CDU | One day blip - only Genscape reported. Not considering. | [14 empty] | OK | 2024-09-06: 0; 2024-09-20: 0
XOM Baton Rouge | 3 | 56.45 | 1.227% | 2024-09-10 | 2024-09-13 | CDU (35), 6kbd Ref, 25 Coker, and 54 KBD FCC rate cut | Hurricane Francine impact | [14 empty] | OK | 2024-09-13: -16.1286; 2024-09-20: 16.1286
Calcasieu - Lake Charles | 3 | 40.5 | 0.8804% | 2024-09-10 | 2024-09-13 | 2 CDUs (65 kbd ea) | IIR has both CDUs (65 kbd ea) down for Hurricane Francine; Started up 9/13 after hurricane SD | [14 empty] | OK | 2024-09-13: -17.3571; 2024-09-20: 17.3571
Marathon Garyville | 3 | 72.5 | 1.576% | 2024-09-11 | 2024-09-13 | CDU (290) | Hurricane Francine impact; SU on 9/13 according to Genscape | [14 empty] | OK | 2024-09-13: -20.7143; 2024-09-20: 20.7143
Francine Other Refineries cut back | 3 | 7 | 0.1522% | 2024-09-11 | 2024-09-13 | Refineries in the region cut back 5% crude as prep for Hurricane Francine | [15 empty] | OK | 2024-09-13: -2; 2024-09-20: 2
CVR Coffeyville | 2 | 15 | 0.625% | 2024-09-01 | 2024-09-14 | CDU | Up after unplanned SD | [14 empty] | OK | 2024-09-06: -9; 2024-09-20: 6.75; 2024-09-27: 2.25
Cenovus Lima | 2 | 43 | 1.792% | 2024-09-03 | 2024-09-14 | CDU1 (172) | Pulled forward by 10 days | [14 empty] | OK | 2024-09-06: -12.2857; 2024-09-13: -30.7143; 2024-09-20: 36.8571; 2024-09-27: 6.1429
Valero Meraux | 3 | 12.5 | 0.2717% | 2024-09-11 | 2024-09-14 | CDU/VDU (50 kbd) | Unplanned outage due to Francine | [14 empty] | OK | 2024-09-13: -3.5714; 2024-09-20: 3.5714
Total Port Arthur | 3 | 34 | 0.7391% | 2024-09-11 | 2024-09-14 | CDU (165), VDU (55), CDU2 (80), VDU2 (52) | Up after unplanned SD | [14 empty] | OK | 2024-09-13: -6.8; 2024-09-20: 6.8
Cenovus Toledo | 2 | 35.75 | 1.49% | 2024-09-11 | 2024-09-14 | FCCU (55) | SU after unplanned shutdown | [14 empty] | OK | 2024-09-13: -7.15; 2024-09-20: 7.15
Shell Norco | 3 | 2 | 0.04348% | 2024-09-12 | 2024-09-15 | HDC (40) | S/D unplanned due to power issue and rolling into outage | [14 empty] | OK | 2024-09-13: -0.4; 2024-09-20: 0.4
Cenovus Lima | 2 | 34 | 1.417% | 2024-09-13 | 2024-09-18 | Reformer (40) | Planned maintenance (did not move up with CDU change in dates) | [14 empty] | OK | 2024-09-20: -24.2857; 2024-09-27: 24.2857
PBF Delaware City | 1 | 36.55 | 7.615% | 2024-09-15 | 2024-09-19 | Ref | SU after unplanned SD | [14 empty] | OK | 2024-09-20: -20.8857; 2024-09-27: 20.8857
Chevron Richmond | 5 |  | 0% | 2024-09-16 | 2024-09-19 | HDT | No gasoline impact | [14 empty] | OK | 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Citgo Corpus Christi | 3 | 4.4 | 0.09565% | 2024-09-18 | 2024-09-19 | Coker (44) | SU after unplanned SD | [14 empty] | OK | 2024-09-20: -0.44; 2024-09-27: 0.44
Total Port Arthur | 3 | 52 | 1.13% | 2024-09-18 | 2024-09-20 | FCC (80) | FCC SU 9/18 after unplanned Sd | [14 empty] | OK | 2024-09-20: -7.4286; 2024-09-27: 7.4286
XOM Beaumont | 3 | 3.25 | 0.07065% | 2024-09-16 | 2024-09-22 | HDC | SU after unplanned Sd | [14 empty] | OK | 2024-09-20: -2.4375; 2024-10-04: 2.4375
Total Port Arthur | 3 | 20 | 0.4348% | 2024-09-18 | 2024-09-23 | CDU2 (80) | CDU SU after unplanned Sd | [14 empty] | OK | 2024-09-20: -2.8571; 2024-09-27: -8.5714; 2024-10-04: 11.4286
Marathon Catlettsburg | 2 | 115.55 | 4.815% | 2024-09-17 | 2024-09-24 | CDU (255), FCC(98), and Ref (31) | SU after unplanned outages | [14 empty] | OK | 2024-09-20: -57.775; 2024-10-04: 57.775
Big West North Salt Lake | 4 | 8.45 | 2.485% | 2024-09-23 | 2024-09-24 | FCC | up after unplanned sd | [14 empty] | OK | 2024-09-27: -1.2071; 2024-10-04: 1.2071
Lyondell Houston | 3 | 58.5 | 1.272% | 2024-08-29 | 2024-09-25 | FCC | SU after fire. Genscape cameras you can see stack, even though Genscape not officially calling it up yet | [14 empty] | OK | 2024-09-06: -19.5; 2024-09-13: -39; 2024-10-04: 58.5
Woods Cross Refinery | 4 | 3.4 | 1% | 2024-09-23 | 2024-09-26 | HDC and Alky | [15 empty] | OK | 2024-09-27: -1.9429; 2024-10-04: 1.9429
Citgo Lemont | 2 | 18.5 | 0.7708% | 2024-09-25 | 2024-09-27 | CDU/VDU | SD unplanned, genscape has them up, but we have info they are just getting back up | [14 empty] | OK | 2024-09-27: -7.9286; 2024-10-04: 7.9286
P66 Ponca City | 2 | 16.9 | 0.7042% | 2024-09-06 | 2024-09-28 | FCC (26 kbd) | Up per IIR | [14 empty] | OK | 2024-09-13: -12.675; 2024-09-20: -4.225; 2024-10-04: 16.9
Marathon St. Paul Park | 2 | 9.52 | 0.3967% | 2024-09-22 | 2024-09-28 | CR (11.2) | Su after unplanned outage | [14 empty] | OK | 2024-09-27: -4.76; 2024-10-04: 4.76
Total Port Arthur | 3 | 41.25 | 0.8967% | 2024-09-25 | 2024-09-28 | CDU2 (165) | SU after unplanned SD. Was assuming SU of 10/1 | [14 empty] | OK | 2024-09-27: -11.7857; 2024-10-04: 11.7857
Par Billings | 4 | 3 | 0.8824% | 2024-08-01 | 2024-09-29 | Fluid Bed Coker | Planned maint 8/1-9/29 | [14 empty] | OK | 2024-08-09: -3; 2024-10-04: 2.1429; 2024-10-11: 0.85714
Valero McKee | 3 | 35.75 | 0.7772% | 2024-08-02 | 2024-09-29 | FCC | Confirmed SU 9/29 | [14 empty] | OK | 2024-08-09: -25.025; 2024-08-16: -10.725; 2024-08-23: 0; 2024-10-04: 35.75
Valero McKee | 3 | 23.8 | 0.5174% | 2024-08-02 | 2024-09-29 | Reformer/Alky | Confirmed SU 9/29 | [14 empty] | OK | 2024-08-09: -16.66; 2024-08-16: -7.14; 2024-10-04: 23.8
P66 Ponca City | 2 | 28.5 | 1.188% | 2024-09-20 | 2024-09-29 | CDU1 (95 kbd) | IIR updated | [14 empty] | OK | 2024-09-27: -21.375; 2024-10-04: 21.375
Marathon Carson | 5 | 17 | 1.259% | 2024-09-23 | 2024-09-29 | Reformer | Su after unplanned SD | [14 empty] | OK | 2024-09-27: -9.7143; 2024-10-11: 9.7143; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Citgo Lemont | 2 | 17 | 0.7083% | 2024-09-06 | 2024-09-30 | Ref | Planned TA | [14 empty] | OK | 2024-09-13: -11.3333; 2024-09-20: -5.6667; 2024-10-04: 5.6667; 2024-10-11: 11.3333
XOM Baytown | 3 | 17 | 0.3696% | 2024-09-11 | 2024-09-30 | Reformer (HF4) cut back by 20kbd | Planned catalyst C/O | [14 empty] | OK | 2024-09-20: -17; 2024-10-04: 8.5; 2024-10-11: 8.5
XOM Joliet | 2 | 9.5 | 0.3958% | 2024-09-21 | 2024-09-30 | Cut: CDU 30kbd, FCC 25kbd, Ref 15kbd | issues should be resolved 9/30 | [14 empty] | OK | 2024-09-27: -6.7857; 2024-10-04: -2.7143; 2024-10-11: 6.7857; 2024-10-18: 2.7143
Chevron Salt Lake | 4 |  | 0% | 2024-09-23 | 2024-09-30 | Diesle HDT | Sd unplanned assuming 1 wk | [14 empty] | Missing
Flint Hills Pine Bend | 2 | 7.2 | 0.3% | 2024-09-27 | 2024-09-30 | Coker | SU after unaplnned Sd | [14 empty] | OK | 2024-10-04: -3.0857; 2024-10-11: 3.0857
Calcasieu - Lake Charles | 3 | 19.5 | 0.4239% | 2024-09-14 | 2024-10-01 | 1 CDU (65 kbd ea) | SU after unplanned SD | [14 empty] | OK | 2024-09-20: -19.5; 2024-10-04: 19.5
XOM Joliet | 2 | 8.5 | 0.3542% | 2024-09-26 | 2024-10-02 | Ref 10kbd | issues should be resolved 9/30 | [14 empty] | OK | 2024-09-27: -1.2143; 2024-10-04: 1.2143
Marathon El Paso | 3 | 22.8 | 0.4957% | 2024-09-29 | 2024-10-03 | CDU (75), Ref (18) | SU after unplanned SD | [14 empty] | OK | 2024-10-04: -17.1; 2024-10-11: 17.1
Citgo Corpus Christi | 3 | 4.4 | 0.09565% | 2024-09-29 | 2024-10-03 | Coker (44) | SU after unplanned SD | [14 empty] | OK | 2024-10-04: -3.1429; 2024-10-11: 3.1429
XOM Joliet | 2 | 58.5 | 2.438% | 2024-09-30 | 2024-10-03 | FCC SD unplanned | Up on 10/2, expect to be back to full rates on 10/5 | [14 empty] | OK | 2024-10-04: -25.0714; 2024-10-11: 25.0714
XOM Joliet | 2 | 4 | 0.1667% | 2024-09-30 | 2024-10-03 | CDU (40 kbd) | [15 empty] | OK | 2024-10-04: -1.7143; 2024-10-11: 1.7143
Marathon Robinson | 2 | 3.6 | 0.15% | 2024-09-30 | 2024-10-04 | Coker | SU after unplanned SD | [14 empty] | OK | 2024-10-04: -1.8; 2024-10-11: 1.8
Marathon Carson | 5 | 26 | 1.926% | 2024-10-01 | 2024-10-04 | FCC | Su after unplanned SD | [14 empty] | OK | 2024-10-04: -13; 2024-10-11: 13; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Joliet | 2 | 12 | 0.5% | 2024-10-03 | 2024-10-04 | CDU (40 kbd cut) | [15 empty] | OK | 2024-10-04: -1.7143; 2024-10-11: 1.7143
Monroe Trainer | 1 | 34.45 | 7.177% | 2024-10-03 | 2024-10-04 | FCC (53 kbd) | SU after unplanned SD | [14 empty] | OK | 2024-01-05: -4.9214; 2024-01-12: -29.5286; 2024-02-23: 29.5286; 2024-03-01: 4.9214; 2024-10-04: -9.8429; 2024-10-11: 9.8429
Flint Hills Pine Bend | 2 | 7.2 | 0.3% | 2024-10-03 | 2024-10-04 | Coker | SU after unaplnned Sd | [14 empty] | OK | 2024-01-05: -3.0857; 2024-01-12: 3.0857; 2024-10-04: -1.0286; 2024-10-11: 1.0286
Delek El Dorado | 3 | 15.5 | 0.337% | 2024-09-06 | 2024-10-05 | FCC (20) and 10 KBD CDU derate | Planned outage | [14 empty] | OK | 2023-11-10: 13; 2024-09-13: -15.5; 2024-10-11: 15.5
Marathon Garyville | 3 | 36.25 | 0.788% | 2024-09-16 | 2024-10-07 | CDU 10A (145) | SU after T/A | [14 empty] | OK | 2024-09-20: -18.125; 2024-09-27: -18.125; 2024-10-11: 18.125; 2024-10-18: 18.125
Marathon Garyville | 3 | 36.25 | 0.788% | 2024-09-16 | 2024-10-07 | CDU 10B (145) | SU after T/A | [14 empty] | OK | 2024-09-20: -18.125; 2024-09-27: -18.125; 2024-10-11: 18.125; 2024-10-18: 18.125
Flint Hills Pine Bend | 2 | 7.2 | 0.3% | 2024-10-04 | 2024-10-07 | Coker | SU after unplanned SD | [14 empty] | OK | 2024-01-05: -3.0857; 2024-01-12: 3.0857; 2024-10-11: -3.6; 2024-10-18: 3.6
Calcasieu - Lake Charles | 3 | 19.5 | 0.4239% | 2024-09-27 | 2024-10-08 | CDU (65kbd) | SU after unplanned SD | [14 empty] | OK | 2024-10-04: -19.5; 2024-10-11: 8.3571; 2024-10-18: 11.1429
Valero Wilmington | 5 | 36.4 | 2.696% | 2024-10-04 | 2024-10-09 | FCC | SU after unplanned SD | [14 empty] | OK | 2024-10-11: -26; 2024-10-18: 26; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Ponca City | 2 | 2.3 | 0.09583% | 2024-10-07 | 2024-10-09 | Coker (23) | Assuming this is unplanned, 1 wk | [14 empty] | OK | 2024-10-11: -1.15; 2024-10-18: 1.15
Total Port Arthur | 3 | 41.25 | 0.8967% | 2024-10-08 | 2024-10-09 | CDU2 (165) | Up after unplanned SD | [14 empty] | OK | 2024-10-11: -5.8929; 2024-10-18: 5.8929
HF Sinclair Wyoming | 4 | 20.3 | 5.971% | 2024-09-06 | 2024-10-10 | CDU (62), Coker (16) | SD for planned maintenance | [14 empty] | OK | 2024-09-13: -20.3; 2024-10-11: 2.9; 2024-10-18: 17.4
El Segundo | 5 | 55.825 | 4.135% | 2024-09-26 | 2024-10-10 | FCC (72.5), Crude cut (87) | SD unplanned, assuming down to 10/10 per IIR | [14 empty] | OK | 2024-09-27: -13.9563; 2024-10-04: -41.8688; 2024-10-18: 41.8688; 2024-10-25: 13.9563; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Ponca City | 2 | 9.5 | 0.3958% | 2024-09-30 | 2024-10-11 | CDU1 (95 kbd) | IIR updated, SU delayed | [14 empty] | OK | 2024-10-04: -6.7857; 2024-10-11: -2.7143; 2024-10-18: 6.7857; 2024-10-25: 2.7143
Marathon Galveston Bay | 3 | 65.875 | 1.432% | 2024-10-06 | 2024-10-13 | Reformer (77.5) | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-10-11: -47.0536; 2024-10-18: 47.0536
Motiva Port Arthur | 3 | 66.4 | 1.443% | 2024-10-17 | 2024-10-18 | FCCU (81), Alky (9), DC (55), FCCU FHDT (25) | Up after unplanned SD | [14 empty] | OK | 2024-10-18: -18.9714; 2024-10-25: 18.9714
HF Sinclair Tulsa | 2 | 2.55 | 0.1062% | 2024-10-13 | 2024-10-20 | Coker | Up afetr unplanned Sd | [14 empty] | OK | 2024-10-18: -2.55; 2024-10-25: 2.55
Total Port Arthur | 3 | 52.5 | 1.141% | 2024-10-20 | 2024-10-20 | CDU (210) | Up after unplanned SD | [14 empty] | OK | 2024-10-25: -7.5; 2024-11-01: 7.5
PBF Martinez | 5 | 6.25 | 0.463% | 2024-10-18 | 2024-10-21 | Coker (25) | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-10-25: -3.5714; 2024-11-01: 3.5714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Cenovus Superior | 2 | 7.975 | 0.3323% | 2024-10-20 | 2024-10-21 | Alky (FCC 6.5 KBD cut), CDU (15 KBD cut) | SU after unplanned SD | [14 empty] | OK | 2024-10-25: -1.1393; 2024-11-01: 1.1393
Chevron Richmond | 5 | 52 | 3.852% | 2024-08-30 | 2024-10-22 | FCC (80) | Unplanned S/D - Per IIR | [14 empty] | OK | 2024-09-06: -39; 2024-09-13: -13; 2024-10-25: 13; 2024-11-01: 39; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Irving St John | Canada | 0 | #N/A | 2024-09-13 | 2024-10-22 | Alky | Planned TA | [14 empty] | Missing
HF Sinclair El Dorado | 2 | 20.4 | 0.85% | 2024-10-20 | 2024-10-25 | Ref (24) | Removed from scope per IIR | [14 empty] | OK | 2024-10-25: 0; 2024-11-01: 0
Marathon Detroit | 2 | 65.75 | 2.74% | 2024-09-12 | 2024-10-26 | CDU (147), FCC (35), Reformer (22), Coker (28), Alky (10) | Detroit Fall maintenance Moved to 9/12 - 10/23 vs starting 8/30. Full plant (FCC 50kbd on IIR and 37 on Genscape- assuming 45kbd). Genscape still showing up on 9/16 | [14 empty] | OK | 2024-09-20: -46.025; 2024-09-27: -19.725; 2024-11-01: 32.875; 2024-11-08: 5.875; 2024-11-15: 27
Shell Norco | 3 | 2 | 0.04348% | 2024-09-15 | 2024-10-26 | HDC (40) | Extended to 10/29 per ENT | [14 empty] | OK | 2024-09-20: -1.6; 2024-09-27: -0.4; 2024-11-01: 2
Cenovus Lima | 2 | 0 | 0% | 2024-09-25 | 2024-10-27 | CDU2 (52) | Crude unit removed from T/A scope. Crude analyst think we are 60kbd cut back | [14 empty] | OK | 2024-09-27: 0; 2024-10-04: 0; 2024-11-01: 0; 2024-11-08: 0
P66 Ponca City | 2 | 17 | 0.7083% | 2024-09-30 | 2024-10-27 | Reformer (20 kbd) | Extended from 10/20 SU to 10/27 SU per IIR | [14 empty] | OK | 2024-10-04: -11.3333; 2024-10-11: -5.6667; 2024-11-01: 17
United Warren | 1 | 17.5 | 3.646% | 2024-10-11 | 2024-10-27 | VDU (20), DHDT (25), CDU (70) | [15 empty] | OK | 2024-10-18: -17.5; 2024-11-01: 17.5
Valero Three Rivers | 3 | 19.55 | 0.425% | 2024-10-15 | 2024-10-28 | Ref | SD unplanned, assuming 2 wks | [14 empty] | OK | 2024-10-18: -8.3786; 2024-10-25: -11.1714; 2024-11-01: 19.55
Valero Meraux | 3 | 2.75 | 0.05978% | 2024-09-10 | 2024-10-29 | HDC | Shutdown per plan | [14 empty] | OK | 2024-09-20: -2.75; 2024-11-01: 2.75
GCC Galveston Bunkers | 3 | 12.5 | 0.2717% | 2024-08-21 | 2024-10-30 | CDU | Sd unlanned, assuming SU 10/31 (delayed) | [14 empty] | OK | 2024-08-23: -1.7857; 2024-08-30: -10.7143; 2024-11-01: 1.7857; 2024-11-08: 10.7143
HF Sinclair El Dorado | 2 | 5.125 | 0.2135% | 2024-09-23 | 2024-10-30 | Coker (20.5) | SD for planned maintenance | [14 empty] | OK | 2024-09-27: -3.6607; 2024-10-04: -1.4643; 2024-11-01: 5.125
HF Sinclair El Dorado | 2 | 6.15 | 0.2562% | 2024-09-27 | 2024-10-30 | Coker (20.5) | SD for planned maintenance | changed the Sd from 9/27 to 9/21 | [13 empty] | OK | 2024-10-04: -3.5143; 2024-10-11: -2.6357; 2024-11-01: 6.15
Pemex Deer Park | 3 | 9.2 | 0.2% | 2024-10-11 | 2024-10-31 | Coker (92) | Updated timing per IIR | [14 empty] | OK | 2024-10-11: -1.3143; 2024-10-18: -7.8857; 2024-11-01: 9.2
Pemex Deer Park | 3 | 10 | 0.2174% | 2024-10-11 | 2024-10-31 | CDU (100kbd cut) | Updated timing per IIR | [14 empty] | OK | 2024-10-11: -1.4286; 2024-10-18: -8.5714; 2024-11-01: 10
Pemex Deer Park | 3 | 9.75 | 0.212% | 2024-10-11 | 2024-10-31 | FCC (15 kbd cut) | Updated timing per IIR | [14 empty] | OK | 2024-10-11: -1.3929; 2024-10-18: -8.3571; 2024-11-01: 9.75
Calcasieu - Lake Charles | 3 | 19.2 | 0.4174% | 2024-10-29 | 2024-11-01 | CDU (64kbd) | SD unplanned, assuming 2 day outage | [14 empty] | OK | 2024-11-01: -5.4857; 2024-11-08: 5.4857
P66 Wood River | 2 | 16.875 | 0.7031% | 2024-08-30 | 2024-11-02 | DCU (75)/Coker | Moved from 8/30-11/2 to Sep-Oct '25 | [14 empty] | Missing
Woods Cross Refinery | 4 | 5.525 | 1.625% | 2024-10-20 | 2024-11-02 | FCC (8.5) | SU after unplanned SD | [14 empty] | OK | 2024-10-25: -3.9464; 2024-11-08: 3.9464
P66 Lake Charles | 3 | 30.03 | 0.6528% | 2024-09-06 | 2024-11-03 | FCC (46.2) | Down for planned maintenance | [14 empty] | OK | 2024-09-13: -20.02; 2024-09-20: -10.01; 2024-11-08: 10.01; 2024-11-15: 20.02
Citgo Lake Charles | 3 | 44.2 | 0.9609% | 2024-09-27 | 2024-11-03 | Ref (52) | Planned outage, original timing was 9/13-1027 (pulled up to 9/3 unknown end date- assuming 10/17) - now going back to orig timing (9/13-10/27), Genscape showing down as of 9/3. Pushed 1 wk haven't seen confirmation of SD | 2024-11-10 | [13 empty] | OK | 2024-10-04: -33.15; 2024-10-11: -11.05; 2024-11-08: 11.05; 2024-11-15: 33.15
Citgo Lake Charles | 3 | 2.56 | 0.05565% | 2024-09-27 | 2024-11-03 | HC (51.2) | Planned outage, original timing was 9/13-1027 (pulled up to 9/3 unknown end date- assuming 10/17) - now going back to orig timing (9/13-10/27), Genscape showing down as of 9/3. Pushed 1 wk haven't seen confirmation of SD | [14 empty] | OK | 2023-12-08: -30.6057; 2024-10-04: -2.56; 2024-11-08: 2.56
Suncor Commerce City | 4 | 6.045 | 1.778% | 2024-10-19 | 2024-11-03 | FCC (9.3) | SU after unplanned SD | [14 empty] | OK | 2024-10-25: -3.4286; 2024-11-08: 3.4286
United Warren | 1 | 16.25 | 3.385% | 2024-10-22 | 2024-11-03 | FCC(25) | [15 empty] | OK | 2024-10-25: -6.9643; 2024-11-08: 6.9643
Marathon Galveston Bay | 3 | 0 | 0% | 2024-09-09 | 2024-11-04 | Reformer (65.5) | Genscape only source reporting. Assuming it did not come down based on naptha being short and gasoline production coming in high w/e 9/13 | [14 empty] | OK | 2024-11-01: 0; 2024-11-08: 0
Suncor Commerce City | 4 | 6.045 | 1.778% | 2024-10-20 | 2024-11-04 | FCC(9.3) | [15 empty] | OK | 2024-10-25: -4.3179; 2024-11-01: 4.3179
Cenovus Lima | 2 | 26 | 1.083% | 2024-09-03 | 2024-11-05 | FCC(40) | SU extended to 11/8 (originally planned for 10/17) | [14 empty] | OK | 2024-09-06: -7.4286; 2024-09-13: -18.5714; 2024-11-08: 7.4286; 2024-11-15: 18.5714
Chevron Richmond | 5 | 10.4 | 0.7704% | 2024-10-29 | 2024-11-05 | FCC (80) | Unplanned S/D - Per IIR | [14 empty] | OK | 2024-11-01: -10.4; 2024-11-08: 10.4; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
BP Whiting | 2 | 35 | 1.458% | 2024-09-20 | 2024-11-06 | CDU (250), Coker (102) | Coker SD 9/20. CDU SD 9/24 | [14 empty] | OK | 2024-09-27: -25; 2024-10-04: -10; 2024-11-08: 10; 2024-11-15: 25
BP Whiting | 2 | 51 | 2.125% | 2024-09-24 | 2024-11-06 | CR (70) Ref | Down for planned maintenance. SD 9/24 vs 9/20 | [14 empty] | OK | 2024-09-27: -36.4286; 2024-10-04: -14.5714; 2024-11-08: 14.5714; 2024-11-15: 36.4286
Mobile Refinery (Vertex) | 3 | 15.475 | 0.3364% | 2024-10-04 | 2024-11-07 | CDU (40 kbd) / Reformer (13.5 kbd) | Planned maintenance (10/4-11/12) | [14 empty] | OK | 2024-10-11: -12.38; 2024-10-18: -3.095; 2024-11-15: 7.7375; 2024-11-22: 7.7375
Pemex Deer Park | 3 | 25.5 | 0.5543% | 2024-10-06 | 2024-11-08 | Ref (30) | Updated timing per IIR | [14 empty] | OK | 2024-10-11: -25.5; 2024-11-15: 12.75; 2024-11-22: 12.75
Pemex Deer Park | 3 | 38.25 | 0.8315% | 2024-11-06 | 2024-11-08 | Ref (45) | Genscape first reported s/d unplanned(assuming 1 wk) | [14 empty] | OK | 2024-11-08: -10.9286; 2024-11-15: 10.9286
Cenovus Lima | 2 | 7.75 | 0.3229% | 2024-09-03 | 2024-11-09 | Coker (31) | SU extended to 11/8 (originally planned for 10/17) | [14 empty] | OK | 2024-09-06: -2.2143; 2024-09-13: -5.5357; 2024-11-15: 5.5357; 2024-11-22: 2.2143
P66 LA/Wilmington | 5 | 32.5 | 2.407% | 2024-11-06 | 2024-11-09 | FCC (51.6) | Up after unplanned SD | [14 empty] | OK | 2024-11-08: -13.9286; 2024-11-15: 13.9286; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Cenovus Lima | 2 | 13.75 | 0.5729% | 2024-09-03 | 2024-11-10 | 55 kbd CDU cut due to FCC/Coker outage | Added on 9/3 due to ENT reporting | [14 empty] | OK | 2024-09-06: -5.8929; 2024-09-13: -7.8571; 2024-11-15: 7.8571; 2024-11-22: 5.8929
El Segundo | 5 | 51 | 3.778% | 2024-09-09 | 2024-11-10 | Reformer (60) | Down 9/9 per IIR for planned maintenance; pushed out to 11/17 from 11/11 | [14 empty] | OK | 2024-09-13: -40.8; 2024-09-20: -10.2; 2024-11-15: 25.5; 2024-11-22: 25.5; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Galveston Bay | 3 | 12 | 0.2609% | 2024-09-10 | 2024-11-10 | Hydrocracker (60 kbd) | assuming down for planned mainteance | [14 empty] | OK | 2024-09-13: -3.4286; 2024-09-20: -8.5714; 2024-11-15: 3.4286; 2024-11-22: 8.5714
Marathon Texas City | 3 | 39 | 0.8478% | 2024-11-08 | 2024-11-11 | FCC (60) | short unplanned SD no real impact | [14 empty] | OK | 2024-11-15: -16.7143; 2024-11-22: 16.7143
Calcasieu - Lake Charles | 3 | 21.9 | 0.4761% | 2024-10-29 | 2024-11-12 | CDU (73kbd) | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-11-01: -6.2571; 2024-11-15: 1.7878; 2024-11-22: 4.4694
Irving St John | Canada | 1.7 | #N/A | 2024-11-04 | 2024-11-13 | HC (34) | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-11-08: -1.7; 2024-11-15: 1.7
HF Sinclair El Dorado | 2 | 26 | 1.083% | 2024-09-23 | 2024-11-14 | FCC (40), Alky (14) | SD for planned maintenance. Confirmed back up on 11/15 | Restart 11/13 per IIR | [13 empty] | OK | 2024-09-27: -18.5714; 2024-10-04: -7.4286; 2024-11-22: 18.5714; 2024-11-29: 7.4286
HF Sinclair El Dorado | 2 | 26.25 | 1.094% | 2024-09-24 | 2024-11-14 | CDU derate (87.5 KBD) | SD for planned maintenance. Confirmed back up on 11/15 | [14 empty] | OK | 2024-09-27: -11.25; 2024-10-04: -15; 2024-11-22: 15; 2024-11-29: 11.25
Monroe Trainer | 1 | 6.25 | 1.302% | 2024-10-23 | 2024-11-14 | VDU(26) | SD unplanned, assuming 25 kbd crude cut and 2 week duration | [14 empty] | OK | 2024-10-25: -1.7857; 2024-11-01: -4.4643; 2024-11-15: 1.7857; 2024-11-22: 4.4643
Monroe Trainer | 1 | 34.45 | 7.177% | 2024-10-03 | 2024-11-15 | FCC (53 kbd) | Previously had FCC outage 9/15-10/28, outage has not started yet | [14 empty] | OK | 2024-10-04: 0; 2024-10-11: 0; 2024-11-22: 0; 2024-11-29: 0
P66 LA/Wilmington | 5 | 43.86 | 3.249% | 2024-10-22 | 2024-11-15 | Ref (16) | SD unplanned, assuming 1 wk downtime | [14 empty] | OK | 2024-10-25: -18.7971; 2024-11-01: -25.0629; 2024-11-22: 18.7971; 2024-11-29: 25.0629; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero Houston | 3 | 2.5 | 0.05435% | 2024-11-05 | 2024-11-15 | HC(50) | Added on 11/8 used 5% as MoGas impact from HC 50KBD capacity. Came back up on 11/16 | [14 empty] | OK | 2024-11-01: -1.4286; 2024-11-08: -1.0714; 2024-11-15: 1.4286; 2024-11-22: 1.0714
P66 Ponca City | 2 | 2.3 | 0.09583% | 2024-11-10 | 2024-11-17 | Coker (23) | Assuming this is unplanned, 1 wk | [14 empty] | OK | 2024-11-15: -1.725; 2024-11-22: 1.725
XOM Beaumont | 3 | 5 | 0.1087% | 2024-11-13 | 2024-11-17 | Coker rate cut | [15 empty] | OK | 2024-11-15: -2.1429; 2024-11-22: 2.1429
El Segundo | 5 | 2.75 | 0.2037% | 2024-09-08 | 2024-11-18 | HDC (55) | Down 9/9 per IIR for planned maintenance | Restarted | [13 empty] | OK | 2023-11-24: -37.7; 2023-12-01: -9.425; 2023-12-08: 32.9875; 2023-12-15: 14.1375; 2024-09-13: -2.75; 2024-11-22: 2.75; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
BP Whiting | 2 | 87.5 | 3.646% | 2024-11-07 | 2024-11-18 | CDU (250), Coker (102) | CDU staying down until 11/18 | [14 empty] | OK | 2024-11-15: -61.25; 2024-11-22: 30.625; 2024-11-29: 30.625
Valero Port Arthur | 3 | 66.25 | 1.44% | 2024-11-08 | 2024-11-19 | CDU | 265 kbd CDU went down unplanned the morning of 11/8, according to Genscape . Updated outage date to 11/19 vs 11/22 per Genscape | [14 empty] | OK | 2024-11-15: -53; 2024-11-22: 53
Cenovus Toledo | 2 | 1.875 | 0.07812% | 2024-11-11 | 2024-11-19 | Coker (7.5) | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-11-15: -1.0714; 2024-11-29: 1.0714
XOM Baytown | 3 | 79.95 | 1.738% | 2024-11-13 | 2024-11-20 | FCC (123) | Hot Stanby due to SV101 leak CLEU Sour Gas limit / no fueling Assuming 5 day outage | [14 empty] | OK | 2024-11-15: -47.97; 2024-11-22: -45.6857; 2024-11-29: 79.95
Marathon Carson | 5 | 17 | 1.259% | 2024-11-16 | 2024-11-20 | Reformer (20) | Planned SD; extended a week center still looks S/D | [14 empty] | OK | 2024-11-22: -12.1429; 2024-11-29: 12.1429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Paulsboro | 1 | 2.7 | 0.5625% | late 2020 | 2024-11-20 | Coker (27) | SU Coker in 4Q24 after being SD since '20 | [14 empty] | OK | 2024-11-22: 2.7
BP Whiting | 2 | 87.5 | 3.646% | 2024-11-06 | 2024-11-21 | CDU (250), Coker (102) | Coker SD 9/20. CDU SD 9/24 | [14 empty] | OK | 2024-11-08: -37.5; 2024-11-15: -50; 2024-11-22: 37.5; 2024-11-29: 50
Marathon Catlettsburg | 2 | 63.7 | 2.654% | 2024-11-12 | 2024-11-22 | FCC(98) | SD unplanned, assuing 1 wk | [14 empty] | OK | 2024-11-15: -27.3; 2024-11-22: -36.4; 2024-11-29: 36.4; 2024-12-06: 27.3
Marathon Catlettsburg | 2 | 13 | 0.5417% | 2024-11-15 | 2024-11-22 | CDU assuming 50 kbd cut due to VGO containment | [15 empty] | OK | 2024-11-22: -10.4; 2024-11-29: 10.4
Citgo Corpus Christi | 3 | 45.5 | 0.9891% | 2024-11-18 | 2024-11-22 | FCC (70) | SU after unplanned SD | [14 empty] | OK | 2024-11-22: -26; 2024-11-29: 26
P66 Lake Charles | 3 | 10.2 | 0.2217% | 2024-10-15 | 2024-11-23 | Ref (12) | Down for planned maint per Chem team | [14 empty] | OK | 2024-10-18: -4.3714; 2024-10-25: -5.8286; 2024-12-06: 7.2857; 2024-12-13: 2.9143
PBF Toledo | 2 | 25.5 | 1.062% | 2024-11-11 | 2024-11-23 | Ref (30) | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-11-15: -14.5714; 2024-11-29: 14.5714
PBF Delaware City | 1 | 36.55 | 7.615% | 2024-11-21 | 2024-11-23 | Ref(43), | Sd unplanned assuming 1 wk; removed FCC (82) 11/21 | [14 empty] | OK | 2024-11-22: -10.4429; 2024-11-29: 10.4429
PBF Chalmette | 3 | 63.2375 | 1.375% | 2024-09-27 | 2024-11-27 | CDU1 (96)/CDU2 (96), DCU (42) and Ref(17.5) are cut back and FCC(68) 100% offline | Confirmed SD for planned TA 9/27. CDUs/Cokers/Ref are now cut back vs 100% offline | updated SU to 11/17 from 11/22 | [13 empty] | OK | 2024-10-04: -36.1357; 2024-10-11: -27.1018; 2024-11-29: 27.1018; 2024-12-06: 36.1357
Marathon Carson | 5 | 22.1 | 1.637% | 2024-11-01 | 2024-11-27 | Reformer (26) | Planned SD; extended a week center still looks S/D | [14 empty] | OK | 2024-11-01: -3.1571; 2024-11-08: -18.9429; 2024-11-29: 9.4714; 2024-12-06: 12.6286; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero Houston | 3 | 24.7 | 0.537% | 2024-11-26 | 2024-11-27 | CDU (95 kbd) | [15 empty] | OK | 2024-11-29: -7.0571; 2024-12-06: 7.0571
Delek Krotz Springs | 3 | 18.45 | 0.4011% | 2024-10-12 | 2024-12-01 | CDU (74 kbd) / FCC (32.5 kbd) / Ref (13 kbd) / Alky (5 kbd) | IIR updated timing from 10/12-11/22 to 10/12-12/1 | [14 empty] | OK | 2024-10-18: -15.6825; 2024-10-25: -2.7675; 2024-12-06: 10.5429; 2024-12-13: 7.9071
CVR Wynnewood | 2 | 19.5 | 0.8125% | 2024-11-30 | 2024-12-01 | CDU (39), VDU (27), CDU2 (39) | SU after unplanned SD | [14 empty] | OK | 2024-12-06: -5.5714; 2024-12-13: 5.5714
Valero Meraux | 3 | 27.2 | 0.5913% | 2024-10-01 | 2024-12-02 | Ref (32) | SD still. Pushed out another week to 11/22' Pushed out another week; s/u 12.2 | [14 empty] | OK | 2024-10-04: -13.6; 2024-10-11: -13.6; 2024-12-06: 13.6; 2024-12-13: 13.6
Chevron Pasadena | 3 | 32 | 0.6957% | 2024-10-04 | 2024-12-04 | CDU (100 kbd) / Reformer (24 kbd)/ VDU | Planned maintenance (10/4-11/12). Entire plant SD for project tie-ins' Extended from 11/18 to 11/27 | [14 empty] | OK | 2024-10-11: -32; 2024-12-06: 4.5714; 2024-12-13: 27.4286
PBF Torrance | 5 | 2.5 | 0.1852% | 2024-10-14 | 2024-12-06 | Planned DCU outage (25 kbd) | Per IIR 10/14-11/22 | [14 empty] | OK | 2024-10-18: -1.75; 2024-10-25: -0.75; 2024-12-13: 1.75; 2024-12-20: 0.75; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Borger | 3 | 5.95 | 0.1293% | 2024-11-13 | 2024-12-06 | Ref | SD unplanned, pushed out another week (2 weeks); pushed out to 12/13; up on 12/6 per Genscape | [14 empty] | OK | 2024-11-15: -2.55; 2024-11-22: -3.4; 2024-12-06: 3.4; 2024-12-13: 2.55
Marathon Robinson | 2 | 3 | 0.125% | 2024-12-02 | 2024-12-07 | Coker | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-12-06: -2.5714; 2024-12-13: 2.5714
Cenovus Toledo | 2 | 1.875 | 0.07812% | 2024-12-04 | 2024-12-10 | Coker (7.5) | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-12-06: -0.80357; 2024-12-13: 0.80357
Puget Sound | 5 | 6.325 | 0.4685% | 2024-12-09 | 2024-12-10 | Coker (25.3) | SD unplanned, assuming 1 wk | [14 empty] | OK | 2024-12-13: -0.90357; 2024-12-20: 0.90357
XOM Baytown | 3 | 21.25 | 0.462% | 2024-10-31 | 2024-12-12 | Reformer (HF3) cut back by 25kbd | Planned catalyst C/O | [14 empty] | OK | 2024-11-01: -3.0357; 2024-11-08: -18.2143; 2024-12-13: 3.0357; 2024-12-20: 18.2143
Marathon Wilmington | 5 | 10.5 | 0.7778% | 2024-11-22 | 2024-12-12 | Coker (42) | Came back up on 12/12 | [14 empty] | OK | 2024-11-29: -10.5; 2024-12-20: 10.5; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Carson | 5 | 19 | 1.407% | 2024-12-02 | 2024-12-12 | CDU (65), VDU (62), HC (55) | ENT has it back up on 12/12 | [14 empty] | OK | 2024-12-06: -10.8571; 2024-12-13: -8.1429; 2024-12-20: 10.8571; 2024-12-27: 8.1429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Delaware City | 1 | 0.9 | 0.1875% | 2024-11-29 | 2024-12-13 | HDC (18) | Assuming 1 week outages; pushed out one more week on 12/6; Extended to 12/20 | [14 empty] | OK | 2024-12-06: -0.9; 2024-12-20: 0.9
XOM Joliet | 2 | 18 | 0.75% | 2024-12-02 | 2024-12-15 | CDU (20 kbd cut), 20 kbd FCC cut | [15 empty] | OK | 2024-12-06: -10.2857; 2024-12-13: -7.7143; 2024-12-20: 7.7143; 2024-12-27: 10.2857
Marathon Wilmington | 5 | 12.75 | 0.9444% | 2024-12-03 | 2024-12-17 | Ref(15) | Down per genscape | [14 empty] | OK | 2024-12-06: -31.0714; 2024-12-20: 31.0714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Shell Norco | 3 | 72.5 | 1.576% | 2024-12-12 | 2024-12-17 | CDU5 (240), VDU (91.3), DC (25) | [15 empty] | OK | 2024-12-20: -46.6071; 2024-12-27: 46.6071
Marathon St. Paul Park | 2 | 20.8 | 0.8667% | 2024-12-15 | 2024-12-18 | FCC (32 kbd) | up after unplanned SD | [14 empty] | OK | 2024-12-20: -8.9143; 2024-12-27: 8.9143
Delek Krotz Springs | 3 | 21.125 | 0.4592% | 2024-10-12 | 2024-12-20 | FCC (32.5 kbd) | IIR reported FCC is coming up later now (prev. 12/1); IIR pushed startup back to 12/20 | [14 empty] | OK | 2024-10-18: -17.9563; 2024-10-25: -3.1687; 2024-12-27: 17.9563; 2025-01-03: 3.1687
Marathon Texas City | 3 | 13.11 | 0.285% | 2024-12-13 | 2024-12-20 | FCC (60) | short unplanned SD no real impact | [14 empty] | OK | 2024-12-20: -11.1435; 2024-12-27: 11.1435
PBF Torrance | 5 | 14.45 | 1.07% | 2024-11-27 | 2024-12-23 | Planned maintenance of 17 kbd Reformer | [15 empty] | OK | 2024-11-29: -4.1286; 2024-12-06: -10.3214; 2024-12-27: 10.3214; 2025-01-03: 4.1286; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
El Segundo | 5 | 51 | 3.778% | 2024-12-17 | 2024-12-24 | Reformer (60) | Down unplanned on 12/17 - assuming 1 wk downtime. (Per IIR & Genscape) | [14 empty] | OK | 2024-12-20: -21.8571; 2024-12-27: 21.8571; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
El Segundo | 5 | 2.75 | 0.2037% | 2024-12-17 | 2024-12-24 | HDC (55) | Down unplanned on 12/17 - assuming 1 wk downtime. (Per IIR & Genscape) | [14 empty] | OK | 2024-12-20: -1.1786; 2024-12-27: 1.1786; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Salt Lake City | 4 | 17.16 | 5.047% | 2024-12-07 | 2024-12-25 | FCC(26.4) | Uplanned shutdown on 12/7 per Genscape | [14 empty] | OK | 2024-12-13: -17.16; 2024-12-27: 4.9029; 2025-01-03: 12.2571
Valero Port Arthur | 3 | 16.5 | 0.3587% | 2024-12-27 | 2024-12-29 | Coker (55) | Reported as an upset on 12/27. Assuming 1 wk downtime | [14 empty] | OK | 2025-01-03: -4.7143; 2025-01-10: 4.7143
Chevron Salt Lake City | 4 | 3 | 0.8824% | 2024-11-22 | 2024-12-31 | Coker (10 kbd) | Unplanned outage on 11/22. Assuming 1 wk outage; revised to 2day outage | [14 empty] | OK | 2024-11-29: -1.7143; 2024-12-06: -1.2857; 2025-01-03: 3
Marathon Carson | 5 | 2.75 | 0.2037% | 2024-12-24 | 2024-12-31 | HC (55) | Up after unplanned SD | [14 empty] | OK | 2024-12-27: -1.1786; 2025-01-03: 1.1786; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
HF Sinclair - Tulsa West | 2 | 2.55 | 0.1062% | 2024-12-12 | 2025-01-02 | Coker (8.5) | [7 empty] | -0.16452 | [7 empty] | OK | 2024-12-20: -2.04; 2024-12-27: -0.51; 2025-01-03: 2.55
Suncor Commerce City | 4 | 9.75 | 2.868% | 2024-12-25 | 2025-01-03 | CDU (39), VDU (8.375) | SD unplanned assuming 1 wk | [6 empty] | -0.94355 | [7 empty] | OK | 2024-12-27: -2.7857; 2025-01-03: -6.9643; 2025-01-10: 2.7857; 2025-01-17: 6.9643
Valero Port Arthur | 3 | 0 | 0% | 2024-12-29 | 2025-01-03 | Coker (100) | Reported as an upset on 12/27. Assuming 1 wk downtime | [6 empty] | 0 | [7 empty] | OK | 2025-01-03: 0; 2025-01-10: 0
BP Cherry Point | 5 | 2.75 | 0.2037% | 2024-12-28 | 2025-01-04 | HDC (55) | SD unplanned, assuming 1 wk | [6 empty] | -0.35484 | [7 empty] | OK | 2025-01-03: -2.3571; 2025-01-10: 2.3571; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero Three Rivers | 3 | 55.5 | 1.207% | 2025-01-01 | 2025-01-06 | CDU (95),Alky (6.5), CCR (34), FCCU (24), HDC (10) | Up after unplanned sd | [6 empty] | -8.9516 | [7 empty] | OK | 2025-01-03: -7.9286; 2025-01-10: -15.8571; 2025-01-17: 47.175; 2025-01-24: 8.325
Cenovus Lima | 2 | 34 | 1.417% | 2024-12-31 | 2025-01-08 | Reformer (40) | Up after unplanned SD | [14 empty] | OK | 2025-01-03: -14.5714; 2025-01-17: 14.5714
Valero McKee | 3 | 25.3 | 0.55% | 2025-01-06 | 2025-01-08 | CR (28), HC (30) | SD unplanned, assuming 3 days per IIR | [6 empty] | -1.6323 | [7 empty] | OK | 2025-01-10: -10.8429; 2025-01-17: 10.8429
XOM Joliet | 2 | 8.75 | 0.3646% | 2025-01-02 | 2025-01-10 | Coker/CDU cuts | Coker issue driving CDU cut | [6 empty] | -2.2581 | [7 empty] | OK | 2025-01-03: -1.25; 2025-01-10: -7.5; 2025-01-17: 7.5; 2025-01-24: 1.25
Valero Port Arthur | 3 | 29.9 | 0.65% | 2024-12-27 | 2025-01-12 | CDU (115) | CDU had fire on 12/27. Assuming 1 wk of downtime | [14 empty] | OK | 2025-01-03: -23.92; 2025-01-10: -5.98; 2025-01-17: 8.5429; 2025-01-24: 21.3571
Calcasieu - Lake Charles | 3 | 19.5 | 0.4239% | 2025-01-03 | 2025-01-12 | CDU (65) | Up after planned T/A | 8.8065 | [5 empty] | -5.6613 | [7 empty] | OK | 2025-01-10: -19.5; 2025-01-17: 13.9286; 2025-01-24: 5.5714
Marathon Galveston Bay | 3 | 93.55 | 2.034% | 2025-01-06 | 2025-01-13 | CDU (265),FCC (140) | FCC removed from scope (assuming it is at min during TA) | [6 empty] | -21.1242 | [7 empty] | OK | 2025-01-10: -53.4571; 2025-01-24: 53.4571
Marathon Carson | 5 | 2.75 | 0.2037% | 2025-01-09 | 2025-01-13 | HC (55) | Up after unplanned SD | [6 empty] | -0.35484 | [7 empty] | OK | 2025-01-10: -0.39286; 2025-01-24: 0.39286; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Carson | 5 | 13.25 | 0.9815% | 2025-01-12 | 2025-01-15 | Coker (53) | Su after unplanned SD | [6 empty] | -1.2823 | [7 empty] | OK | 2025-01-17: -5.6786; 2025-01-24: 5.6786; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Calcasieu - Lake Charles | 3 | 19.5 | 0.4239% | 2025-01-12 | 2025-01-15 | Assuming the 2nd CDU will SD after the first CDU | 2nd CDU up early on will monitor for future SD | [6 empty] | -1.8871 | [7 empty] | OK | 2025-01-17: -8.3571; 2025-01-24: 8.3571
Valero Ardmore | 2 | 0.7 | 0.02917% | 2025-01-14 | 2025-01-15 | Hydrocracker (14) | SU after unplanned SD | [6 empty] | -0.022581 | [7 empty] | OK | 2025-01-17: -0.1; 2025-01-24: 0.1
Puget Sound | 5 | 2.53 | 0.1874% | 2025-01-14 | 2025-01-15 | Coker(25.3) | Up after unplanned SD | [6 empty] | -0.081613 | [7 empty] | OK | 2025-01-17: -0.36143; 2025-01-24: 0.36143
Suncor Commerce City | 4 | 11.7 | 3.441% | 2025-12-27 | 2025-01-15 | CDU (39) | Unplanned SD | [14 empty] | OK | 2025-01-03: -11.7; 2025-01-17: 5.0143; 2025-01-24: 6.6857
XOM Joliet | 2 | 13.75 | 0.5729% | 2025-01-10 | 2025-01-16 | CDU cut (40) | Coker issue driving CDU cut | [6 empty] | -2.6613 | [7 empty] | OK | 2025-01-17: -11.7857; 2025-01-24: 11.7857
Valero McKee | 3 | 48.45 | 1.053% | 2025-01-11 | 2025-01-16 | CDU (70), HDC (30), Ref (47) | Up after unplanned SD | [6 empty] | -7.8145 | [7 empty] | OK | 2025-01-17: -41.5286; 2025-01-24: 41.5286
XOM Baton Rouge | 3 | 25 | 0.5435% | 2025-01-14 | 2025-01-16 | PS7 (100) | Unplanned SD due to leak on nozzle | [6 empty] | -1.6129 | [7 empty] | OK | 2025-01-17: -10.7143; 2025-01-24: 10.7143
Valero McKee | 3 | 49.4 | 1.074% | 2025-01-06 | 2025-01-17 | FCC (76) | SD unplanned, assuming 3 days per IIR | [6 empty] | -17.529 | [7 empty] | OK | 2025-01-10: -35.2857; 2025-01-17: -14.1143; 2025-01-24: 14.1143; 2025-01-31: 35.2857
El Segundo | 5 | 31.35 | 2.322% | 2024-12-19 | 2025-01-18 | Alky(33) | Added on 1/20 | [14 empty] | OK | 2023-12-22: -13.4357; 2023-12-29: -17.9143; 2024-01-19: 4.4786; 2024-01-26: 26.8714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Joliet | 2 | 10 | 0.4167% | 2025-01-16 | 2025-01-18 | Coker cuts (40) | Coker issue driving CDU cut | [6 empty] | -0.64516 | [7 empty] | OK | 2025-01-17: -1.4286; 2025-01-24: 1.4286
Marathon Galveston Bay | 3 | 55.675 | 1.21% | 2025-01-13 | 2025-01-20 | Reformer (65.5) | SD, assuming unplanned and 1 wk duration | [6 empty] | -12.5718 | [7 empty] | OK | 2025-01-17: -31.8143; 2025-01-31: 31.8143
Marathon Galveston Bay | 3 | 53.8 | 1.17% | 2025-01-13 | 2025-01-20 | CDU (265),FCC (140) | Adjusting production offline due to reformer outage | [6 empty] | -12.1484 | [7 empty] | OK | 2025-01-17: -30.7429; 2025-01-31: 30.7429
Chevron Pasadena | 3 | 6.25 | 0.1359% | 2025-12-05 | 2025-01-21 | CDU derate (25 KBD) | CDU derate per IIR; pushed back half a week | [14 empty] | OK | 2024-12-06: -0.89286; 2024-12-13: -5.3571; 2025-01-24: 6.25
Monroe Trainer | 1 | 26 | 5.417% | 2025-01-21 | 2025-01-22 | CDU (104) | SD unplanned, assuming 1 wk | [6 empty] | -0.83871 | [7 empty] | OK | 2025-01-24: -3.7143; 2025-01-31: 3.7143
Lyondell Houston | 3 | 14.625 | 0.3179% | 2025-01-22 | 2025-01-22 | FCC | One day blip per IIR | [6 empty] | 0 | [7 empty] | OK | 2025-01-24: -2.0893; 2025-01-31: 2.0893
Total Port Arthur | 3 | 16.5 | 0.3587% | 2025-01-20 | 2025-01-23 | CDU cut due to freeze (60) | [7 empty] | -1.5968 | [7 empty] | OK | 2025-01-24: -9.4286; 2025-01-31: 9.4286
CVR Coffeyville | 2 | 21.25 | 0.8854% | 2025-01-21 | 2025-01-23 | Ref (25) | SD due to fire | [6 empty] | -1.371 | [7 empty] | OK | 2025-01-24: -6.0714; 2025-01-31: 6.0714
Motiva Port Arthur | 3 | 99.7 | 2.167% | 2025-01-21 | 2025-01-23 | FCC (81), Ref (49), Coker (54) | Assume it is down until T/Aon | [6 empty] | -6.4323 | [7 empty] | OK | 2025-01-24: -42.7286; 2025-01-31: 42.7286
Monroe Trainer | 1 | 6.25 | 1.302% | 2025-01-21 | 2025-01-23 | VDU(26) | SD unplanned, assuming 25 kbd crude cut and | [6 empty] | -0.40323 | [7 empty] | OK | 2025-01-24: -2.6786; 2025-01-31: 2.6786
PBF Chalmette | 3 | 11.875 | 0.2582% | 2025-01-22 | 2025-01-23 | Alky (12.5) | Up after unplanned SD | [6 empty] | -0.38306 | [7 empty] | OK | 2025-01-24: -1.6964; 2025-01-31: 1.6964
El Segundo | 5 | 31.35 | 2.322% | 2025-01-12 | 2025-01-24 | Alky(33) | Excluding for now 1/24 | past | [5 empty] | -12.1355 | [7 empty] | OK | 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero Three Rivers | 3 | 19.55 | 0.425% | 2025-01-20 | 2025-01-24 | Ref (23) | SD unplanned assuming 1 wk | [6 empty] | -2.5226 | [7 empty] | OK | 2025-01-24: -11.1714; 2025-02-07: 11.1714
Other Refinery Cuts due to Freeze | 3 | 61.8975 | 1.346% | 2025-01-20 | 2025-01-24 | 3% CDU cut at refineries in affected region | Freeze | [6 empty] | -7.9868 | [7 empty] | OK | 2025-01-24: -35.37; 2025-02-07: 35.37
XOM Baytown | 3 | 2.5 | 0.05435% | 2025-01-21 | 2025-01-24 | Crude cut due to freeze | [7 empty] | -0.24194 | [7 empty] | OK | 2025-01-24: -1.4286; 2025-01-31: 1.4286
XOM Baton Rouge | 3 | 2.5 | 0.05435% | 2025-01-21 | 2025-01-24 | Crude cut due to freeze | [7 empty] | -0.24194 | [7 empty] | OK | 2025-01-24: -1.4286; 2025-01-31: 1.4286
Valero St Charles | 3 | 16.5 | 0.3587% | 2025-01-21 | 2025-01-24 | CDU cut due to freeze (73) | [7 empty] | -1.5968 | [7 empty] | OK | 2025-01-24: -7.0714; 2025-01-31: 7.0714
Marathon Wilmington | 5 | 39.9 | 2.956% | 2025-01-13 | 2025-01-25 | CDU (103), Ref (28), HDC (32), Coker (42) | 3 day SD per IIR; extending still looks cold + Crane onsite | [6 empty] | -15.4452 | [7 empty] | OK | 2025-01-17: -17.1; 2025-01-24: -22.8; 2025-01-31: 17.1; 2025-02-07: 22.8; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Beaumont | 3 | 53.75 | 1.168% | 2025-01-20 | 2025-01-25 | CDU cut (155), FCC (10), Ref (10) | Freeze | [6 empty] | -8.6694 | [7 empty] | OK | 2025-01-24: -30.7143; 2025-01-31: 30.7143
HF Sinclair Tulsa East | 2 | 18.875 | 0.7865% | 2025-01-14 | 2025-01-26 | CDU (75.5) | Up after unplanned SD | [6 empty] | -7.3065 | [7 empty] | OK | 2025-01-17: -8.0893; 2025-01-24: -10.7857; 2025-01-31: 18.875
HF Sinclair - Tulsa West | 2 | 2.55 | 0.1062% | 2025-01-16 | 2025-01-26 | Coker (8.5) | Up after unplanned SD | [6 empty] | -0.82258 | [7 empty] | OK | 2025-01-17: -0.36429; 2025-01-24: -2.1857; 2025-01-31: 2.55
P66 Lake Charles | 3 | 30.03 | 0.6528% | 2025-01-20 | 2025-01-27 | FCC (46.2) | SD due to freeze | [6 empty] | -6.781 | [7 empty] | OK | 2025-01-24: -17.16; 2025-02-07: 17.16
Marathon Garyville | 3 | 21.45 | 0.4663% | 2025-01-20 | 2025-01-27 | CDU (275) | Crude cut due to freeze | [6 empty] | -4.8435 | [7 empty] | OK | 2025-01-24: -12.2571; 2025-01-31: 12.2571
Marathon Catlettsburg | 2 | 26 | 1.083% | 2025-01-21 | 2025-01-27 | CDU (104) | SD unplanned, assuming 1 wk | [6 empty] | -5.0323 | [7 empty] | OK | 2025-01-24: -11.1429; 2025-01-31: 11.1429
Lyondell Houston | 3 | 17.5 | 0.3804% | 2025-01-21 | 2025-01-27 | Crude cut due to freeze | Assumed a 30% cut due to elevated flaring | [6 empty] | -3.3871 | [7 empty] | OK | 2025-01-24: -7.5; 2025-01-31: 7.5
Valero Houston | 3 | 15 | 0.3261% | 2025-01-21 | 2025-01-28 | Crude cut due to freeze | Assumed a 30% cut due to elevated flaring | [6 empty] | -3.3871 | [7 empty] | OK | 2025-01-24: -8.5714; 2025-01-31: 8.5714
HF Sinclair El Dorado | 3 | 12.5 | 0.2717% | 2025-01-21 | 2025-01-28 | Crude cut due to freeze | Assumed a 30% cut due to elevated flaring | [6 empty] | -2.8226 | [7 empty] | OK | 2025-01-24: -7.1429; 2025-01-31: 7.1429
PBF Toledo | 2 | 23.5 | 0.9792% | 2025-01-26 | 2025-01-28 | CDU(94) | Up after unplanned SD | [6 empty] | -1.5161 | [7 empty] | OK | 2025-01-31: -6.7143; 2025-02-07: 6.7143
Citgo Lemont | 2 | 18.05 | 0.7521% | 2025-01-27 | 2025-01-28 | Alky (19) | [7 empty] | -0.58226 | [7 empty] | OK | 2025-01-31: -2.5786; 2025-02-07: 2.5786
Citgo Corpus Christi | 3 | 41.25 | 0.8967% | 2025-01-15 | 2025-01-29 | CDU (165) | Planned TA 1/15-26 (delayed by 9 days), pushed out by 3 days due to not being up on 1/27 | [6 empty] | -18.629 | [7 empty] | OK | 2025-01-17: -11.7857; 2025-01-24: -29.4643; 2025-02-07: 29.4643; 2025-02-14: 11.7857
World Oil South Gate Asphalt | 5 | 2.125 | 0.1574% | 2025-01-20 | 2025-01-29 | CDU (8.5), VDU (7), Asphalt (5.8) | Planned outage | [6 empty] | -0.61694 | [7 empty] | OK | 2025-01-24: -1.2143; 2025-02-07: 1.2143; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Calcasieu - Lake Charles | 3 | 18.25 | 0.3967% | 2025-01-20 | 2025-01-29 | CDU (73kbd) | SD due to freeze | [6 empty] | -5.2984 | [7 empty] | OK | 2025-01-24: -10.4286; 2025-02-07: 10.4286
Valero St Charles | 3 | 16.25 | 0.3533% | 2025-01-22 | 2025-01-29 | Crude cut due to freeze | Assumed a 30% cut due to elevated flaring | [6 empty] | -3.6694 | [7 empty] | OK | 2025-01-24: -6.9643; 2025-02-07: 6.9643
Valero Meraux | 3 | 8.75 | 0.1902% | 2025-01-22 | 2025-01-29 | Crude cut due to freeze | Assumed a 30% cut due to elevated flaring | [6 empty] | -1.9758 | [7 empty] | OK | 2025-01-24: -3.75; 2025-02-07: 3.75
Shell Norco | 3 | 17.5 | 0.3804% | 2025-01-22 | 2025-01-29 | Crude cut due to freeze | Assumed a 30% cut due to elevated flaring | [6 empty] | -3.9516 | [7 empty] | OK | 2025-01-24: -7.5; 2025-02-07: 7.5
P66 Bayway | 1 | 20.9 | 4.354% | 2025-01-02 | 2025-01-31 | Alky (22) | Planned T/A 1/2-1/31 | [6 empty] | -19.5516 | [7 empty] | OK | 2025-01-03: -5.9714; 2025-01-10: -14.9286; 2025-02-07: 20.9
Delek Big Spring | 3 | 36.725 | 0.7984% | 2025-01-27 | 2025-01-31 | FCC (25), CR (21.5), CDU cut (22) | SD unplanned, assume 1 wk outage | [6 empty] | -4.7387 | [7 empty] | OK | 2025-01-31: -20.9857; 2025-02-07: 20.9857
Valero Port Arthur | 3 | 26.5 | 0.5761% | 2024-09-01 | 2025-02-01 | CDU and Coker running at reduced rates | Running at reduced rates until repairs can be made; removing 1/8 due to high December crude runs | [6 empty] | -26.5 | 0 | [6 empty] | OK | 2024-09-06: -18.9286; 2024-09-13: -7.5714
Valero Port Arthur | 3 | 0 | 0% | 2024-09-01 | 2025-02-01 | [9 empty] | 0 | [6 empty] | Missing
Citgo Corpus Christi | 3 | 11.25 | 0.2446% | 2025-01-20 | 2025-02-01 | Coker(45) | SD unplanned due to freeze,assuming 1wk; extended to 1/29 from 1.21 | [6 empty] | -3.9919 | 0 | [6 empty] | OK | 2025-01-24: -1.6071; 2025-01-31: -9.6429; 2025-02-07: 9.6429; 2025-02-14: 1.6071
Total Port Arthur | 3 | 41.25 | 0.8967% | 2025-01-23 | 2025-02-01 | CDU (165) | SD after freeze issues, extended to 2/1 | [6 empty] | -10.6452 | 0 | [6 empty] | OK | 2025-01-24: -23.5714; 2025-01-31: -17.6786; 2025-02-14: 41.25
Marathon Texas City | 3 | 16.75 | 0.3641% | 2025-01-31 | 2025-02-01 | CDU (67) | Up after unplanned SD | [6 empty] | 0 | 0 | [6 empty] | OK | 2025-02-07: -2.3929; 2025-02-14: 2.3929
Chevron Richmond | 5 | 52 | 3.852% | 2025-01-13 | 2025-02-06 | FCC(80) | Ended T/A early on 2/6 vs. 2/26 | [6 empty] | -30.1935 | -0.89286 | [6 empty] | OK | 2025-01-17: -29.7143; 2025-01-24: -22.2857; 2025-02-14: 29.7143; 2025-02-21: 22.2857; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Citgo Lemont | 2 | 3.135 | 0.1306% | 2025-01-24 | 2025-02-06 | Coker derate 33% | [7 empty] | -0.7079 | -0.35714 | [6 empty] | OK | 2025-01-24: -0.44786; 2025-01-31: -2.6871; 2025-02-07: 3.135
Chevron Richmond | 5 | 5.2 | 0.3852% | 2025-02-02 | 2025-02-06 | HDC(44), HDC (60) | SU after unplanned SD | [7 empty] | -0.74286 | [6 empty] | OK | 2025-02-07: -2.9714; 2025-02-14: 2.9714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Cenovus Lima | 2 | 34 | 1.417% | 2025-02-03 | 2025-02-06 | Reformer (40) | SU after unplanned SD | [7 empty] | -3.6429 | [6 empty] | OK | 2025-02-07: -14.5714; 2025-02-14: 14.5714
Valero Corpus Christi East | 3 | 8.5 | 0.1848% | 2024-07-20 | 2025-02-07 | Ref | Assuming permanently down as it has been down for 7 months | [7 empty] | -0.64286 | [6 empty] | OK | 2024-07-26: -5.6667; 2024-08-02: -2.8333
Valero Wilmington | 5 | 5.5 | 0.4074% | 2025-01-10 | 2025-02-07 | CDU (44), Coker (15) | Ended T/A early | [6 empty] | -3.7258 | -1.0714 | [6 empty] | OK | 2025-01-17: -5.5; 2025-02-14: 5.5; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Texas City | 3 | 16.75 | 0.3641% | 2025-01-31 | 2025-02-07 | CDU (67) | SD unplanned, assuming 1 wk | [6 empty] | 0 | -0.64286 | [6 empty] | OK | 2025-01-31: -2.3929; 2025-02-07: -14.3571; 2025-02-14: 2.3929; 2025-02-21: 14.3571
P66 Borger | 3 | 19.5 | 0.4239% | 2025-02-03 | 2025-02-07 | FCC(30) | Su after unplanned SD | [7 empty] | -2.7857 | [6 empty] | OK | 2025-02-07: -11.1429; 2025-02-14: 11.1429
Woods Cross Refinery (HF Sinclair) | 4 | 0.75 | 0.2206% | 2025-02-05 | 2025-02-07 | HDC (15) | Added 2/7 per IIR | [7 empty] | -0.053571 | [6 empty] | OK | 2025-02-07: -0.21429; 2025-02-14: 0.21429
PBF Toledo | 2 | 12.75 | 0.5312% | 2025-01-10 | 2025-02-08 | Reformer | 15 kbd Ref down 1/10-2/8 | [6 empty] | -8.6371 | -0.5 | [6 empty] | OK | 2025-01-17: -10.2; 2025-01-24: -2.55; 2025-02-14: 10.2; 2025-02-21: 2.55
Marathon Galveston Bay | 3 | 3.2 | 0.06957% | 2025-01-16 | 2025-02-09 | Hydrocracker (60 kbd) | SU after unplanned SD | [6 empty] | -1.5484 | -0.85714 | [6 empty] | OK | 2025-01-17: -0.45714; 2025-01-24: -2.7429; 2025-03-14: 3.2
P66 Borger | 3 | 5.95 | 0.1293% | 2025-01-16 | 2025-02-10 | Ref | SD unplanned; still down on 2/7 pushed out S/U 1 wk; UP on evening of 2/10 per Genscape updated ramp | updated 2/11 | [5 empty] | -2.879 | -0.96429 | [6 empty] | OK | 2025-01-17: -0.99167; 2025-01-24: -5.1; 2025-02-14: 3.4; 2025-02-21: 2.55
Marathon Wilmington | 5 | 11.05 | 0.8185% | 2025-01-25 | 2025-02-10 | Ref (13) | Su after unplanned SD | [6 empty] | -2.1387 | -1.6071 | [6 empty] | OK | 2025-01-31: -9.4714; 2025-02-07: -1.5786; 2025-02-14: 6.3143; 2025-02-21: 4.7357; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Wood River | 2 | 27.5 | 1.146% | 2025-02-07 | 2025-02-11 | CDU (110) | SU after unplanned SD | [7 empty] | -3.9286 | [6 empty] | OK | 2025-02-07: -3.9286; 2025-02-21: 3.9286
Marathon Wilmington | 5 | 1.6 | 0.1185% | 2025-02-06 | 2025-02-12 | HDC (32) | SD unplanned, assuming 1 wk | [7 empty] | -0.34286 | [6 empty] | OK | 2025-02-07: -0.22857; 2025-02-14: -0.91429; 2025-02-21: 1.1429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Catlettsburg | 2 | 26 | 1.083% | 2025-02-09 | 2025-02-12 | CDU (104) | Up after unplanned SD | [7 empty] | -2.7857 | [6 empty] | OK | 2025-02-14: -14.8571; 2025-02-21: 14.8571
Marathon Robinson | 2 | 3 | 0.125% | 2025-02-11 | 2025-02-12 | Coker (12) | Up after unplanned sd | added 2/11 | [6 empty] | -0.10714 | [6 empty] | OK | 2025-02-14: -0.42857; 2025-02-21: 0.42857
Chevron Richmond | 5 | 3 | 0.2222% | 2025-02-08 | 2025-02-14 | HDC (60) | SD unplanned, assuming 1 wk | [7 empty] | -0.64286 | [6 empty] | OK | 2025-02-14: -2.5714; 2025-02-21: 2.5714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Garyville | 3 | 34.375 | 0.7473% | 2025-01-27 | 2025-02-16 | CDU (275) | Planned TA, 50% derate per IIR | [6 empty] | -4.4355 | -1.6071 | [6 empty] | OK | 2025-01-31: -19.6429; 2025-02-07: -14.7321; 2025-02-21: 34.375
Chevron Richmond | 5 | 52 | 3.852% | 2025-02-14 | 2025-02-16 | FCC(80) | Unplanned S/D post T/A | [7 empty] | -3.7143 | [6 empty] | OK | 2025-02-14: -2; 2025-02-21: 2; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Baytown | 3 | 6.3 | 0.137% | 2025-01-03 | 2025-02-17 | Flexicoker (42) | Planned T/A - 1/3- 2/15 | [6 empty] | -5.6903 | -1.7143 | [6 empty] | OK | 2025-01-10: -5.04; 2025-01-17: -1.26; 2025-02-21: 3.15; 2025-02-28: 3.15
Valero Wilmington | 5 | 7 | 0.5185% | 2025-01-10 | 2025-02-17 | CDU (40); Coker (15) | Pulled up T/A end to 2/19 from (1/10-3/1). cdu (40), fcc (54); CDU/Coker SU on 2/7 (captured in other line) | added reformer and coker to outage per Genscape | [5 empty] | -4.7419 | -2.8571 | [6 empty] | OK | 2025-01-10: -1; 2025-01-17: -6; 2025-02-21: 5; 2025-02-28: 2; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero Wilmington | 5 | 15.3 | 1.133% | 2025-01-10 | 2025-02-18 | Ref (18) | Split out Reformer | [6 empty] | -10.3645 | -3.0357 | [6 empty] | OK | 2025-01-17: -13.1143; 2025-02-21: 6.5571; 2025-02-28: 8.7429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Joliet | 2 | 69.85 | 2.91% | 2025-02-07 | 2025-02-18 | CDU cut (120), FCC cut (38), Coker cut (30), Ref (9) | Reformer pre-treater issue | [7 empty] | -27.4411 | [6 empty] | OK | 2025-02-07: -9.9786; 2025-02-14: -59.8714; 2025-02-21: 69.85
Delek Big Spring | 3 | 28.7 | 0.6239% | 2025-02-07 | 2025-02-18 | CR (21.5), assuming min rates for CDU/FCC | Up after unplanned SD | [7 empty] | -11.275 | [6 empty] | OK | 2025-02-07: -4.1; 2025-02-14: -24.6; 2025-02-21: 28.7
GCC Galveston Bunkers | 3 | 12.5 | 0.2717% | 2025-02-17 | 2025-02-18 | CDU | Up after unplanned SD | [7 empty] | -0.44643 | [6 empty] | OK | 2025-02-21: -1.7857; 2025-02-28: 1.7857
Suncor Commerce City | 4 | 9.75 | 2.868% | 2025-02-17 | 2025-02-19 | CDU (39) | Up after unplanned SD; 2/19 revised SU date to 2/19 | [7 empty] | -0.69643 | [6 empty] | OK | 2025-02-21: -2.7857; 2025-02-28: 2.7857
FH Corpus West | 3 | 113.75 | 2.473% | 2025-01-13 | 2025-02-21 | CDU (255), FCC (55), HDC (30), Coker (17), Ref (58) | Planned T/A 1/13-2/11 (whole TA delayed by 3 days), extended SU due to FH rack pricing being elevated on 2/19 | Monitor; IIR expects TA to end on time | [5 empty] | -66.0484 | -2.1429 | [6 empty] | OK | 2025-01-17: -65; 2025-01-24: -48.75; 2025-02-28: 48.75; 2025-03-07: 65
Valero McKee | 3 | 39.9 | 0.8674% | 2025-02-06 | 2025-02-21 | Ref (29), HDC (30), CDU (40), FCC (15) | Up per ENT | [7 empty] | -21.375 | [6 empty] | OK | 2023-11-03: -14.1143; 2023-11-10: 14.1143; 2023-11-17: 35.2857; 2025-02-07: -11.4; 2025-02-14: -28.5; 2025-02-28: 11.4; 2025-03-07: 28.5
XOM Baytown | 3 | 1.35 | 0.02935% | 2025-02-17 | 2025-02-21 | HDC (27) | Up per DV | [7 empty] | -0.19286 | [6 empty] | OK | 2025-02-21: -0.77143; 2025-02-28: 0.77143
Valero Three Rivers | 3 | 19.55 | 0.425% | 2025-02-20 | 2025-02-21 | Ref (23) | Up after unplanned SD | [7 empty] | -0.69821 | [6 empty] | OK | 2025-02-21: -2.7929; 2025-02-28: 2.7929
Marathon Carson | 5 | 17 | 1.259% | 2025-02-20 | 2025-02-22 | Ref (20) | up after unplaned SD | [7 empty] | -1.2143 | [6 empty] | OK | 2025-02-21: -2.4286; 2025-02-28: 2.4286; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
HF Artesia | 3 | 24.12 | 0.5243% | 2025-02-20 | 2025-02-22 | Ref (24) | Up after unplanned Sd | [7 empty] | -1.7229 | [6 empty] | OK | 2025-02-21: -6.8914; 2025-02-28: 6.8914
Monroe Trainer | 1 | 1.2 | 0.25% | 2025-01-18 | 2025-02-23 | HDC (24); Iso Cracker (24) | Up per IIR | [6 empty] | -0.50323 | -0.78571 | [6 empty] | OK | 2025-01-24: -0.85714; 2025-01-31: -0.34286; 2025-02-28: 0.34286; 2025-03-07: 0.85714
Delek Big Spring | 3 | 0 | 0% | 2025-02-03 | 2025-02-23 | CDU (73), Ref (21) | ENT only source (planned maintenance)- removed as still looks hot in Genscape | [7 empty] | 0 | [6 empty] | OK | 2025-02-07: 0; 2025-02-14: 0; 2025-02-28: 0; 2025-03-07: 0
Monroe Trainer | 1 | 24.115 | 5.024% | 2025-02-21 | 2025-02-23 | FCC (53) | Up after unplanned SD | [7 empty] | -1.7225 | [6 empty] | OK | 2025-02-21: -3.445; 2025-02-28: 3.445
P66 Sweeny | 3 | 77.39 | 1.682% | 2025-01-10 | 2025-02-24 | CDU (185), Coker (84), 20% FCC cut (15 kbd) | Planned T/A 1/17-2/29(pushed back from 1/10-2/22); pulled back up to 1/10 per IIR | [6 empty] | -52.4255 | -2.4643 | [6 empty] | OK | 2025-01-17: -61.912; 2025-01-24: -15.478; 2025-02-28: 15.478; 2025-03-07: 61.912
FH Corpus East | 3 | 18.75 | 0.4076% | 2025-02-23 | 2025-02-24 | CDU (75) | Up after unplanned SD | [7 empty] | -0.66964 | [6 empty] | OK | 2025-02-28: -2.6786; 2025-03-07: 2.6786
XOM Baton Rouge | 3 | 47.5 | 1.033% | 2025-02-04 | 2025-02-25 | PS8 (190) | Up post T/A | [7 empty] | -35.625 | [6 empty] | OK | 2025-02-07: -47.5; 2025-03-07: 6.7857; 2025-03-14: 40.7143
HF Artesia | 3 | 21.27 | 0.4624% | 2025-02-20 | 2025-02-26 | FCC (27), Crude Cut (36) | up 2/26 per genscape | [7 empty] | -4.5579 | [6 empty] | OK | 2025-02-21: -6.0771; 2025-02-28: -12.1543; 2025-03-07: 12.1543; 2025-03-14: 6.0771
PBF Chalmette | 3 | 16.15 | 0.3511% | 2025-02-24 | 2025-02-26 | CR (19) | Updated timing per IIR | [7 empty] | -1.1536 | [6 empty] | OK | 2025-02-28: -4.6143; 2025-03-07: 4.6143
Shell Norco | 3 | 5.25 | 0.1141% | 2025-01-24 | 2025-02-27 | Coker (21) | Assuming they pulled forward coker T/A | [6 empty] | -1.1855 | -2.7857 | [6 empty] | OK | 2025-01-31: -5.25; 2025-02-28: 5.25
Marathon Garyville | 3 | 34.375 | 0.7473% | 2025-02-25 | 2025-02-27 | CDU (275) | Unplanned S/D 2/25 | added 2/28 | [6 empty] | -2.4554 | [6 empty] | OK | 2025-02-28: -9.8214; 2025-03-07: 9.8214
Monroe Trainer | 1 | 41.4 | 8.625% | 2025-01-23 | 2025-02-28 | Alky(12)- inclusive of FCC cut; Added Isom unit impact | no new assuming up | FCC Up on 2/23 reducting alky/isom duration on 2/28 "increased" HC activity on 2/28 Gescape still showing down | [5 empty] | -10.6839 | -0.96429 | [6 empty] | OK | 2025-01-31: -5.9143; 2025-02-07: -35.4857; 2025-02-28: 35.4857; 2025-03-07: 5.9143
XOM Baton Rouge | 3 | 97.5 | 2.12% | 2025-02-27 | 2025-02-28 | FCC(110), CDU cut (50) | Major intial cut | [7 empty] | -3.4821 | [6 empty] | OK | 2025-02-28: -13.9286; 2025-03-07: 13.9286
San Joaquin Bakersfield | 5 | 6.25 | 0.463% | 2025-02-20 | 2025-03-01 | CDU(24) | Updated timing per IIR; pushed back to 3/10 IIR; up 3/11 per IIR | [7 empty] | -1.7857 | 0 | [5 empty] | OK | 2025-02-21: -0.89286; 2025-02-28: -5.3571; 2025-03-07: 6.25; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
HF Sinclair - Tulsa West | 2 | 22.8 | 0.95% | 2025-02-28 | 2025-03-01 | CDU 91.2 | [8 empty] | 0 | 0 | [5 empty] | OK | 2025-03-07: -3.2571; 2025-03-14: 3.2571
Marathon Robinson | 2 | 3 | 0.125% | 2025-03-01 | 2025-03-02 | Coker (12) | unplanned 1day outage | added 3/3 | [7 empty] | -0.096774 | [5 empty] | OK | 2025-03-07: -0.42857; 2025-03-14: 0.42857
Marathon Galveston Bay | 3 | 93.55 | 2.034% | 2025-01-20 | 2025-03-03 | CDU (265),FCC (140) | SU pulled forward from 3/20 to 3/3 | IIR reporting 2/19 ENT 2/9 | [5 empty] | -33.1952 | -93.55 | -6.0355 | [5 empty] | OK | 2025-01-24: -53.4571; 2025-01-31: -40.0929; 2025-03-07: 53.4571; 2025-03-14: 40.0929
Marathon Carson | 5 | 17 | 1.259% | 2025-02-26 | 2025-03-03 | Ref (20) | Up after unplanned SD | [7 empty] | -1.2143 | -1.0968 | [5 empty] | OK | 2025-02-28: -4.8571; 2025-03-14: 4.8571; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
El Segundo | 5 | 2.25 | 0.1667% | 2025-02-28 | 2025-03-03 | HDC (45) | Down unplanned on 2/28 - assuming 1 wk downtime. (Per IIR & Genscape); up on 3/2; full capacity 3/5 | added 2/28 | [6 empty] | 0 | -0.14516 | [5 empty] | OK | 2025-03-07: -0.64286; 2025-03-14: 0.64286; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
El Segundo | 5 | 2.25 | 0.1667% | 2025-02-27 | 2025-03-05 | HDC (45) | Up after unplanned SD | [7 empty] | -0.080357 | -0.29032 | [5 empty] | OK | 2025-02-28: -0.32143; 2025-03-14: 0.32143; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Wilmington | 5 | 11.875 | 0.8796% | 2025-01-25 | 2025-03-06 | Alky (12.5) | Alky (12.5) - Mid-Jan-early Mar | [6 empty] | -2.2984 | -11.875 | -1.9153 | [5 empty] | OK | 2025-01-31: -10.1786; 2025-02-07: -1.6964; 2025-03-07: 1.6964; 2025-03-14: 10.1786; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Chevron Pasadena | 3 | 29 | 0.6304% | 2025-02-24 | 2025-03-06 | CDU (116) | Up after unplanned SD | [7 empty] | -4.1429 | -4.6774 | [5 empty] | OK | 2025-02-28: -16.5714; 2025-03-14: 16.5714
Woods Cross Refinery (HF Sinclair) | 4 | 0.75 | 0.2206% | 2025-03-03 | 2025-03-06 | HDC (15) | Up after unplanned SD | [8 empty] | -0.072581 | [5 empty] | OK | 2025-03-07: -0.32143; 2025-03-14: 0.32143
Valero Wilmington | 5 | 35.1 | 2.6% | 2025-01-10 | 2025-03-07 | FCC (54) | Up on 3/7 per genscape | [6 empty] | -23.7774 | -35.1 | -6.7935 | [5 empty] | OK | 2025-01-17: -35.1; 2025-03-07: 5.0143; 2025-03-14: 30.0857; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Baytown | 3 | 22 | 0.4783% | 2025-01-13 | 2025-03-07 | PS7 (88) | Delayed due to overhead exchanger issues | [6 empty] | -12.7742 | -22 | -4.2581 | [5 empty] | OK | 2025-01-17: -22; 2025-03-07: 3.1429; 2025-03-14: 18.8571
Calcasieu - Lake Charles | 3 | 16 | 0.3478% | 2025-03-05 | 2025-03-07 | CDU (73kbd) | restarted 3/7 | [8 empty] | -1.0323 | [5 empty] | OK | 2025-03-07: -4.5714; 2025-03-14: 4.5714
Puget Sound | 5 | 6.325 | 0.4685% | 2025-02-21 | 2025-03-08 | Coker(25.3) | Up after unplanned SD | [7 empty] | -1.5813 | -1.4282 | [5 empty] | OK | 2025-02-21: -0.90357; 2025-02-28: -5.4214; 2025-03-14: 6.325
PBF Toledo | 2 | 23.5 | 0.9792% | 2025-03-05 | 2025-03-08 | CDU (94) | Up after unplanned SD | [8 empty] | -2.2742 | [5 empty] | OK | 2025-03-07: -6.7143; 2025-03-14: 6.7143
Calcasieu - Lake Charles | 3 | 18.25 | 0.3967% | 2025-02-27 | 2025-03-09 | CDU (73kbd) | Up after unplanned SD | [7 empty] | -0.65179 | -4.7097 | [5 empty] | OK | 2025-02-28: -2.6071; 2025-03-07: -15.6429; 2025-03-14: 18.25
XOM Beaumont | 3 | 19.5 | 0.4239% | 2025-03-07 | 2025-03-10 | FCC cut (30) | [9 empty] | -1.8871 | [5 empty] | OK | 2025-03-14: -8.3571; 2025-03-21: 8.3571
Marathon Salt Lake City | 4 | 16 | 4.706% | 2025-03-10 | 2025-03-12 | CDU(64) | Up after unplanned SD | assuming 1 wk | [7 empty] | -1.0323 | [5 empty] | OK | 2025-03-14: -4.5714; 2025-03-21: 4.5714
P66 Lake Charles | 3 | 30.03 | 0.6528% | 2025-02-18 | 2025-03-13 | FCC (46.2) | Up 3/13 | [7 empty] | -10.725 | -11.6245 | [5 empty] | OK | 2023-11-10: -17.16; 2023-11-24: 17.16; 2025-02-21: -12.87; 2025-02-28: -17.16; 2025-03-14: 15.015; 2025-03-21: 15.015
P66 Wood River | 2 | 15.725 | 0.6552% | 2025-03-01 | 2025-03-13 | Ref (18.5) | Up after unplanned SD | [8 empty] | -6.0871 | [5 empty] | OK | 2025-03-07: -15.725; 2025-03-14: 15.725
Valero St Charles | 3 | 78.5 | 1.707% | 2025-01-24 | 2025-03-14 | FCC(115), HDC (75) | Completed 3/14 | iir revised end date 3/14 | [5 empty] | -17.7258 | -78.5 | -32.9194 | [5 empty] | OK | 2025-01-24: -44.8571; 2025-01-31: -33.6429; 2025-03-14: 33.6429; 2025-03-21: 44.8571
Delek Big Spring | 3 | 16.25 | 0.3533% | 2025-03-12 | 2025-03-14 | FCC(25) | Unplanned SD up on 3/14 | [8 empty] | -1.0484 | [5 empty] | OK | 2025-03-14: -9.2857; 2025-03-21: 9.2857
Marathon El Paso | 3 | 15.3 | 0.3326% | 2025-03-14 | 2025-03-17 | Ref (18) | Up after unplanned SD | [8 empty] | -1.4806 | [6 empty] | 2025-03-14: -2.1857; 2025-03-21: -4.3714; 2025-03-28: 4.3714; 2025-04-04: 2.1857
Suncor Commerce City | 4 | 9.75 | 2.868% | 2025-03-09 | 2025-03-18 | CDU (39) | [9 empty] | -2.8306 | [5 empty] | OK | 2025-03-14: -6.9643; 2025-03-28: 6.9643
Valero Three Rivers | 3 | 27.45 | 0.5967% | 2025-01-22 | 2025-03-19 | FCC (24), HDC (30), Ref(11), Crude Cut (10) | Planned T/A; CDU no longer in scope | increased FCC activity 3/17 delaying SU to 3/19; softned ramp | [5 empty] | -7.9694 | -27.45 | -15.9387 | [5 empty] | OK | 2025-01-24: -7.8429; 2025-01-31: -19.6071; 2025-03-21: 27.45
Valero McKee | 3 | 26.15 | 0.5685% | 2025-03-16 | 2025-03-19 | Ref (29), HDC (30) | Up after unplanned SD | [8 empty] | -2.5306 | [5 empty] | OK | 2025-03-21: -11.2071; 2025-03-28: 11.2071
P66 Borger | 3 | 41.12 | 0.8939% | 2025-03-01 | 2025-03-20 | Ref (20) | Splitting out reformer from T/A since it started up early | [8 empty] | -25.2026 | [6 empty] | 2025-03-07: -32.896; 2025-03-14: -8.224; 2025-03-21: 8.224; 2025-03-28: 32.896
P66 Borger | 3 | 24.12 | 0.5243% | 2025-03-01 | 2025-03-20 | FCC(30), Crude cut (46) | IIR updated timing 3/1-3/30 and added Ref (PrevTA 3/7-4/11) | Increased reformer activity 3/18; extended FCC still down | [7 empty] | -14.7832 | [5 empty] | OK | 2025-03-07: -19.296; 2025-03-14: -4.824; 2025-03-21: 24.12
GCC Galveston Bunkers | 3 | 12.5 | 0.2717% | 2025-03-20 | 2025-03-23 | CDU | Up 3/23 after unplanned SD | [8 empty] | -1.2097 | [5 empty] | OK | 2025-03-21: -1.7857; 2025-03-28: -3.5714; 2025-04-04: 3.5714; 2025-04-11: 1.7857
P66 Ponca City | 2 | 47 | 1.958% | 2025-03-08 | 2025-03-24 | FCC (45); Assuming 30% crude cut due to VGO logistics and 10% Coker cut | Updated timing per ENT | up after 16 days vs 28 | [7 empty] | -24.2581 | [5 empty] | OK | 2025-03-14: -40.2857; 2025-03-21: -6.7143; 2025-04-04: 20.1429; 2025-04-11: 26.8571
Placid Port Allen | 3 | 9.35 | 0.2033% | 2025-03-08 | 2025-03-24 | REF(11) | [9 empty] | -4.8258 | [5 empty] | OK | 2025-03-14: -9.35; 2025-03-28: 4.0071; 2025-04-04: 5.3429
XOM Joliet | 2 | 44.45 | 1.852% | 2025-03-17 | 2025-03-24 | CDU cut (70), Coker (35), FCC (28) | [9 empty] | -10.0371 | [5 empty] | OK | 2025-03-21: -25.4; 2025-04-04: 25.4
Marathon Robinson | 2 | 36.35 | 1.515% | 2025-03-17 | 2025-03-24 | CDU derate (64), FCC derate(15) | Derate with other units pre-CDU outage | Added CDU outage | [7 empty] | -8.2081 | [5 empty] | OK | 2025-03-21: -20.7714; 2025-04-04: 20.7714
P66 LA/Wilmington | 5 | 32.5 | 2.407% | 2025-03-21 | 2025-03-25 | FCC(50) | Uplanned shutdown on 3/21-3/24 | [8 empty] | -4.1935 | [5 empty] | OK | 2025-03-21: -4.6429; 2025-03-28: -9.2857; 2025-04-04: 9.2857; 2025-04-11: 4.6429; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Valero Corpus Christi East | 3 | 31.75 | 0.6902% | 2025-03-03 | 2025-03-26 | CDU (110), Coker (17) | Unplanned outaged due to fire | [8 empty] | -23.5565 | [5 empty] | OK | 2025-03-07: -22.6786; 2025-03-14: -9.0714; 2025-03-28: 9.0714; 2025-04-04: 22.6786
Total Port Arthur | 3 | 20 | 0.4348% | 2025-03-22 | 2025-03-26 | CDU(80) | Unplanned CDU VDU outage; assuming 1 wk | added 3/25 per GS | [7 empty] | -2.5806 | [5 empty] | OK | 2025-03-28: -11.4286; 2025-04-04: 11.4286
Marathon Robinson | 2 | 35.75 | 1.49% | 2025-03-24 | 2025-03-26 | FCC (55) | SD for 2 days, not in T/A scope | [8 empty] | -2.3065 | [5 empty] | OK | 2025-03-28: -10.2143; 2025-04-04: 10.2143
Valero Three Rivers | 3 | 9.35 | 0.2033% | 2025-03-24 | 2025-03-26 | Ref (11) | Unplanned SD 3/24-3/26 | [8 empty] | -0.60323 | [5 empty] | OK | 2025-03-28: -2.6714; 2025-04-04: 2.6714
Delek Big Spring | 3 | 4.0625 | 0.08832% | 2025-03-21 | 2025-03-27 | FCC(25) 25% cut | Reduced rates for 6 days; per emmisions filing via IPIS | [8 empty] | -0.78629 | [5 empty] | OK | 2025-03-21: -0.58036; 2025-03-28: -2.9018; 2025-04-04: 4.0625
Cenovus Toledo | 2 | 1.875 | 0.07812% | 2025-03-12 | 2025-03-28 | Coker (10) | SD unplanned, assuming will stay down into T/A | [8 empty] | -0.96774 | [5 empty] | OK | 2025-03-14: -0.53571; 2025-03-21: -1.3393; 2025-04-04: 1.3393; 2025-04-11: 0.53571
PBF Torrance | 5 | 16.6 | 1.23% | 2025-03-13 | 2025-03-28 | CDU (166) | CDU restarted 3/28 per Genscape | [8 empty] | -8.0323 | [5 empty] | OK | 2025-03-14: -2.3714; 2025-03-21: -14.2286; 2025-04-04: 16.6; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Baytown | 3 | 5 | 0.1087% | 2025-03-03 | 2025-03-29 | Crude cut per crude team (20) | [9 empty] | -4.1935 | [5 empty] | OK | 2025-03-07: -2.8571; 2025-03-14: -2.1429; 2025-04-04: 5
Shell Norco | 3 | 2.2 | 0.04783% | 2025-02-24 | 2025-03-31 | HDC (44) | up on 3/31 | genscape showin increased activity 3/16 | [6 empty] | -0.31429 | -2.129 | [5 empty] | OK | 2025-02-28: -1.2571; 2025-03-07: -0.94286; 2025-04-04: 1.2571; 2025-04-11: 0.94286
Petromax Houston Fractionation Refinery | 3 | 6.25 | 0.1359% | 2025-02-28 | 2025-03-31 | CDU (25) | IIR updated timing to 2/28-3/31 | Confirmed timing on 3/11 | [6 empty] | 0 | -6.0484 | [5 empty] | OK | 2025-02-28: -0.89286; 2025-03-07: -5.3571; 2025-04-04: 3.5714; 2025-04-11: 2.6786
Marathon Robinson | 2 | 25.5 | 1.062% | 2025-03-24 | 2025-03-31 | CDU (266) | Up 3/31 per Genscape;IIR confirmed | Extended outage to 4/26 per IIR | [7 empty] | -5.7581 | [5 empty] | OK | 2025-03-28: -14.5714; 2025-04-11: 14.5714
Marathon Catlettsburg | 2 | 20 | 0.8333% | 2025-03-22 | 2025-04-01 | Ref(20), CDU cut (30) | Adding crude cut based on hydrogen constraints and reduced Pipeline flows | [8 empty] | -5.8065 | 0 |  |  |  |  | OK | 2025-03-28: -20; 2025-04-11: 20
XOM Baton Rouge | 3 | 71.5 | 1.554% | 2025-03-28 | 2025-04-02 | FCC(110) | Sustained cuts; PCLA2 up to 75kbd 4/2 | [8 empty] | -6.9194 | -2.3833 |  |  |  |  | OK | 2025-03-28: -10.2143; 2025-04-11: 10.2143
Citgo Corpus Christi | 3 | 11.25 | 0.2446% | 2025-04-01 | 2025-04-02 | Coker (45) | Unplanned SD 4/1; assuming 1wk | [9 empty] | -0.375 |  |  |  |  | OK | 2025-04-04: -3.2143; 2025-04-11: 3.2143
Total Port Arthur | 3 | 41.25 | 0.8967% | 2025-04-01 | 2025-04-02 | CDU(80) | [10 empty] | -1.375 | [5 empty] | 2025-04-04: -5.8929; 2025-04-11: 5.8929
Lazarus Nixon | 3 | 3.75 | 0.08152% | 2025-04-01 | 2025-04-02 | CDU(15) | Unplanned outage 4/1; Topping site | [9 empty] | -0.125 |  |  |  |  | OK | 2025-04-04: -0.53571; 2025-04-11: 0.53571
Total Port Arthur | 3 | 20 | 0.4348% | 2025-04-01 | 2025-04-03 | CDU(80) | Unplanned CDU VDU outage | Added 4/2 per GS | [8 empty] | -1.3333 |  |  |  |  | OK | 2025-04-04: -8.5714; 2025-04-11: 8.5714
XOM Joliet | 2 | 41.85 | 1.744% | 2025-03-24 | 2025-04-04 | CDU cut (70), Coker (35), FCC (24) | [9 empty] | -9.45 | -4.185 |  |  |  |  | OK | 2025-03-28: -23.9143; 2025-04-04: -17.9357; 2025-04-11: 41.85
XOM Baytown | 3 | 7.5 | 0.163% | 2025-03-29 | 2025-04-04 | CDU cut (40) | [9 empty] | -0.48387 | -0.75 | [5 empty] | 2025-04-04: -6.4286; 2025-04-11: 6.4286
PBF Torrance | 5 | 15.85 | 1.174% | 2025-03-13 | 2025-04-05 | HDC (28), Ref (17) | HDC Split out; su 4/5 | [8 empty] | -9.2032 | -2.1133 |  |  |  |  | OK | 2025-03-14: -2.2643; 2025-03-21: -13.5857; 2025-04-11: 15.85; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon Detroit | 2 | 14.35 | 0.5979% | 2025-03-31 | 2025-04-05 | Coker(28), Crude cut (30) | Up after unplanned SD | [8 empty] | 0 | -1.9133 |  |  |  |  | OK | 2025-04-04: -8.2; 2025-04-11: 8.2
United Warren | 1 | 4.0625 | 0.8464% | 2025-04-03 | 2025-04-05 | FCC(25) | Assuming derate due to decreased activity/crane next to FCC | up 4/5 per GS | [8 empty] | -0.27083 |  |  |  |  | OK | 2025-04-04: -1.1607; 2025-04-11: 1.1607
BP Cherry Point | 5 | 23.85 | 1.767% | 2025-03-23 | 2025-04-07 | CDU derate (75), Ref (6) | Full CDU SD on 4/7 | still up on 3/10 in genscape; delaying to 3/27 on 3/24 | [7 empty] | -6.1548 | -4.77 |  |  |  |  | OK | 2025-03-28: -17.0357; 2025-04-04: -6.8143; 2025-04-11: 10.2214; 2025-04-18: 13.6286; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Joliet | 2 | 29.35 | 1.223% | 2025-04-04 | 2025-04-07 | CDU cut (20), Coker (35), FCC (24) | [10 empty] | -2.935 |  |  |  |  | OK | 2025-04-11: -12.5786; 2025-04-18: 12.5786
P66 Bayway | 1 | 101.14 | 21.07% | 2025-02-14 | 2025-04-08 | CDU (272), FCC derate (40 kbd) | T/A scope now covers both CDUs | Powerformer 2 (26), DSU 1 (54), DSU 2 (29), VDU (75), CDU 7 (130) ; | [6 empty] | -50.57 | -101.14 | -23.5993 |  |  |  |  | OK | 2025-02-14: -14.4486; 2025-02-21: -86.6914; 2025-04-11: 57.7943; 2025-04-18: 43.3457
Chevron Salt Lake | 4 | 0.845 | 0.2485% | 2025-04-03 | 2025-04-08 | FCC(13) % derate | [10 empty] | -0.14083 |  |  |  |  | OK | 2025-04-04: -0.24143; 2025-04-11: -0.48286; 2025-04-18: 0.845
Flint Hills Pine Bend | 2 | 4.125 | 0.3% | 2025-03-31 | 2025-04-09 | DC (16.5) | Planned T/A 3/28-4/9; | https://energyrt.woodmac.com/oil/alerts/images/37c18c5b-d6fe-4dbf-b487-c00bb97e9e03 | [7 empty] | 0 | -1.1 |  |  |  |  | OK | 2025-04-04: -4.125; 2025-04-11: 2.9464; 2025-04-18: 1.1786
Flint Hills Pine Bend | 2 | 45.15 | 1.881% | 2025-04-06 | 2025-04-09 | CDU (190), Reformer derate (14) | Only down for 2 days, assuming derate for remainder of T/A | [9 empty] | -4.515 |  |  |  |  | OK | 2025-04-11: -12.9; 2025-04-18: 12.9
HF Sinclair El Dorado | 2 | 1.2812 | 0.05339% | 2025-04-07 | 2025-04-09 | Coker (20.5) | short unplanned derate 25% cut | [9 empty] | -0.085417 |  |  |  |  | OK | 2025-04-11: -0.32031; 2025-04-18: 0.32031
PBF Paulsboro | 1 | 14 | 2.917% | 2024-10-23 | 2025-04-10 | CDU (56 kbd) | Argus reporting SU mid APR '25 | Starting Ramp earlier than initial assumption of 4/15; increased activity 4/10 | [5 empty] | -14 | -14 | -14 | -4.2 |  |  |  |  | OK | 2024-10-25: -9; 2024-11-01: -5; 2025-04-11: 4; 2025-04-18: 10
XOM Baton Rouge | 3 | 20 | 0.4348% | 2025-04-01 | 2025-04-10 | PS7 (80) | [10 empty] | -6 |  |  |  |  | OK | 2025-04-04: -8.5714; 2025-04-11: -11.4286; 2025-04-18: 11.4286; 2025-04-25: 8.5714
XOM Baton Rouge | 3 | 53.95 | 1.173% | 2025-04-02 | 2025-04-10 | FCC(80) derate | total FCC 140 vs 223 until mid week | [9 empty] | -14.3867 |  |  |  |  | OK | 2025-04-04: -38.5357; 2025-04-11: -15.4143; 2025-04-18: 53.95
Valero Three Rivers | 3 | 9.35 | 0.2033% | 2025-04-11 | 2025-04-13 | Ref (11) | Up after unplanned SD | [9 empty] | -0.62333 | [5 empty] | 2025-04-11: -1.3357; 2025-04-25: 1.3357
P66 Sweeny | 3 | 19.5 | 0.4239% | 2024-11-15 | 2025-04-14 | FCC | Restarted 4/14; previously assumed permanently shut | [6 empty] | -19.5 | -19.5 | -0.0042391 | -8.45 |  |  |  |  | OK | 2024-11-22: -13.65; 2025-04-18: 11.1429; 2025-04-25: 8.3571
CVR Coffeyville | 2 | 30.05 | 1.252% | 2025-01-23 | 2025-04-14 | CDU (60), FCC (37) | Split out since SU was ahead of other secondary units | Extended to apr 18; increased activity may need to split our Reformer start up; 4/3 increase coker activity | [5 empty] | -7.7548 | -30.05 | -30.05 | -13.0217 |  |  |  |  | OK | 2025-01-24: -4.2929; 2025-01-31: -25.7571; 2025-04-18: 17.1714; 2025-04-25: 12.8786
XOM Baytown | 3 | 2.5 | 0.05435% | 2025-04-04 | 2025-04-14 | CDU cut (10) | [10 empty] | -0.83333 | [5 empty] | 2025-04-11: -2.5; 2025-04-25: 2.5
Motiva Port Arthur | 3 | 52.65 | 1.145% | 2025-01-24 | 2025-04-15 | FCC (81) | Up 4/15 per IIR | missed 4/12 IIR date; attempted 4/14 SU | [5 empty] | -11.8887 | -52.65 | -52.65 | -24.57 |  |  |  |  | OK | 2025-01-24: -7.5214; 2025-01-31: -45.1286; 2025-04-18: 22.5643; 2025-04-25: 30.0857
XOM Baton Rouge | 3 | 21.45 | 0.4663% | 2025-04-10 | 2025-04-15 | FCC(30) derate | total FCC 190 vs 223 until mid week | [9 empty] | -3.575 | [5 empty] | 2025-04-11: -3.0643; 2025-04-18: -12.2571; 2025-04-25: 12.2571; 2025-05-02: 3.0643
XOM Beaumont | 3 | 18.7 | 0.4065% | 2025-04-09 | 2025-04-16 | HDC (14) derate, CDU derate (7) , FCC derate (25) | Fire on pump | [9 empty] | -4.3633 | [5 empty] | 2025-04-11: -5.3429; 2025-04-25: 5.3429
PBF Torrance | 5 | 64.5 | 4.778% | 2025-03-13 | 2025-04-17 | FCC (90), Coker (60) | CDU Split out | coker never went down in GS | [7 empty] | -37.4516 | -34.4 |  |  |  |  | OK | 2025-03-14: -9.2143; 2025-03-21: -55.2857; 2025-04-18: 64.5; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Borger | 3 | 31.05 | 0.675% | 2025-03-20 | 2025-04-17 | FCC(30), Crude cut (46) | Up per IIR | Revise to 4/17 per IIR; increased activity 4/14 https://energyrt.woodmac.com/oil/alerts/images/ead06639-47dc-40ef-b392-fcf4959b2cb8 | [7 empty] | -11.0177 | -16.56 |  |  |  |  | OK | 2025-03-21: -4.4357; 2025-03-28: -26.6143; 2025-04-18: 4.4357; 2025-04-25: 26.6143
PBF Torrance | 5 | 4.15 | 0.3074% | 2025-03-28 | 2025-04-17 | CDU(166) | Assuming CDU running at Min until secondary units come up | pushed to 4/11 per IIR | [7 empty] | -0.40161 | -2.2133 |  |  |  |  | OK | 2025-04-04: -4.15; 2025-04-18: 1.1857; 2025-04-25: 2.9643; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
XOM Joliet | 2 | 29.05 | 1.21% | 2025-04-07 | 2025-04-17 | Coker (14), FCC (20), Ref (13), CDU(10) | [10 empty] | -9.6833 |  |  |  |  | OK | 2025-04-11: -16.6; 2025-04-18: -12.45; 2025-04-25: 16.6; 2025-05-02: 12.45
Marathon St. Paul Park | 2 | 9.52 | 0.3967% | 2025-04-08 | 2025-04-18 | CR (11.2) | SD unplanned, assuming 1 wk | [9 empty] | -3.1733 | [5 empty] | 2025-04-11: -4.08; 2025-04-18: -5.44; 2025-04-25: 5.44; 2025-05-02: 4.08
XOM Baton Rouge | 3 | 6.25 | 0.1359% | 2025-04-08 | 2025-04-18 | Coker (25) | SD 4/8 | [9 empty] | -2.0833 |  |  |  |  | OK | 2025-04-11: -2.6786; 2025-04-18: -3.5714; 2025-04-25: 3.5714; 2025-05-02: 2.6786
Marathon Robinson | 2 | 34 | 1.417% | 2025-03-17 | 2025-04-19 | Ref (40) | HDC outage, secondary unit derates during T/A duration | [8 empty] | -15.3548 | -20.4 |  |  |  |  | OK | 2025-03-21: -14.5714; 2025-03-28: -19.4286; 2025-04-25: 29.1429; 2025-05-02: 4.8571
Citgo Lake Charles | 3 | 45.05 | 0.9793% | 2025-03-31 | 2025-04-19 | Ref (53) | SU on 4/19 | still down pushing out | [7 empty] | 0 | -27.03 |  |  |  |  | OK | 2025-04-04: -32.1786; 2025-04-11: -12.8714; 2025-04-25: 38.6143; 2025-05-02: 6.4357
Marathon Robinson | 2 | 6.65 | 0.2771% | 2025-04-01 | 2025-04-19 | CDU derate (64) | [10 empty] | -3.99 | [5 empty] | 2025-04-04: -2.85; 2025-04-11: -3.8; 2025-04-25: 5.7; 2025-05-02: 0.95
Valero Meraux | 3 | 27.2 | 0.5913% | 2025-04-03 | 2025-04-19 | Ref (32) | SD unplanned, increased activity 4.10 | pushed back to 4/18; IIR not reporting | [8 empty] | -14.5067 |  |  |  |  | OK | 2025-04-04: -7.7714; 2025-04-11: -19.4286; 2025-04-25: 23.3143; 2025-05-02: 3.8857
Citgo Corpus Christi | 3 | 11.25 | 0.2446% | 2025-04-17 | 2025-04-19 | Coker (45) | Up after unplanned SD | [9 empty] | -0.75 | [5 empty] | 2025-04-18: -1.6071; 2025-04-25: 1.6071
Chevron Salt Lake | 4 | 5.32 | 1.565% | 2025-04-17 | 2025-04-19 | Alky (5.6) | Sd unplanned, assuming 1 wk | [9 empty] | -0.35467 | [5 empty] | 2025-04-18: -0.76; 2025-04-25: 0.76
P66 Lake Charles | 3 | 16.25 | 0.3533% | 2025-03-12 | 2025-04-20 | CDU (65) | Up after unplanned SD | Added 3/20- Genscape email added late | [7 empty] | -9.9597 | -10.2917 |  |  |  |  | OK | 2025-03-14: -4.6429; 2025-03-21: -11.6071; 2025-04-25: 11.6071; 2025-05-02: 4.6429
Marathon Canton | 2 | 42.25 | 1.76% | 2025-04-11 | 2025-04-20 | CDU(92),Ref(19),FCC(26) | Full Site unplanned SD; assuming 1wk. possibly starting TA early | [9 empty] | -12.675 |  |  |  |  | OK | 2025-04-11: -6.0357; 2025-04-18: -36.2143; 2025-04-25: 24.1429; 2025-05-02: 18.1071
CVR Coffeyville | 2 | 1.95 | 0.08125% | 2025-01-23 | 2025-04-21 | Coker (19.5) | Split out Coker | [6 empty] | -0.50323 | -1.95 | -1.95 | -1.3 | [5 empty] | 2025-03-07: -1.95; 2025-04-25: 1.1143; 2025-05-02: 0.83571
CVR Coffeyville | 2 | 28.85 | 1.202% | 2025-01-23 | 2025-04-23 | Ref (25), CDU (76) | Split out FCC/CDU; extended to 4/30 per IIR | [6 empty] | -7.4452 | -28.85 | -28.85 | -21.1567 |  |  |  |  | OK | 2025-01-24: -4.1214; 2025-01-31: -24.7286; 2025-04-25: 8.2429; 2025-05-02: 20.6071
Marathon Robinson | 2 | 1.4 | 0.05833% | 2025-03-17 | 2025-04-23 | HDC (28) | Separated HDC and Ref | [8 empty] | -0.63226 | -1.0267 | [5 empty] | 2025-03-21: -0.8; 2025-03-28: -0.6; 2025-04-25: 0.6; 2025-05-02: 0.8
Big West-Salt Lake City | 4 | 8.125 | 2.39% | 2025-04-13 | 2025-04-23 | FCC(12.5) | Unplanned SD 4/13 | [9 empty] | -2.7083 |  |  |  |  | OK | 2025-04-18: -4.6429; 2025-05-02: 4.6429
Flint Hills Pine Bend | 2 | 4.125 | 0.3% | 2025-04-15 | 2025-04-23 | DC2 (16.5) | Up per Genscape | [9 empty] | -1.1 |  |  |  |  | OK | 2025-04-18: -2.9464; 2025-05-02: 2.9464
Lazarus Nixon | 3 | 3.75 | 0.08152% | 2025-04-21 | 2025-04-23 | CDU(15) | Unplanned SD | [9 empty] | -0.25 | [5 empty] | 2025-04-25: -1.0714; 2025-05-02: 1.0714
Valero McKee | 3 | 18.55 | 0.4033% | 2025-04-08 | 2025-04-24 | Ref (18) | Assuming it is up- unmonitored in Genscape | Added 3/11 per IIR | [8 empty] | -9.8933 |  |  |  |  | OK | 2025-04-11: -7.95; 2025-04-18: -10.6; 2025-04-25: 2.65; 2025-05-02: 15.9
Total Port Arthur | 3 | 10 | 0.2174% | 2025-04-21 | 2025-04-24 | CDU (40) | [10 empty] | -1 | [5 empty] | 2025-04-25: -4.2857; 2025-05-02: 4.2857
Total Port Arthur | 3 | 15 | 0.3261% | 2025-04-23 | 2025-04-24 | Coker (60) | [10 empty] | -0.5 | [5 empty] | 2025-04-25: -2.1429; 2025-05-02: 2.1429
Pemex Deer Park | 3 | 25.5 | 0.5543% | 2025-04-21 | 2025-04-25 | Ref (30) | Up after unplanned SD | [9 empty] | -3.4 | [5 empty] | 2025-04-25: -14.5714; 2025-05-02: 14.5714
HF Sinclair Puget/Anacortes | 5 | 14 | 1.037% | 2025-04-23 | 2025-04-26 | Coker (26), CDU derate (30) | Up after unplanned SD | [9 empty] | -1.4 | [5 empty] | 2025-04-25: -4; 2025-05-02: 4; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Martinez | 5 | 92.775 | 6.872% | 2025-02-01 | 2025-04-27 | CDU (155),Coker (21), Coker (25), HDC (42), Ref (29.5), FCC (70) | Unplanned SD due to fire on hydrotreater, assuming 45 day downtime; increased to 4 months | [7 empty] | -92.775 | -92.775 | -80.405 |  |  |  |  | OK | 2025-02-07: -79.5214; 2025-02-14: -13.2536; 2025-05-02: 92.775; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Chevron Pasadena | 3 | 29 | 0.6304% | 2025-04-21 | 2025-04-27 | CDU (116) | Up after unplanned SD | [9 empty] | -5.8 | [5 empty] | 2025-04-25: -16.5714; 2025-05-02: 16.5714
CVR Coffeyville | 2 | 19 | 0.7917% | 2025-04-23 | 2025-04-27 | CDU (76) | Up after T/A | [9 empty] | -2.5333 | [5 empty] | 2025-04-25: -5.4286; 2025-05-02: 5.4286
HF Sinclair - Tulsa West | 2 | 2.125 | 0.08854% | 2025-03-07 | 2025-04-28 | Coker (8.5) | Up after unplanned SD | [8 empty] | -1.6452 | -1.9125 | [5 empty] | 2025-03-07: -0.30357; 2025-03-14: -1.8214; 2025-03-21: -0.30357; 2025-05-02: 1.2143; 2025-05-09: 0.91071
HF Tulsa East | 2 | 19.265 | 0.8027% | 2025-03-08 | 2025-04-28 | CDU (40), FCC cut (9), Ref cut (6) | Still looks cold despite IIR notification it started up | iir 3/1-4/16; still cold on 4/14 pushing SU | [7 empty] | -14.2934 | -17.3385 |  |  |  |  | OK | 2025-03-14: -16.5129; 2025-03-21: -2.7521; 2025-05-02: 11.0086; 2025-05-09: 8.2564; 2025-12-19: 0; 2025-12-26: 0
PBF Delaware City | 1 | 0.9 | 0.1875% | 2025-02-26 | 2025-04-30 | HC(18) | Planned TA 3/3/-4/11; unplanned SD 2/26 assuming TA will start early; | IIR planned dates 4/1-5/11; increased activity 4/5 | [6 empty] | -0.064286 | -0.9 | -0.87 |  |  |  |  | OK | 2025-02-28: -0.25714; 2025-03-07: -0.64286; 2025-05-02: 0.9
XOM Joliet | 2 | 2 | 0.08333% | 2025-04-22 | 2025-04-30 | Coker (8) cut | [10 empty] | -0.53333 | [5 empty] | 2025-04-25: -0.85714; 2025-05-09: 0.85714
PBF Chalmette | 3 | 35.85 | 0.7793% | 2025-04-26 | 2025-04-30 | CR (19), CDU (197) | CDUs up, ref remains down | [9 empty] | -4.78 |  |  |  |  | OK | 2025-05-02: -20.4857; 2025-05-09: 20.4857
Wyoming Refing Company (Newcastle) | 4 | 8.295 | 2.44% | 2025-02-12 | 2025-05-01 | CDU(20),FCC(5.5),Ref(3.2) | Will return to 50% rates in mid-April per Par Pacific webcast | Furnace explosion | [6 empty] | -4.74 | -8.295 | -8.295 | 0 |  |  |  | OK | 2025-02-14: -2.37; 2025-02-21: -5.925; 2025-05-02: 2.37; 2025-05-09: 5.925
Marathon Anacortes | 5 | 67.9 | 5.03% | 2025-03-17 | 2025-05-01 | CDU(120), FCC (52), Ref (26) | CDU (120) outage 3/13-5/30; IIR pushed back 3/17-5/30 | Reduced duration per IIR | [7 empty] | -30.6645 | -67.9 | 0 |  |  |  | OK | 2025-03-21: -29.1; 2025-03-28: -38.8; 2025-05-02: 67.9; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
P66 Bayway | 1 | 17.5 | 3.646% | 2025-04-30 | 2025-05-02 | CDU (70) cut due to VDU issue | Assuming issue based on purchasing | [9 empty] | 0 | -0.56452 |  |  |  |  | 2025-05-02: -5; 2025-05-09: 5
XOM Joliet | 2 | 18.75 | 0.7812% | 2025-04-29 | 2025-05-03 | Coker (55), CDU cut (20) | [10 empty] | -0.625 | -1.2097 |  |  |  |  | 2025-05-02: -10.7143; 2025-05-16: 10.7143
Flint Hills Pine Bend | 2 | 4.125 | 0.3% | 2025-04-24 | 2025-05-05 | DC3 (16.5) | SD, assuming down until TA end | [9 empty] | -0.825 | -0.53226 |  |  |  |  | 2025-04-25: -1.1786; 2025-05-02: -2.9464; 2025-05-09: 2.9464; 2025-05-16: 1.1786
Woods Cross Refinery | 4 | 10.11 | 2.974% | 2025-04-28 | 2025-05-05 | CDU (26.4) | SD unplanned, assuming 2 wk | [9 empty] | -0.674 | -1.3045 |  |  |  |  | 2025-05-02: -5.7771; 2025-05-16: 5.7771
XOM Baytown | 3 | 13 | 0.2826% | 2025-04-17 | 2025-05-06 | FCC (20) | Cut back due to BOP SD | [9 empty] | -5.6333 | -2.0968 |  |  |  |  | 2025-04-18: -3.7143; 2025-04-25: -9.2857; 2025-05-09: 5.5714; 2025-05-16: 7.4286
Marathon Anacortes | 5 | 30 | 2.222% | 2025-05-02 | 2025-05-06 | CDU(120) | CDU down longer than other units | [10 empty] | -3.871 |  |  |  |  | 2025-05-02: -4.2857; 2025-05-16: 4.2857; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
BP Whiting | 2 | 59.5 | 2.479% | 2025-04-27 | 2025-05-07 | CR (70) | Up after unplanned SD | [9 empty] | -5.95 | -11.5161 |  |  |  |  | 2025-05-02: -42.5; 2025-05-16: 42.5
Valero Benicia | 5 | 90 | 6.667% | 2025-05-05 | 2025-05-08 | Full site outage | SD due to fire at FCC | [10 empty] | -8.7097 |  |  |  |  | 2025-05-09: -38.5714; 2025-05-16: 38.5714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Cenex McPherson | 2 | 56.855 | 2.369% | 2025-03-16 | 2025-05-09 | CDU (109), HDC (30), Coker (25), FCC (22.7), Ref (32) | Extended to 5/6 despite IIR saying it was up since it looks cold in Genscape | [8 empty] | -27.5105 | -56.855 | -14.6723 |  |  |  | OK | 2025-03-21: -40.6107; 2025-03-28: -16.2443; 2025-05-09: 8.1221; 2025-05-16: 48.7329
P66 Wood River | 2 | 38.3 | 1.596% | 2025-03-19 | 2025-05-09 | CDU derate (44), FCC (42) | Pushed back 2 weeks per IIR | Moved back to 3/19 | [7 empty] | -14.8258 | -38.3 | -9.8839 |  |  |  | OK | 2025-03-21: -10.9429; 2025-03-28: -27.3571; 2025-05-09: 5.4714; 2025-05-16: 32.8286
Chevron Pascagoula | 3 | 26.59 | 0.578% | 2025-03-27 | 2025-05-09 | CDU (50), Hydrocracker (24), Assuming Coker/FCC/Ref derates | Planned TA 3/27-4/30, made it 50 kbd rather than full CDU outage per crude purchasing patterns; coker added to scope per ENT; | CDU 2 not monitored | [7 empty] | -3.431 | -26.59 | -6.8619 |  |  |  | OK | 2025-03-28: -3.7986; 2025-04-04: -22.7914; 2025-05-09: 3.7986; 2025-05-16: 22.7914
Marathon Carson | 5 | 20.28 | 1.502% | 2025-05-07 | 2025-05-09 | FCC (30) | Rate cut due to issues | [10 empty] | -1.3084 |  |  |  |  | 2025-05-09: -8.6914; 2025-05-16: 8.6914; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
El Segundo | 5 | 25 | 1.852% | 2025-05-05 | 2025-05-11 | CDU(100) | SU after unplanned SD | [10 empty] | -4.8387 |  |  |  | OK | 2025-05-09: -14.2857; 2025-05-23: 14.2857; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Marathon St. Paul Park | 2 | 9.52 | 0.3967% | 2025-05-06 | 2025-05-11 | CR (11.2) | SU after unplanned SD | [10 empty] | -1.5355 |  |  |  |  | 2025-05-09: -4.08; 2025-05-16: 4.08
Hunt Tuscaloosa | 3 | 29.125 | 0.6332% | 2025-05-07 | 2025-05-11 | DC (32), HDC (18.5), Ref (22), CDU(63) | SU after fire | [10 empty] | -3.7581 |  |  |  |  | 2025-05-09: -8.3214; 2025-05-23: 8.3214
Calcasieu - Lake Charles | 3 | 16 | 0.3478% | 2025-04-23 | 2025-05-12 | CDU (64kbd) | Up after T/A | [9 empty] | -3.7333 | -5.6774 |  |  |  | OK | 2025-04-25: -4.5714; 2025-05-02: -11.4286; 2025-05-16: 11.4286; 2025-05-23: 4.5714
Petro Star Valdez | 5 | 15 | 1.111% | 2025-04-28 | 2025-05-12 | CDU (60) | 60 kbd CDU down 5/2-5/16 | [9 empty] | -1 | -5.3226 |  |  |  | OK | 2025-05-02: -8.5714; 2025-05-09: -6.4286; 2025-05-16: 6.4286; 2025-05-23: 8.5714; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
PBF Chalmette | 3 | 16.15 | 0.3511% | 2025-05-01 | 2025-05-12 | CR (19) | Up after unplanned SD | [10 empty] | -5.7306 |  |  |  | OK | 2025-05-02: -4.6143; 2025-05-09: -11.5357; 2025-05-23: 11.5357; 2025-05-30: 4.6143
Cenex McPherson | 2 | 14.755 | 0.6148% | 2025-05-09 | 2025-05-12 | FCC (22.7) | FCC still down, expecting start up shortly after the other units | [10 empty] | -1.4279 |  |  |  |  | 2025-05-09: -2.1079; 2025-05-23: 2.1079
Valero Benicia | 5 | 61.3 | 4.541% | 2025-05-08 | 2025-05-13 | FCC (77), Crude cut (45) | SD due to fire at FCC | [10 empty] | -9.8871 |  |  |  |  | 2025-05-09: -17.5143; 2025-05-23: 17.5143; 2025-12-26: 2025-12-26; 2026-01-02: 2026-01-02; 2026-01-09: 2026-01-09
Hunt Tuscaloosa | 3 | 2.4 | 0.05217% | 2025-05-11 | 2025-05-13 | DC 9) | Reduced rates due to fire | [10 empty] | -0.15484 |  |  |  |  | 2025-05-16: -2.4; 2025-05-23: 2.4
Countrymark Mt Vernon | 2 | 3.5 | 0.1458% | 2025-04-24 | 2025-05-14 | CDU (35) | [10 empty] | -0.7 | -1.4677 |  |  |  | OK | 2025-04-25: -1; 2025-05-02: -2.5; 2025-05-16: 1; 2025-05-23: 2.5
PBF Chalmette | 3 | 11.875 | 0.2582% | 2025-05-13 | 2025-05-14 | Alky (12.5) | SD unplanned, looks hot 5/14 | [10 empty] | -0.38306 |  |  |  | OK | 2025-05-16: -3.3929; 2025-05-23: 3.3929
Valero Meraux | 3 | 32 | 0.6957% | 2025-05-13 | 2025-05-14 | CDU (128) | Split out bc ref SD | [10 empty] | -1.0323 |  |  |  |  | 2025-05-16: -9.1429; 2025-05-23: 9.1429
Valero Port Arthur | 3 | 12.75 | 0.2772% | 2025-05-07 | 2025-05-15 | Ref (15) | Su after issues | [10 empty] | -3.2903 |  |  |  |  | 2025-05-09: -5.4643; 2025-05-23: 5.4643
Chevron Pasadena | 3 | 19.55 | 0.425% | 2025-05-12 | 2025-05-15 | Ref (23) | Up after unplanned SD | [10 empty] | -1.8919 |  |  |  |  | 2025-05-16: -8.3786; 2025-05-23: 8.3786
Par Billings | 4 | 2.5 | 0.7353% | 2025-04-26 | 2025-05-16 | Coker (10) | Su after Sd unplanned | [9 empty] | -0.33333 | -1.2097 |  |  |  |  | 2025-05-02: -2.1429; 2025-05-09: -0.35714; 2025-05-23: 2.1429; 2025-05-30: 0.35714
PBF Martinez | 5 | 5.25 | 0.3889% | 2025-04-27 | 2025-05-16 | Coker (21) | Still down, assuming it will come up a few days after the other units | [9 empty] | -0.525 | -2.5403 |  |  |  |  | 2025-05-02: -2.25; 2025-05-09: -3; 2025-05-23: 5.25
Citgo Lemont | 2 | 11.9 | 0.4958% | 2025-05-11 | 2025-05-16 | Ref (14) | assuming SU 5/16, no official confirmation yet | [10 empty] | -1.9194 |  |  |  |  | 2025-05-16: -5.1; 2025-05-23: 5.1
Calcasieu - Lake Charles | 3 | 18.25 | 0.3967% | 2025-04-22 | 2025-05-17 | CDU (73kbd) | SU after SD unplanned | up 5/19 per IIR vs 5/17 | [8 empty] | -4.8667 | -9.4194 |  |  |  | OK | 2025-04-25: -7.8214; 2025-05-02: -10.4286; 2025-05-23: 15.6429; 2025-05-30: 2.6071
Valero Corpus Christi East | 3 | 8.5 | 0.1848% | 2025-05-14 | 2025-05-18 | Coker (34) | Su after SD unplanned | [10 empty] | -1.0968 |  |  |  |  | 2025-05-16: -2.4286; 2025-05-23: 2.4286
Flint Hills Pine Bend | 2 | 55.25 | 2.302% | 2025-03-31 | 2025-05-20 | FCC (85) | Revised dates to 3/31 start 39 day duration. Increased activity on 5/18; SU 5/20 | changed SU from 5/27 to 5/20 | [7 empty] | 0 | -55.25 | -33.8629 |  |  |  | OK | 2025-04-04: -31.5714; 2025-04-11: -23.6786; 2025-05-23: 23.6786; 2025-05-30: 31.5714
Flint Hills Pine Bend | 2 | 14.25 | 0.3% | 2025-04-09 | 2025-05-20 | CDU (57) | CDU restarted 4/9, assuming derated until FCC starts up | [9 empty] | -9.975 | -8.7339 |  |  |  | OK | 2025-04-11: -4.0714; 2025-04-18: -10.1786; 2025-05-23: 4.0714; 2025-05-30: 10.1786
Valero Corpus Christi West | 3 | 62.4 | 1.357% | 2025-05-19 | 2025-05-20 | FCC (96) | SD unplanned, FCC SU 5/20, assuming HDC still down given that Ref just SD | [10 empty] | -2.0129 |  |  |  |  | 2025-05-23: -17.8286; 2025-05-30: 17.8286
Sinclair Refinery (HF Sinclair) Wyoming | 4 | 16.345 | 4.807% | 2025-04-12 | 2025-05-21 | Ref (12.5), FCC (22), Coker cut (4), and CDU cut (26) | Planned T/A 4/12-5/21 | [9 empty] | -9.807 | -10.5452 |  |  |  |  | 2025-04-18: -14.01; 2025-04-25: -2.335; 2025-05-23: 2.335; 2025-05-30: 14.01
HF Sinclair - Tulsa West | 2 | 22.8 | 0.95% | 2025-05-19 | 2025-05-21 | CDU 91.2 | down for 2 days per IIR | [10 empty] | -1.471 |  |  |  |  | 2025-05-23: -6.5143; 2025-05-30: 6.5143
Valero Meraux | 3 | 40 | 0.8696% | 2025-05-15 | 2025-05-22 | CDU (128), Ref (32) | CDU Up after unplanned SD | increased activity 5/22 | [9 empty] | -9.0323 |  |  |  |  | 2025-05-16: -11.4286; 2025-05-23: -28.5714; 2025-05-30: 5.7143; 2025-06-06: 34.2857
Valero Wilmington | 5 | 3.75 | 0.2778% | 2025-05-21 | 2025-05-22 | Coker (15) | SU after unplanned SD | [10 empty] | -0.12097 |  |  |  |  | 2025-05-23: -0.53571; 2025-05-30: 0.53571
Countrymark Mt Vernon | 2 | 6.825 | 0.2844% | 2025-04-24 | 2025-05-23 | Ref (6.5), FCC derate (2) | [10 empty] | -1.365 | -4.8435 |  |  |  | OK | 2025-04-25: -1.95; 2025-05-02: -4.875; 2025-05-23: 1.95; 2025-05-30: 4.875
Lazarus Nixon | 3 | 3.75 | 0.08152% | 2025-05-13 | 2025-05-23 | CDU(15) | Su after unplanned Sd | IIR reporting SU on 5/22, still cold so extending to 5/25 | [9 empty] | -1.2097 |  |  |  |  | 2025-05-16: -1.6071; 2025-05-23: -2.1429; 2025-05-30: 2.1429; 2025-06-06: 1.6071
Countrymark Mt Vernon | 2 | 1 | 0.04167% | 2025-05-14 | 2025-05-23 | CDU derate (10) | [11 empty] | -0.29032 |  |  |  | OK | 2025-05-16: -0.28571; 2025-05-23: -0.71429; 2025-05-30: 1
Valero Corpus Christi West | 3 | 29.75 | 0.6467% | 2025-05-20 | 2025-05-23 | Ref (35) | SD unplanned, assuming 1 wk | [10 empty] | -2.879 |  |  |  |  | 2025-05-23: -12.75; 2025-05-30: 12.75
Marathon Robinson | 2 | 3 | 0.125% | 2025-05-18 | 2025-05-24 | Coker (12) | SU after unplanned SD | [10 empty] | -0.58065 |  |  |  |  | 2025-05-23: -3; 2025-05-30: 3
Cenovus Toledo | 2 | 54.75 | 2.281% | 2025-03-31 | 2025-05-25 | Ref (40), HDC (35),CDU (50), Coker (10), FCC derate (20) | Genscape still showing up but IIR said it started 3/31 | possibly starting early due to coker on 3/15; was 4/1 -6/15 | [7 empty] | 0 | -54.75 | -42.3871 |  |  |  | OK | 2025-04-04: -31.2857; 2025-04-11: -23.4643; 2025-05-30: 31.2857; 2025-06-06: 23.4643
Silver Eagle Evanston | 4 | 2.89 | 0.85% | 2025-05-09 | 2025-05-25 | CDU(3.4),ref(3) | planned outage, expected start-up 5/25 | [10 empty] | -1.4916 |  |  |  | OK | 2025-05-09: -1.6514; 2025-05-16: -1.2386; 2025-05-30: 2.0643; 2025-06-06: 0.82571
Par Billings | 4 | 18.375 | 5.404% | 2025-04-01 | 2025-05-26 | FCC (21) CDU (4 kbd derate) | SU after Planned maint 4/1/25 - 5/10/25 | Extending due to cranes still on site 5/22 | [8 empty] | -17.7625 | -14.8185 |  |  |  | OK | 2025-04-04: -10.5; 2025-04-11: -7.875; 2025-05-30: 10.5; 2025-06-06: 7.875
Petro Star North Pole | 5 | 5.5 | 0.4074% | 2025-05-17 | 2025-05-26 | CDU (22) | 22 kbd CDU unit down 5/17-26, previously 5/9-5/18 | [10 empty] | -1.5968 |  |  |  | OK | 2025-05-23: -5.5; 2025-05-30: 3.1429; 2025-06-06: 2.3571
Valero Corpus Christi West | 3 | 2.45 | 0.05326% | 2025-05-19 | 2025-05-26 | HDC (49) | Su afetr SD unplanned, FCC SU 5/20, assuming HDC still down given that Ref just SD | 98.6 | [9 empty] | -0.55323 |  |  |  |  | 2025-05-23: -1.4; 2025-05-30: -1.05; 2025-06-06: 1.4; 2025-06-13: 1.05
Cenovus Lima | 2 | 34 | 1.417% | 2025-05-13 | 2025-05-27 | Reformer (40) | SD unplanned, extending b/c still down on 5/26 | [10 empty] | -15.3548 |  |  |  |  | 2025-05-16: -14.5714; 2025-05-23: -19.4286; 2025-06-06: 19.4286; 2025-06-13: 14.5714
P66 Bayway | 1 | 38.5 | 8.021% | 2025-05-14 | 2025-05-27 | Assuming 50kbd crude cut & 40kbd FCC | Updating SU timing based on them coming out to sell | [10 empty] | -16.1452 |  |  |  |  | 2025-05-16: -5.5; 2025-05-23: -33; 2025-05-30: 38.5
XOM Joliet | 2 | 85.7 | 3.571% | 2025-05-21 | 2025-05-27 | FCC (95), CDU cut (100), Ref (15), Coker (12) | SU after Boiler leak | [10 empty] | -16.5871 |  |  |  |  | 2025-05-23: -36.7286; 2025-06-06: 36.7286
Pemex Deer Park | 3 | 1.925 | 0.04185% | 2025-05-26 | 2025-05-27 | HDC (38.5) | SU after unplanned SD | [10 empty] | -0.062097 |  |  |  |  | 2025-05-30: -0.55; 2025-06-06: 0.55
Wyoming Refing Company (Newcastle) | 4 | 4.1475 | 1.22% | 2025-05-01 | 2025-05-28 | CDU(20),FCC(5.5),Ref(3.2) | 50% rates until memorial day per Par Pacific webcast | [10 empty] | -3.6123 |  |  |  |  | 2025-05-02: -1.185; 2025-05-09: -2.9625; 2025-05-30: 1.185; 2025-06-06: 2.9625
Motiva Port Arthur | 3 | 57.2 | 1.243% | 2025-05-26 | 2025-05-28 | FCC (88), Gasoline HDT | Up after unplanned SD | up 5/29 per GS | [9 empty] | -3.6903 |  |  |  |  | 2025-05-30: -16.3429; 2025-06-06: 16.3429
XOM Joliet | 2 | 30.5 | 1.271% | 2025-05-27 | 2025-05-28 | FCC (20), CDU cut (70) | Expect to come back at reduced rates | [10 empty] | -0.98387 |  |  |  |  | 2025-05-30: -4.3571; 2025-06-06: 4.3571
Valero Corpus Christi West | 3 | 107.2 | 2.33% | 2025-05-28 | 2025-05-28 | CDU (37), HF Alky (22), VDU (30), CDU (102), CCR (35), RHDT (76), FCCU GHDT (58), DHC (36) | Brief blip due to power outage, back up | [10 empty] | 0 |  |  |  |  | 2025-05-30: -7.6571; 2025-06-06: 7.6571
El Segundo | 5 | 2.25 | 0.1667% | 2025-05-25 | 2025-05-29 | HDC (45) | Up after unplanned SD | Up 5/29 per GS | [9 empty] | -0.29032 |  |  |  | OK | 2025-05-30: -1.2857; 2025-06-06: 1.2857
Calcasieu - Lake Charles | 3 | 16 | 0.3478% | 2025-05-28 | 2025-05-29 | CDU (64kbd) | Up after unplanned SD | [10 empty] | -0.51613 |  |  |  |  | 2025-05-30: -2.2857; 2025-06-06: 2.2857
Citgo Lake Charles | 3 | 8.5 | 0.1848% | 2025-04-28 | 2025-05-30 | Coker (34) | SD unplanned | [9 empty] | -0.56667 | -7.9516 |  |  |  |  | 2025-05-02: -4.8571; 2025-05-09: -3.6429; 2025-05-30: 1.2143; 2025-06-06: 7.2857
Valero Port Arthur | 3 | 25 | 0.5435% | 2025-05-28 | 2025-05-30 | Coker (100) | SU after unplanned SD | [10 empty] | -1.6129 |  |  |  |  | 2025-05-30: -7.1429; 2025-06-06: 7.1429
Valero Meraux | 3 | 27.2 | 0.5913% | 2025-05-22 | 2025-05-31 | Ref (32) | Ref SU for 1 day and then SD on 5/25 | [10 empty] | -7.8968 |  |  |  |  | 2025-05-23: -7.7714; 2025-05-30: -19.4286; 2025-06-06: 19.4286; 2025-06-13: 7.7714
Valero Meraux | 3 | 15.55 | 0.338% | 2025-05-25 | 2025-05-31 | CDU (128), HDC (55) | SD unplanned on 5/25 | [10 empty] | -3.0097 |  |  |  |  | 2025-05-30: -13.3286; 2025-06-06: -2.2214; 2025-06-13: 15.55
Calcasieu - Lake Charles | 3 | 18.25 | 0.3967% | 2025-05-28 | 2025-05-31 | CDU (73kbd) | Assuming 2 day SD based on it looking hot in Genscape | [10 empty] | -1.7661 |  |  |  | OK | 2025-05-30: -5.2143; 2025-06-06: 5.2143
BP Cherry Point | 5 | 55.35 | 4.1% | 2025-04-07 | 2025-06-01 | CDU (250), Ref cut (21) | Extending due to TMX activity | Up 5/14 per IIR looks cold in GS | [8 empty] | -42.435 | -55.35 | -1.845 |  |  |  | 2025-04-11: -31.6286; 2025-04-18: -23.7214; 2025-06-06: 55.35
HF Tulsa East | 2 | 18.875 | 0.7865% | 2025-05-15 | 2025-06-01 | CDU (75.5) | SU after unplanned SD | [10 empty] | -9.7419 | -0.62917 |  |  |  | 2025-05-16: -5.3929; 2025-05-23: -13.4821; 2025-06-06: 13.4821; 2025-06-13: 5.3929
XOM Baytown | 3 | 5 | 0.1087% | 2025-05-30 | 2025-06-01 | CDU cut (20) | [11 empty] | -0.16129 | -0.16667 |  |  |  | 2025-05-30: -0.71429; 2025-06-06: -0.71429; 2025-06-13: 1.4286
PBF Toledo | 2 | 67.4 | 2.808% | 2025-05-29 | 2025-06-02 | FCC (82), CDU cut (55) | FCC up 6/2 after unplanned SD | [10 empty] | -4.3484 | -4.4933 |  |  |  | 2025-05-30: -19.2571; 2025-06-06: 19.2571
Chevron Richmond | 5 | 52 | 3.852% | 2025-05-31 | 2025-06-02 | FCC(80) | Up after unplanned SD | [10 empty] | 0 | -3.4667 |  |  |  | 2025-06-06: -22.2857; 2025-06-13: 22.2857
Cenovus Toledo | 2 | 36.45 | 1.519% | 2025-05-26 | 2025-06-03 | Ref (40), HDC (35), Coker (7) | Splitting out CDU since it started up 5/25 | [10 empty] | -5.879 | -3.645 |  |  |  | 2025-05-30: -20.8286; 2025-06-13: 20.8286
El Segundo | 5 | 31.35 | 2.322% | 2025-05-28 | 2025-06-03 | Alky (33) | SD unplanned, assuming 1 wk | [10 empty] | -3.0339 | -3.135 |  |  |  | 2025-05-30: -13.4357; 2025-06-13: 13.4357
PBF Toledo | 2 | 31 | 1.292% | 2025-06-02 | 2025-06-04 | CDU cut (55), Ref (30) | Su after SD unplanned | [11 empty] | -2.0667 |  |  |  | 2025-06-06: -8.8571; 2025-06-13: 8.8571
HF Sinclair - Tulsa West | 2 | 2.125 | 0.08854% | 2025-05-20 | 2025-06-05 | Coker (8.5) | Up after unplanned SD | [10 empty] | -0.75403 | -0.35417 |  |  |  | 2025-05-23: -0.91071; 2025-05-30: -1.2143; 2025-06-13: -2.125
P66 Ponca City | 2 | 24.4 | 1.017% | 2025-06-03 | 2025-06-05 | FCC (26 kbd), Crude cut (70) | SD unplanned, assuming 1 wk | [11 empty] | -1.6267 |  |  |  | 2025-06-06: -10.4571; 2025-06-13: 10.4571
Valero Benicia | 5 | 18.765 | 1.39% | 2025-05-14 | 2025-06-06 | FCC (23), Crude cut (15) | Assuming min rates for 2 months. SD permanent in Apr 26. Intalled heater from AP, no rate cuts going forward | [10 empty] | -10.2905 | -3.753 |  |  |  | 2025-05-16: -5.3614; 2025-05-23: -13.4036; 2025-06-06: 18.765
Valero Ardmore | 2 | 34.65 | 1.444% | 2025-04-18 | 2025-06-10 | Ref (30), 91.5 (CDU) | Splitting out since CDU and Ref SU 6/10 after planned maintenace | [9 empty] | -13.86 | -34.65 | -11.55 |  |  |  | 2025-04-18: -4.95; 2025-04-25: -29.7; 2025-06-13: 9.9; 2025-06-20: 24.75
PBF Paulsboro | 1 | 28 | 5.833% | 2025-05-31 | 2025-06-10 | CDU(110), Ref (20) | Su after CDU SD for planned maintenance, pulled from 6/20 | Start date pulled fwd to 5/30 per IIR; updated duration | [9 empty] | 0 | -9.3333 |  |  | OK | 2025-05-30: -4; 2025-06-06: -24; 2025-06-13: 12; 2025-06-20: 16
PBF Torrance | 5 | 32.31 | 2.393% | 2025-06-03 | 2025-06-10 | FCC cut (30), HDC cut (7), Crude Cut (50) | Reduced rates per ENT | Don't now duration, but don't expect to get a notification of increased rate, so leaving assumption for 1 wk only | [10 empty] | -7.539 |  |  |  | 2025-06-06: -13.8471; 2025-06-20: 13.8471
CVR Wynnewood | 2 | 9.5 | 0.3958% | 2025-06-09 | 2025-06-10 | Cdu (39) | SD unplanned | [11 empty] | -0.31667 |  |  |  | 2025-06-13: -1.3571; 2025-06-20: 1.3571
Valero McKee | 3 | 1.475 | 0.03207% | 2025-06-10 | 2025-06-12 | HDC ( 29.5) | SD unapplanned assuming 1 wk | [11 empty] | -0.098333 |  |  |  | 2025-06-13: -0.42143; 2025-06-20: 0.42143
BP Cherry Point | 5 | 13.75 | 1.019% | 2025-03-17 | 2025-06-13 | Coker(55) | Unwinding due to crude purchases | Split coker out; Up 5/14 per IIR looks cold in GS | [7 empty] | -6.2097 | -13.75 | -13.75 | -5.9583 |  |  | OK | 2025-03-21: -7.8571; 2025-03-28: -5.8929; 2025-06-13: 13.75
BP Cherry Point | 5 | 5 | 0.3704% | 2025-06-01 | 2025-06-13 | CDU cut (20) | Unwinding due to crude purchases | [11 empty] | -2 |  |  |  | 2025-06-13: 5
PBF Martinez | 5 | 6.25 | 0.463% | 2025-06-03 | 2025-06-13 | Coker (25) | SD unplanned, assuming 1 wk | [11 empty] | -2.0833 |  |  |  | 2025-06-06: -2.6786; 2025-06-20: 2.6786
P66 Borger | 3 | 27 | 0.587% | 2025-06-08 | 2025-06-13 | CDU (40)/Ref (20) | Up after unplanned SD | [11 empty] | -4.5 |  |  |  | 2025-06-13: -19.2857; 2025-06-20: 19.2857
XOM Joliet | 2 | 30.75 | 1.281% | 2025-06-12 | 2025-06-14 | CDU (45), FCC (30) | SD due to alky trip | [11 empty] | -2.05 |  |  |  | 2025-06-13: -8.7857; 2025-06-20: 8.7857
Total Port Arthur | 3 | 33.66 | 0.7317% | 2025-06-13 | 2025-06-14 | Ref (39.6) | Up after unplanned SD | [11 empty] | -1.122 |  |  |  | 2025-06-13: -4.8086; 2025-06-20: 4.8086
Valero Ardmore | 2 | 20.1 | 0.8375% | 2025-04-18 | 2025-06-15 | FCC (30), HDC (12) | Splitting out since CDU and Ref SU 6/10, but FCC and HDC still down after planned maintenace | [9 empty] | -8.04 | -20.1 | -10.05 |  |  | OK | 2024-05-03: -14.3571; 2024-05-10: -5.7429; 2024-05-17: 5.7429; 2024-05-24: 14.3571; 2025-04-18: -2.8714; 2025-04-25: -17.2286; 2025-06-20: 14.3571; 2025-06-27: 5.7429
PBF Delaware City | 1 | 15 | 3.125% | 2025-05-27 | 2025-06-15 | Coker (50) | SD unplanned assuming su | [10 empty] | -1.9355 | -7.5 |  |  |  | 2025-05-30: -8.5714; 2025-06-06: -6.4286; 2025-06-20: 15
Cenovus Toledo | 2 | 3.5 | 0.1458% | 2025-06-03 | 2025-06-15 | HDC (35), Coker (7) | Splitting out HDC/Coker since Ref SU 6/3. ENT reporting SU later this week | [11 empty] | -1.4 |  |  |  | 2025-06-06: -2; 2025-06-13: -1.5; 2025-06-20: 3.5
Marathon Texas City | 3 | 54.775 | 1.191% | 2025-06-10 | 2025-06-16 | CDU (67)/FCC (58.5) | SD unplanned assuming 1 wk | [11 empty] | -10.955 |  |  |  | 2025-06-13: -23.475; 2025-06-20: 23.475
Valero Texas City | 3 | 57.2 | 1.243% | 2025-06-12 | 2025-06-16 | FCC (88) | SD unplanned, assuming 4 days per IIR | [11 empty] | -7.6267 |  |  |  | 2025-06-13: -16.3429; 2025-06-20: 16.3429
Total Port Arthur | 3 | 15 | 0.3261% | 2025-06-16 | 2025-06-16 | CDU (150) | 1 day blip | [11 empty] | 0 |  |  |  | 2025-06-20: -2.1429; 2025-06-27: 2.1429
P66 Carson | 5 | 13.25 | 0.9815% | 2025-06-09 | 2025-06-17 | Coker (53) | SU after unplanned SD | [11 empty] | -3.5333 |  |  |  | 2025-06-13: -9.4643; 2025-06-27: 9.4643
BP Cherry Point | 5 | 4.125 | 0.3056% | 2025-06-14 | 2025-06-18 | Coker derate (16.5) | Updated following Genscape SU notification | [11 empty] | -0.55 |  |  |  | 2025-06-20: -2.3571; 2025-06-27: 2.3571
HF Tulsa East | 2 | 2.565 | 0.1069% | 2025-06-14 | 2025-06-18 | Alky (2.7) | Up after unplanned SD | [11 empty] | -0.342 |  |  |  | 2025-06-20: -1.4657; 2025-06-27: 1.4657
Chevron Salt Lake | 4 | 5.32 | 1.565% | 2025-06-16 | 2025-06-19 | Alky (5.6) | Up after unplanned SD | [11 empty] | -0.532 |  |  |  | 2025-06-20: -2.28; 2025-06-27: 2.28
Total Port Arthur | 3 | 41.66 | 0.9057% | 2025-06-16 | 2025-06-19 | CDU (80), Ref (36.9) | SD unplanned, assuming 1 wk | [11 empty] | -4.166 |  |  |  | 2025-06-20: -17.8543; 2025-06-27: 17.8543
Marathon Galveston Bay | 3 | 70 | 1.522% | 2025-06-17 | 2025-06-19 | CDU (280) | Up after unplanned SD | [11 empty] | -4.6667 |  |  |  | 2025-06-20: -30; 2025-06-27: 30
PBF Delaware City | 1 | 0.9 | 0.1875% | 2025-06-06 | 2025-06-21 | HDC (18) | SD unplanned, assuming 1 wk | [11 empty] | -0.45 |  |  |  | 2025-06-06: -0.12857; 2025-06-13: -0.77143; 2025-06-27: 0.77143; 2025-07-04: 0.12857
Woods Cross Refinery (HF Sinclair) | 4 | 3.75 | 1.103% | 2025-06-18 | 2025-06-21 | CDU (15) | SU after unplanned SD | [11 empty] | -0.375 |  |  |  | 2025-06-20: -1.0714; 2025-06-27: 1.0714
Texas International Galveston Crude | 3 | 12.5 | 0.2717% | 2025-06-09 | 2025-06-22 | CDU (50) | SU after planned SD, stilld own extending 1 wk | [11 empty] | -5.4167 |  |  |  | 2025-06-27: 8.9286; 2025-07-04: 3.5714
Valero Ardmore | 2 | 0.6 | 0.025% | 2025-06-16 | 2025-06-22 | HDC (12) | Splitting since FCC SU 6/15 | [11 empty] | -0.12 |  |  |  | 2025-06-20: -0.25714; 2025-06-27: 0.25714
Total Port Arthur | 3 | 20 | 0.4348% | 2025-06-19 | 2025-06-22 | CDU (80) | Splitting out CDU since ref SU | [11 empty] | -2 |  |  |  | 2025-06-20: -5.7143; 2025-06-27: 5.7143
Ergon West Virginia Congo | 1 | 5.575 | 1.161% | 2025-03-31 | 2025-06-23 | CDU (23), Ref (3.6), HDC (4.3) | Planned T/A 3/31-5/9 | [8 empty] | 0 | -5.575 | -5.575 | -4.2742 |  |  | OK | 2025-04-04: -2.7875; 2025-04-11: -2.7875; 2025-06-27: 3.1857; 2025-07-04: 2.3893
Chevron Pasadena | 3 | 4.8875 | 0.1063% | 2025-06-19 | 2025-06-26 | Ref (23) reduced rates | reduced rates due to leak | [11 empty] | -1.1404 |  |  |  | 2025-06-20: -0.69821; 2025-06-27: -4.1893; 2025-07-04: 4.8875
El Segundo | 5 | 51 | 3.778% | 2025-06-24 | 2025-06-26 | Ref (60) | Sdunplanned assuming 1 wk | [11 empty] | -3.4 |  |  |  | 2025-06-27: -14.5714; 2025-07-04: 14.5714
Lazarus Nixon | 3 | 3.75 | 0.08152% | 2025-06-25 | 2025-06-26 | CDU(15) | SD unplanned, assuming 1 wk | [11 empty] | -0.125 |  |  |  | 2025-06-27: -0.53571; 2025-07-04: 0.53571
Monroe Trainer | 1 | 88.5 | 18.44% | 2025-06-23 | 2025-06-27 | CDU (104), FCC (53), Ref (50), HC (23) | SU after unplanned SD | [11 empty] | -11.8 |  |  |  | 2025-06-27: -50.5714; 2025-07-04: 50.5714
P66 Bayway | 1 | 67.275 | 14.02% | 2025-06-26 | 2025-06-27 | FCC (103.5) | SD unplanned for 1 day | [11 empty] | -2.2425 |  |  |  | 2025-06-27: -9.6107; 2025-07-04: 9.6107
P66 Wood River | 2 | 27.5 | 1.146% | 2025-06-24 | 2025-06-28 | CDU (110) | SU after Sd unplanned | [11 empty] | -3.6667 |  |  |  | 2025-06-27: -11.7857; 2025-07-04: 11.7857
Marathon St. Paul Park | 2 | 9.52 | 0.3967% | 2025-06-24 | 2025-06-28 | CR (11.2) | SU after SD unplanned | [11 empty] | -1.2693 |  |  |  | 2025-06-27: -4.08; 2025-07-04: 4.08
El Segundo | 5 | 2.25 | 0.1667% | 2025-06-24 | 2025-06-30 | HDC (45) | Sdunplanned assuming 1 wk | [11 empty] | -0.45 |  |  |  | 2025-06-27: -0.96429; 2025-07-11: 0.96429
XOM Beaumont | 3 | 9.25 | 0.2011% | 2025-06-29 | 2025-06-30 | FCC slow down (5), HDC slowdown (20), CDU (20) | CDU cutback due to crude contamination in region | [11 empty] | -0.30833 |  |  |  | 2025-07-04: -1.3214; 2025-07-11: 1.3214
HF Sinclair - Tulsa West | 2 | 22.75 | 0.9479% | 2025-06-30 | 2025-07-01 | CDU (91), VDU | Sd unplanned, assuming 1wk | [11 empty] | -1.5167 | -0.73387 |  |  | 2025-07-04: -3.25; 2025-07-11: 3.25
P66 Sweeny | 3 | 19.5 | 0.4239% | 2025-06-25 | 2025-07-02 | FCC | SD unplanned, assuming 1 wk | [11 empty] | -3.25 | -1.2581 |  |  | 2025-06-27: -8.3571; 2025-07-11: 8.3571
XOM Baytown | 3 | 39.25 | 0.8533% | 2025-06-30 | 2025-07-02 | FCC3 cut back/CDU(120) slowdown/Coker (30) slowdown | FCC and CDU cutback due to LE losing DCS console | [11 empty] | 0 | -2.5323 |  |  | 2025-07-04: -11.2143; 2025-07-11: 11.2143
Chevron Salt Lake City | 4 | 3 | 0.8824% | 2025-06-26 | 2025-07-03 | Coker (10 kbd) | SD unplanned, assuming 1 wk | [11 empty] | -0.4 | -0.29032 |  |  | 2025-06-27: -0.85714; 2025-07-11: 0.85714
XOM Baytown | 3 | 65 | 1.413% | 2025-06-30 | 2025-07-03 | FCC2 down | FCC down due to LE losing DCS console | [11 empty] | 0 | -6.2903 |  |  | 2025-07-04: -27.8571; 2025-07-11: 27.8571
GCC Galveston Bunkers | 3 | 12.5 | 0.2717% | 2025-06-02 | 2025-07-04 | CDU | Changing to planned T/A per IIR. Extending from 6/19 | [11 empty] | -11.6667 | -1.6129 |  | OK | 2025-06-06: -8.9286; 2025-06-13: -3.5714; 2025-06-27: 8.9286; 2025-07-04: 3.5714
Suncor Commerce City | 4 | 5.85 | 1.721% | 2025-06-22 | 2025-07-04 | FCC(9.3) | SD unplanned. Extended SD | [11 empty] | -1.56 | -0.75484 |  |  | 2025-06-27: -4.1786; 2025-07-04: -1.6714; 2025-07-11: 4.1786; 2025-07-18: 1.6714
Woods Cross Refinery (HF Sinclair) | 4 | 5.85 | 1.721% | 2025-06-23 | 2025-07-04 | FCC (9) | SD unplanned. Extended SD | [11 empty] | -1.365 | -0.75484 |  |  | 2025-06-27: -3.3429; 2025-07-04: -58.1571; 2025-07-11: 58.1571; 2025-07-18: 3.3429
XOM Beaumont | 3 | 61.5 | 1.337% | 2025-07-01 | 2025-07-04 | CDU (246)- BLADE | BLADE trip due to furnace issue | [12 empty] | -5.9516 |  |  | 2025-07-04: -26.3571; 2025-07-11: 26.3571
Citgo Corpus Christi | 3 | 25.5 | 0.5543% | 2025-06-29 | 2025-07-06 | Ref (30) | SD unplanned assuming 1 wk | [11 empty] | -0.85 | -4.9355
Puget Sound | 5 | 6 | 0.4444% | 2025-06-29 | 2025-07-06 | Coker (24) | Sd unplanned assuming 1 wk | [11 empty] | -0.2 | -1.1613 |  |  | 2025-07-04: -5.1429; 2025-07-11: 5.1429
Marathon Wilmington | 5 | 10.5 | 0.7778% | 2025-06-18 | 2025-07-07 | Coker (42) | SD unplanned, assuming 1 wk | [11 empty] | -4.2 | -2.371 |  |  | 2025-06-20: -3; 2025-06-27: -7.5; 2025-07-11: 3; 2025-07-18: 7.5
CVR Wynnewood | 2 | 13.65 | 0.5687% | 2025-06-30 | 2025-07-07 | FCC (21) | SD unplanned, assuming 1 wk | [11 empty] | 0 | -3.0823 |  |  | 2025-07-04: -7.8; 2025-07-18: 7.8
XOM Baton Rouge | 3 | 44.75 | 0.9728% | 2025-06-30 | 2025-07-07 | FCC cutback 25kbd/CDU cutback 84 kbd, Coker cut back 30 kbd | [12 empty] | 0 | -10.1048 |  |  | 2025-07-04: -25.5714; 2025-07-18: 25.5714
HF Tulsa East | 2 | 10.53 | 0.4387% | 2025-06-30 | 2025-07-07 | FCC (16.2) | Sd unplanned, assuming 1wk | [11 empty] | 0 | -2.3777 |  |  | 2025-07-04: -6.0171; 2025-07-18: 6.0171
HF Sinclair - Tulsa West | 2 | 2.125 | 0.08854% | 2025-06-24 | 2025-07-08 | Coker (8.5) | Sd unplanned, SU assumption updated to SU with CDU | [11 empty] | -0.425 | -0.54839 |  |  | 2025-06-27: -0.91071; 2025-07-11: 0.91071
P66 Wood River | 2 | 7.5 | 0.3125% | 2025-07-18 | 2025-07-24 | CDU (110) | Per crude team just cut back | [12 empty] | -1.4516 |  |  | 2025-07-18: -1.0714; 2025-07-25: -5.3571; 2025-08-01: 5.3571; 2025-08-08: 1.0714
Marathon Carson | 5 | 17 | 1.259% | 2025-07-06 | 2025-08-03 | Ref(20) | 20 kbd Reformer down 7/6 to 8/3 | [12 empty] | -13.7097 |  | OK | 2025-07-11: -14.5714; 2025-07-18: -2.4286; 2025-08-08: 7.2857; 2025-08-15: 9.7143
PBF Torrance | 5 | 1.2 | 0.08889% | 2025-07-11 | 2025-08-24 | HDC (24) | Added per IIR 7/11-8/24 | [12 empty] | -0.77419 |  | OK | 2025-07-11: -0.17143; 2025-07-18: -1.0286; 2025-08-08: 1.0286; 2025-08-15: 0.17143; 2025-08-29: 0.85714; 2025-09-05: 0.34286
XOM Beaumont | 3 | 9.8 | 0.213% | 2025-07-13 | 2025-08-28 | HDC (10), Ref (10) | HDC compressor major outage. Limit HDC & Ref | [12 empty] | -5.6903 |  |  | 2025-07-18: -7; 2025-07-25: -2.8; 2025-08-29: 1.4; 2025-09-05: 8.4
Marathon Galveston Bay | 3 | 31.4167 | 0.2717% | 2025-06-10 | 2025-09-01 | FCC (145) | Extending cut while hydrocracker is down due to FCC pre-treater being down | [11 empty] | -20.9444 | -31.4167 |  | OK | 2025-06-13: -13.4643; 2025-06-20: -17.9524; 2025-09-05: 4.1786; 2025-09-12: 1.6714; 2026-01-16: 0; 2026-01-23: 0
Marathon Galveston Bay | 3 | 28.2 | 0.613% | 2025-06-14 | 2025-09-01 | Hydrocracker (64 kbd), CDU cut (100) | SD unplanned due to fire | [11 empty] | -15.04 | -28.2 |  |  | 2025-06-20: -24.1714; 2025-06-27: -4.0286; 2025-09-05: 0; 2025-09-12: 3.3429
Marathon Canton | 2 | 42.25 | 1.76% | 2025-07-09 | 2025-09-06 | CDU(92),Ref(19),FCC(26) | Planned outage 7/9-9/6, changed from 7/11-9/8/25 | [12 empty] | -29.9839 |  | OK | 2025-07-11: -18.1071; 2025-07-18: -24.1429; 2025-09-05: 18.1071; 2025-09-12: 24.1429; 2026-02-06: -30.1786; 2026-02-13: -12.0714; 2026-04-03: 12.0714; 2026-04-10: 30.1786
Flint Hills Pine Bend | 2 | 41.25 | 0.3% | 2025-08-29 | 2025-09-24 | CDU (165) | CDU 2 Planned T/A | added 4/10 | [13 empty] | OK | 2025-09-05: -41.25; 2025-09-26: 11.7857; 2025-10-03: 29.4643
Irving St John | Canada | 16.25 |  | 2025-06-01 | 2025-09-30 | FCC (25) | Reporting they are upgrading this FCC | [11 empty] | -15.7083 | -16.25
P66 Lake Charles | 3 | 20 | 0.4348% | 2025-09-01 | 2025-10-05 | CDU (80) | Planned T/A 9/1-10/5 | [15 empty] | 2025-09-05: -14.2857; 2025-09-12: -5.7143; 2025-10-10: 14.2857; 2025-10-17: 5.7143
Valero Memphis | 2 | 69.75 | 0.3% | 2025-09-01 | 2025-10-05 | CDU (110), FCC (65) | CDU and FCC planned TA - new, added 6/3 | [15 empty] | 2025-09-05: -29.8929; 2025-09-12: -39.8571; 2025-10-17: 9.9643; 2025-10-24: 39.7857; 2025-10-31: 20
Ergon Vicksburg MS | 3 | 6.25 | 0.1359% | 2025-09-03 | 2025-10-07 | CDU (25) | Planned T/A | [15 empty] | 2025-09-05: -1.7857; 2025-09-12: -4.4643; 2025-10-10: 1.7857; 2025-10-17: 4.4643
Foreland Eagle Springs | 5 | 1.25 | 0.09259% | 2025-09-12 | 2025-10-11 | CDU (5) | 5 kbd CDU down 9/12-10/11 | [14 empty] | OK | 2025-09-19: -1.25; 2025-10-17: 1.25
P66 Wood River | 2 | 56.45 | 2.352% | 2025-09-01 | 2025-10-15 | CDU (75), FCC (48), Coker (65) | Planned 2025 outage | [14 empty] | OK | 2025-09-05: -40.3214; 2025-09-12: -16.1286; 2025-10-17: 16.1286; 2025-10-24: 40.3214
Bradford Refinery | 1 | 3.07 | 0.6396% | 2025-09-12 | 2025-10-16 | CDU(12), Ref (2.2) | Planned T/A 9/12-10/16 | [14 empty] | OK | 2025-09-12: -0.43857; 2025-09-19: -2.6314; 2025-10-17: 0.43857; 2025-10-24: 2.6314
Marathon Carson | 5 | 67.6 | 5.007% | 2025-09-20 | 2025-10-20 | FCC (104) | 104 kbd FCC down 9/20-10/20 (previous timing 10/5-11/2) | [14 empty] | OK | 2025-09-26: -57.9429; 2025-10-03: -9.6571; 2025-10-24: 38.6286; 2025-10-31: 28.9714
Marathon Garyville | 3 | 36.25 | 0.788% | 2025-10-04 | 2025-10-24 | CDU 10A (145) | End date pulled up to 10/24 from 11/2 | [14 empty] | OK | 2025-10-10: -36.25; 2025-10-31: 36.25
Marathon Catlettsburg | 2 | 26.5 | 1.104% | 2025-09-12 | 2025-10-26 | CDU (95), Ref (20) | Planned outage 9/12 - 10/26 | [14 empty] | OK | 2025-09-12: -3.7857; 2025-09-19: -22.7143; 2025-10-31: 3.7857; 2025-11-07: 22.7143
Allegiance Refining San Antonio | 3 | 5.145 | 0.1118% | 2025-10-03 | 2025-10-26 | CDU (20), Ref (3.7) | Pushed to Sept from March per IIR | pushed from oct to sept | [13 empty] | OK | 2025-10-10: -5.145; 2025-10-31: 5.145
Shell Norco | 3 | 72.8 | 1.583% | 2025-09-08 | 2025-10-27 | FCC (112), Alky | Planned TA | [15 empty] | 2025-09-12: -41.6; 2025-09-19: -31.2; 2025-10-31: 52; 2025-11-07: 20.8
P66 Borger | 3 | 19.5 | 0.4239% | 2025-09-20 | 2025-10-28 | FCC(30) | FCC/HDT/Alky/SRU TA 9/20-10/28 | event ID 771893 | [13 empty] | OK | 2025-09-26: -19.5; 2025-10-31: 11.1429; 2025-11-07: 8.3571
Citgo Corpus Christi (East) | 3 | 23 | 0.5% | 2025-09-29 | 2025-10-29 | Coker (45), Ref (20), CDU (165) | T/A 9/29-10/29 | [14 empty] | OK | 2025-10-03: -13.1429; 2025-10-10: -9.8571; 2025-10-31: 9.8571; 2025-11-07: 13.1429
Silver Eagle Evanston | 4 | 2.89 | 0.85% | 2025-10-18 | 2025-10-31 | CDU(3.4),ref(3) | Planned 2025 maint | [14 empty] | OK | 2025-10-24: -2.89; 2025-11-07: 2.89
PBF Martinez | 5 | 60.5 | 4.481% | 2025-04-27 | 2025-11-01 | FCC (70), CDU (60) derate | Assuming down until 4Q per company statements; Added 60kbd crude cut | Crude cut/ Alky down | [8 empty] | -6.05 | -60.5 | -60.5 | -60.5 |  | OK | 2025-05-02: -43.2143; 2025-05-09: -17.2857; 2025-11-07: 51.8571; 2025-11-14: 8.6429
Irving St John | Canada | 40.5 | #N/A | 2025-09-01 | 2025-11-01 | CDU (150), ref (35) | Planned T/A
Cenovus Lima | 2 | 39.45 | 1.644% | 2025-09-19 | 2025-11-02 | FCC(40); assuming rate cuts CDU/Ref/Coker/HDC | planned outage per IIR 9/19/25-11/2/25. Removed Coker, HDC and Ref from TA (39kbd change) | [14 empty] | OK | 2025-09-19: -5.6357; 2025-09-26: -33.8143; 2025-11-07: 5.6357; 2025-11-14: 33.8143
Marathon Garyville | 3 | 8.625 | 0.1875% | 2025-10-04 | 2025-11-02 | Coker (34.5) | Planned TA | [14 empty] | OK | 2025-10-10: -8.625; 2025-11-07: 7.3929; 2025-11-14: 1.2321
Total Port Arthur | 3 | 49.25 | 1.071% | 2025-09-05 | 2025-11-03 | CDU (150), Ref (35), Alky (5) | Planned TA. ENT reporting start end of Aug | [15 empty] | 2025-09-12: -35.1786; 2025-09-19: -14.0714; 2025-11-14: 21.1071; 2025-11-21: 28.1429
Pemex Deer Park | 3 | 113.6 | 2.47% | 2025-10-03 | 2025-11-06 | CDU (270), Ref (75), Coker (92), FCC derate (21) | Planned T/A per IIR 10/3-11/6 | [15 empty] | 2025-10-03: -16.2286; 2025-10-10: -97.3714; 2025-11-07: 16.2286; 2025-11-14: 97.3714
Puget Sound | 5 | 31.25 | 2.315% | 2025-10-03 | 2025-11-11 | CDU (144), Coker(24), Ref (17) | Updated timing per IIR | [14 empty] | OK | 2025-10-03: -4.4643; 2025-10-10: -26.7857; 2025-11-14: 13.3929; 2025-11-21: 17.8571
Marathon Garyville | 3 | 36.25 | 0.788% | 2025-10-25 | 2025-11-14 | CDU 10B (145) | Planned TA | [14 empty] | OK | 2025-10-31: -36.25; 2025-11-21: 36.25
Hunt Tuscaloosa | 3 | 8 | 0.1739% | 2025-05-14 | 2025-11-15 | DC (32) | Planned T/A; expedited per IIR on 5/21. Extend to Nov per crude intel that they blew up their furnace | [10 empty] | -4.3871 | -8 | -8 |  |  | 2025-05-16: -2.2857; 2025-05-23: -5.7143; 2025-11-21: 8
Par Pacific Tacoma | 5 | 7.56 | 0.56% | 2025-10-31 | 2025-12-18 | CDU (42), Ref (8.4) | 42 kbd CDU down 10/31-12/18 | data source | [13 empty] | OK | 2025-11-07: -7.56; 2025-12-19: 1.08; 2025-12-26: 6.48
PBF Torrance | 5 | 2 | 0.1481% | 2025-11-27 | 2026-01-10 | Coker (8) | IIR T/A 11/27-1/10/26 | [15 empty] | 2025-11-28: -0.28571; 2025-12-05: -1.7143
Marathon Wilmington | 5 | 25.75 | 1.907% | 2026-01-01 | 2026-02-02 | CDU(103) | Pushed to 2026 per IIR | [14 empty] | Missing
Big West North Salt Lake | 4 | 7.475 | 2.199% | 2026-02-06 | 2026-03-07 | FCC(11.5) | Planned 2025 11.5 kbd FCC down 9/1-9/30. Moved to Feb/Mar '26 | [14 empty] | Missing
Citgo Lake Charles | 3 | 15 | 0.3261% | 2026-01-12 | 2026-03-13 | Delayed Coker (60) | Moved TA from Sep 2025 to Jan-Mar 2026 | [14 empty] | Missing
Delek Big Spring | 3 | 41.825 | 0.9092% | 2026-02-13 | 2026-03-25 | CDU (73), Ref (21), FCC(25) | Full Site T/A per IIR; QC date 7/24. Moved from Oct/Nov to Feb/Mar '26 | Excluding for now | [13 empty] | Missing
Puget Sound | 5 | 6 | 0.4444% | 2026-02-01 | 2026-03-30 | Coker(24) | Planned T/A per ENT
Citgo Lemont | 2 | 53.225 | 2.218% | 2026-03-20 | 2026-05-09 | FCC (58), Crude/Coker Derate | Pushed to Mar 20-May 9 2026 Per IIR vs Sep-Oct 2025 | [14 empty] | Missing
BP Whiting | 2 | 51.25 | 2.135% | 2026-09-05 | 2026-11-03 | CDU (90), FCC (65) | Planned pushed to 2026 vs Sep-Oct 2025 per IIR | [14 empty] | Missing
Chevron Salt Lake | 4 | 15.25 | 4.485% | 2026-10-17 | 2026-12-06 | FCC(13),Ref(8) | 8 kbd and 13kbd FCC reformer down 10/17-12/6. Moved to Oct/Nov '26 | [14 empty] | Missing
Lyondell Houston | 3 | 127.849 | 2.779% | 2025-01-24 | Permanent SD 2/24/25 | CDU (290), FCC (97), Coker (99), Ref (42) | Starting SD in January | [6 empty] | -28.8691 | -127.849 | -127.849 | -127.849 | -127.849 | -127.849 | -127.849 |  | OK | 2025-01-31: -20; 2025-02-07: -50; 2025-02-28: -58
PBF Torrance | 5 | 0 | 0% | removed | removed | CDU(155) | 155 kbd CDU down 5/2-6/10; removing per earnings call | X | [13 empty] | Missing
PBF Torrance | 5 | 6.25 | 0.463% | removed | removed | Coker(25) | Planned T/A 2/14-3/30- removing per earnings call | X | [13 empty] | Missing
P66 LA/Wilmington | 5 | 64.5 | 4.778% | 2025-10-01 | SD permanently | FCC/Ref/HDC | Permanent decomissioning in October | Moved to oct 2025 vs 24 | [13 empty] | OK | 2025-09-05: -32.25; 2025-10-03: -32.25
P66 Carson | 5 | 18.6 | 1.378% | 2025-10-01 | SD permanently | CDU/Coker | Permanent decomissioning in October | Moved to oct 2025 vs 24 | [13 empty] | OK | 2024-10-04: -5.3143; 2024-10-11: -3.9857; 2024-11-08: -9.3; 2025-09-05: -9.3; 2025-10-03: -9.3
| x |  |  | X | X | X |  |  | -518.5352 | -905.1734 | -815.41 | -696.6437 | -460.2605 | -689.2269 | -871.3363 | -931.764 | -1037.8529 | -699.3289 | -284.1657 | -286.575 |  | Missing
| x |  |  | X | X | X |  | CPL Origin Start HTN | [14 empty] | 2024-01-05: 72-1; 2024-01-12: 2; 2024-01-19: 3; 2024-01-26: 4-5; 2024-02-02: 6; 2024-02-09: 7-8; 2024-02-16: 9; 2024-02-23: 10; 2024-03-01: 11-12; 2024-03-08: 13; 2024-03-15: 14-15; 2024-03-22: 16; 2024-03-29: 17; 2024-04-05: 18; 2024-04-12: 13-20; 2024-04-19: 21-22; 2024-04-26: 23; 2024-05-03: 24
| x |  |  | X | X | X | 1 | Padd 1 production change | -24.5252 | 0 | -51.4556 | -2.2967 | -13.0645 | -45.9806 | -68.1068 | -116.04 | -34.5152 | -24.2202 | -38.5 | -30.82 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4.9214 | -86.6714 | 0 | 57.1429 | 0 | -11.6571 | -3.8857 | 45.0714 | 4.9214 | -29.4643 | 1.973 | -11.6071 | 5 | 6.6071 | 0 | 0 | -9.8429 | -4.9214 | 9.8429 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -34.7643 | -0.23571 | 10 | 10 | 15 | 0 | 0 | 0 | 0 | -20.8857 | 20.8857 | -9.8429 | 9.8429 | -17.5 | -17.75 | 8.0357 | 6.9643 | 1.7857 | -3.2786 | 10.4429 | -0.9 | 0 | 0.9 | 0 | -5.9714 | -14.9286 | 0 | -7.25 | 0.13571 | -14.5857 | -14.4486 | -90.1364 | 39.0164 | 6.1286 | 0 | 0 | 0 | -3.9482 | 60.1675 | 53.3457 | 0 | -4.1 | 5 | -5.5 | -33 | 25.9286 | -30.5571 | 11.2286 | 31 | -56.225 | 62.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.43857 | -2.6314 | 0 | 0 | 0 | 0.43857 | 2.6314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| x |  |  | X | X | X | 2 | Padd 2 produciton change | -4.4839 | -280.5819 | -110.8161 | -276.655 | -126.3581 | -47.4305 | -99.6125 | -210.3619 | -371.0731 | -244.7332 | -44.76 | -59.686 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -6.1714 | 6.1714 | -9.8571 | 2.8571 | -56.3036 | -194.875 | 176798.7 | -7.8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 57.4929 | -21.4536 | 23.7857 | 28.1464 | 103.2714 | 69.9107 | -1.275 | -31.275 | 0.61429 | 13.2143 | -3.6643 | -3.5714 | -93.6429 | -60.0286 | -43.6857 | 3.35 | 146.0388 | 77.7643 | 18.4714 | -35.7929 | -100.9869 | -80.0702 | -124.0207 | 8.3933 | 36.7667 | 11.7 | 4.125 | 62.2893 | 0.375 | -35.525 | 64.7286 | 161.7464 | 8.0679 | 1.2321 | -3.24 | 18.69 | -13.2714 | -7.5 | -9.8964 | -27.0336 | -23.8264 | -16.0507 | -50.3857 | 91.6143 | 0 | -28.3786 | -33.0307 | -124.2057 | -132.33 | -18.1 | 7.4318 | -30.9018 | 46.5186 | 19.7493 | 20.3764 | 115.6843 | -41.3707 | 42.7679 | 95.4036 | 56.2393 | 51.0271 | -9.3107 | -1.2014 | -13.9464 | -11.3971 | -5.3571 | 5.3571 | 1.0714 | 0 | 0 | 0 | -93.3571 | -35.6286 | -28.35 | -22.0286 | 29.4643 | 0 | 26.0929 | 80.1071 | 23.7857 | 28.35 | 33.8143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| x |  |  | X | X | X | 3 | Padd 3 produciton change | -409.61 | -453.7881 | -496.328 | -262.8671 | -189.1524 | -487.3607 | -537.594 | -386.376 | -335.2273 | -215.9835 | -94.06 | -125.695 |  |  | 0 | 13 | 0 | -4.8571 | 0 | -25.7486 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 170.1857 | 194589.3667 | #REF! | #REF! | #REF! | #REF! | -323232.4378 | 323445.8447 | 93.0005 | 7.2542 | #REF! | 56.1564 | 20.987 | 33.1964 | 81.9173 | #REF! | #REF! | -77.6185 | -31.3233 | 74.1504 | 62.1942 | 10.1429 | -173.9243 | -59.3714 | 56.1143 | 11.5917 | 28.2543 | 11.1808 | -18.2982 | -9.5 | -31.1429 | -89.051 | -4.3137 | -49.1386 | 41.8704 | -85.2211 | 7.0698 | -11.4648 | 46.3286 | 9.6057 | -31.1462 | 17.7212 | 125.9946 | 81.7 | 52.0786 | -39.5364 | 75.7069 | -33.3941 | -141.2486 | -220.1887 | -295.1187 | -4.1643 | -3.1879 | 20.8714 | 51.9436 | -43.4163 | 157.7529 | 138.9084 | 103.3215 | 0.35279 | -72.7218 | -41.75 | 71.7714 | 116.1071 | 23.4357 | 0.89143 | 0.58429 | -4.9 | -26.8429 | 91.3357 | -55.5693 | -34.1999 | 56.4579 | -79.7554 | 75.1071 | 18.5714 | -2.8 | 0 | 0 | 0 | 0 | 1.4 | -3.4929 | -81.9429 | -45.2714 | -19.5 | -29.3714 | -141.1771 | 10.1786 | 0 | 78.145 | 65.9214 | 119.7107 | 72.3929 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| x |  |  | X | X | X | 4 | Padd 4 produciton change | -3.3871 | -47.5276 | -58.4942 | -28.05 | -5.8855 | -0.94355 | -5.49 | -12.2305 | -40.0757 | -32.9819 | -4.232 | -4.237 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -29 | 22 | 0.96 | 10.9257 | -36.7343 | -18 | 7 | -6.6857 | 4.6667 | 6.4333 | #REF! | #REF! | -4.868 | 0 | 0 | #REF! | #REF! | 7.25 | 7.25 | -2.1125 | 2.1125 | 0 | 0 | 0 | 0 | 0 | -9.6571 | 0 | 9.6571 | -3 | 0 | 0 | 0 | 0 | -20.3 | 0 | -3.15 | 5.2929 | 3.7571 | 17.4 | -11.6929 | 4.3179 | 7.375 | 0 | 0 | -1.7143 | -1.2857 | -17.16 | 0 | 2.1171 | -3.4071 | 2.7857 | 11.9786 | 6.6857 | 0 | -0.21429 | -2.1557 | -8.7107 | 2.7857 | -0.32143 | -11.2143 | 4.5714 | 6.9643 | -10.7414 | -8.3579 | -18.5679 | -1.575 | -2.0921 | 0.95393 | 4.5386 | 4.4779 | 28.1164 | 11.6632 | 0 | -3.3514 | -5.0271 | -59.8286 | 63.1929 | 5.0143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2.89 | 0 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| x |  |  | X | X | X | 5 | Padd 5 produciton change | -76.529 | -123.2759 | -98.3161 | -103.9483 | -100.9484 | -107.5115 | -160.533 | -206.7556 | -256.9617 | -181.4102 | -102.6137 | -66.137 |  |  | 0 | 0 | 0 | -37.7 | -9.425 | 32.9875 | 14.1375 | -13.4357 | -17.9143 | 0 | 0 | -48.0214 | -25.6286 | -24.2857 | 24.2857 | -25 | -38 | -1.8464 | 25.9214 | 23.375 | 27.2417 | 7.5226 | 3.0167 | 10.5662 | #REF! | #REF! | -14.1143 | 2.0857 | 38.7571 | 16.7571 | 43.6714 | -23.8286 | -64.9029 | 44.3429 | 21 | 68.86 | 68.8143 | 4.2857 | 0 | 0 | -40.7 | -6.425 | 0 | 29.3446 | -24.8625 | -67.5429 | 4.4357 | -23.6705 | -60.183 | -7.2714 | 66.1188 | 3.8377 | 3.9514 | -31.7714 | 39.4286 | 34.9043 | 32.0486 | -39.6214 | -7.2964 | 31.0464 | 40.3214 | 2.95 | 0.96429 | -112.5686 | -39.8671 | -2.55 | -61.9821 | 25.7607 | 40.0679 | -2.7857 | 12.3179 | 38.5607 | -124.7 | -71.0143 | 14.9214 | -0.91429 | 55.5929 | -1.0357 | 106.3536 | -105.7771 | 52.6157 | 26.1821 | -11.0429 | 38.9464 | 45.0071 | 11.1686 | -11.2143 | 9.4286 | -5.6357 | 4.0429 | 0 | 0 | 8.3143 | 9.8857 | 0 | 0.85714 | -41.2071 | 0 | -1.25 | -57.9429 | -55.6714 | -26.7857 | 1.25 | 38.6286 | 28.9714 | 44.2971 | 22.0357 | 17.8571 | -0.28571 | -1.7143 | 0 | 1.08 | 4601706.48 | 4602400 | 4603100
| x |  |  | X | X | X |  | Overall Production change | [14 empty] | 2024-01-05: -11.0929; 2024-01-12: #REF!; 2024-01-19: #REF!; 2024-01-26: #REF!; 2024-02-02: #REF!; 2024-02-09: -1.135; 2024-02-16: 371322.4467; 2024-02-23: #REF!; 2024-03-01: #REF!; 2024-03-08: #REF!; 2024-03-15: #REF!; 2024-03-22: #REF!; 2024-03-29: #REF!; 2025-01-17: -330.6751; 2025-01-24: -362.5837; 2025-01-31: -30.405; 2025-02-07: -96.0207; 2025-02-14: -20.3579; 2025-02-21: 84.7786; 2025-02-28: -4.3999; 2025-03-07: 147.4993; 2025-03-14: 133.2241; 2025-03-21: -141.0128; 2025-03-28: -196.0272; 2025-04-04: -90.59; 2025-04-11: 16.5772; 2025-04-18: 131.2403; 2025-04-25: 160.015; 2025-05-02: 143.3464; 2025-05-09: -78.5554; 2025-05-16: 167.9229; 2025-05-23: -48.6107; 2025-05-30: 58.9271; 2025-06-06: 206.7918; 2025-06-13: 56.9057; 2025-06-20: 55.6444; 2025-06-27: -25.3193; 2025-07-04: -68.6568; 2025-07-11: 118.7179; 2025-07-18: 16.2314; 2025-07-25: -8.1571; 2025-08-01: 5.3571; 2025-08-08: 9.3857; 2025-08-15: 9.8857; 2025-08-22: 0; 2025-08-29: 2.2571; 2025-09-05: -138.0571; 2025-09-12: -118.01; 2025-09-19: -77.5029; 2025-09-26: -99.4714; 2025-10-03: -55.5786; 2025-10-10: -167.9629; 2025-10-17: 37.96; 2025-10-24: 118.4771; 2025-10-31: 130.9021; 2025-11-07: 141.4586; 2025-11-14: 175.5607; 2025-11-21: 90.25; 2025-11-28: -0.28571; 2025-12-05: -1.7143; 2025-12-12: 0; 2025-12-19: 1.08; 2025-12-26: 4601706.48; 2026-01-02: 4602400; 2026-01-09: 4603100
| x |  |  | X | X | X |  | Dec 12.25.2024 (achor) Production Projection | [14 empty] | 2023-11-03: Production by PADD
| x |  |  | X | X | X | 1 | 455 | [14 empty] | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 455 | 465 | 460.0786 | 373.4071 | 380 | 437.1429 | 430 | 410 | 395 | 400 | 409.9214 | 400.4571 | 395.4302 | 404.823 | 410.823 | 419.4302 | 414.4302 | 409.4302 | 387.5873 | 382.6659 | 392.5088 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 415 | 380.2357 | 380 | 390 | 400 | 415 | 415 | 415 | 425 | 415 | 404.1143 | 425 | 415.1571 | 425 | 407.5 | 389.75 | 404.7857 | 430.75 | 413.5357 | 409.2571 | 439.7 | 438.8 | 425.8 | 421.7 | 436.7 | 430.7286 | 427.8 | 427.8 | 420.55 | 420.6857 | 406.1 | 379.6514 | 286.515 | 323.5314 | 346.66 | 329.66 | 349.66 | 351.66 | 347.7118 | 407.8793 | 446.225 | 438.225 | 441.125 | 426.125 | 410.625 | 377.625 | 428.5536 | 387.9964 | 399.225 | 430.225 | 364 | 416.7 | 406.7 | 406.7 | 396.7 | 396.7 | 396.7 | 396.7 | 396.7 | 401.7 | 416.7 | 426.2614 | 428.63 | 428.63 | 428.63 | 428.63 | 429.0686 | 431.7 | 431.7 | 431.7 | 431.7 | 431.7 | 431.7 | 431.7 | 431.7 | 431.7 | 431.7 | 431.7 | 431.7
| x |  |  | X | X | X | 2 | 2295 | [14 empty] | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2295 | 2296 | 2289.8286 | 2247 | 2150 | 2191 | 2119.6964 | 1904.8214 | 1880 | 1890 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 2110 | 2158.7286 | 2300.475 | 2268.5429 | 2239.775 | 2246.535 | 2280.225 | 2256.9536 | 2249.4536 | 2274.5571 | 2212.5236 | 2188.6971 | 2182.6464 | 2132.2607 | 2223.875 | 2200.875 | 2172.4964 | 2139.4657 | 2077.26 | 1917.93 | 1884.83 | 1896.2618 | 1894.36 | 1910.8786 | 1936.6279 | 1957.0043 | 2072.6886 | 1991.3179 | 2034.0857 | 2092.4893 | 2148.7286 | 2154.7557 | 2105.445 | 2104.2436 | 2110.2971 | 2098.9 | 2093.5429 | 2098.9 | 2079.9714 | 2079.9714 | 2079.9714 | 2079.9714 | 2046.6143 | 2030.9857 | 2032.6357 | 2040.6071 | 2070.0714 | 2070.0714 | 2096.1643 | 2176.2714 | 2200.0571 | 2228.4071 | 2262.2214 | 2262.2214 | 2262.2214 | 2262.2214 | 2262.2214 | 2262.2214 | 2262.2214 | 2262.2214 | 2262.2214
| x |  |  | X | X | X | 3 | 4445 | [14 empty] | 4445 | 4458 | 4458 | 4440.1429 | 4445 | 4419.2514 | 4445 | 4435 | 4500 | 4500 | 4381 | #REF! | 3842 | #REF! | 3678 | 3750 | #REF! | #REF! | #REF! | #REF! | #REF! | 4156 | 4249.0005 | 4226.2546 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 4387 | 4355.6767 | 4429.8271 | 4407.0213 | 4417.1642 | 4250 | 4190.6286 | 4180.7429 | 4192.3345 | 4215.5888 | 4226.7696 | 4198.4714 | 4181.9714 | 4180.8286 | 4091.7776 | 4197 | 4187.8614 | 4299.7318 | 4144.5107 | 4271.5805 | 4234.1157 | 4330.4443 | 4340.05 | 4258.9038 | 4316.625 | 4442.6196 | 4524.3196 | 4496.3982 | 4456.8619 | 4525.5687 | 4492.1746 | 4390.9261 | 4240.7374 | 3995.6187 | 3991.4544 | 3938.2665 | 3859.138 | 3911.0815 | 3807.6653 | 3915.4181 | 4074.3265 | 4129.648 | 4130.0008 | 4057.279 | 3975.529 | 4047.3005 | 4176.4076 | 4244.8433 | 4245.7348 | 4246.319 | 4241.419 | 4194.5762 | 4255.9119 | 4200.3426 | 4166.1427 | 4222.6006 | 4142.8452 | 4217.9524 | 4206.5238 | 4203.7238 | 4199.7238 | 4205.7238 | 4203.7238 | 4208.7238 | 4204.1238 | 4220.631 | 4203.6881 | 4183.4167 | 4178.9167 | 4149.5452 | 4008.3681 | 4018.5467 | 4018.5467 | 4096.6917 | 4162.6131 | 4282.3238 | 4354.7167 | 4354.7167 | 4354.7167 | 4354.7167 | 4354.7167 | 4354.7167 | 4354.7167 | 4354.7167
| x |  |  | X | X | X | 4 | 267 | [14 empty] | 267 | 267 | 267 | 267 | 267 | 267 | 267 | 267 | 265 | 265 | 270 | 241 | 278 | 280.96 | 288 | 260 | 250 | 272 | 261.3143 | 270 | 282.4333 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 295 | 275.3429 | 275.3429 | 289 | 286 | 286 | 286 | 289 | 289 | 259.7 | 283.185 | 295.035 | 285.3279 | 289.085 | 303.485 | 291.7921 | 290.11 | 287.485 | 293.485 | 293.485 | 291.7707 | 305 | 287.84 | 287.84 | 269.9571 | 266.55 | 269.3357 | 281.3143 | 288 | 286 | 285.7857 | 285.63 | 276.9193 | 279.705 | 254.3836 | 232.1693 | 242.7407 | 265.705 | 269.9636 | 266.6057 | 237.0379 | 250.4629 | 263.3707 | 264.3246 | 268.8632 | 273.3411 | 301.4575 | 313.1207 | 313.1207 | 313.7693 | 308.7421 | 254.9136 | 311.1064 | 316.1207 | 316.1207 | 316.1207 | 316.1207 | 316.1207 | 316.1207 | 316.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 309.2307 | 309.2307 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207 | 312.1207
| x |  |  | X | X | X | 5 | 1229 | [14 empty] | 1229 | 1229 | 1229 | 1191.3 | 1219.575 | 1261.9875 | 1276.125 | 1229 | 1220 | 1220 | 1200 | 1230 | 1189.3714 | 1192.0857 | 1160 | 1107 | 1060 | 1058.1536 | 1110.075 | 1082.45 | 1082.6917 | 1090.2143 | 1084.231 | 1096.7971 | #REF! | #REF! | #REF! | #REF! | 1116 | 1085.7571 | 1120.4286 | 1116.6 | 1091.6971 | 1162.04 | 1178.04 | 1211.9 | 1225.7143 | 1225 | 1203 | 1195 | 1154.3 | 1147.875 | 1147.875 | 1177.2196 | 1167.3571 | 1109.8143 | 1134.25 | 1110.5795 | 1100.3964 | 1070.125 | 1106.2438 | 1115.0814 | 1174.0329 | 1172.2614 | 1161.69 | 1216.5943 | 1203.6429 | 1162.0214 | 1164.725 | 1195.7714 | 1186.0929 | 1179.0429 | 1180.0071 | 1077.4386 | 1037.5714 | 1035.0214 | 943.0393 | 968.8 | 1008.8679 | 971.0821 | 983.4 | 1061.9607 | 946.2607 | 875.2464 | 890.1679 | 889.2536 | 950.8464 | 989.8107 | 1096.1643 | 1020.3871 | 1073.0029 | 1099.185 | 1038.1421 | 1077.0886 | 1122.0957 | 1133.2643 | 1122.05 | 1116.4786 | 1110.8429 | 1114.8857 | 1114.8857 | 1114.8857 | 1128.2 | 1143.0857 | 1143.0857 | 1143.9429 | 1105.7357 | 1105.7357 | 1104.4857 | 1046.5429 | 990.8714 | 964.0857 | 965.3357 | 1003.9643 | 1032.9357 | 1077.2329 | 1099.2686 | 1117.1257 | 1116.84 | 1115.1257 | 1115.1257 | 1116.2057 | 4602822.6857 | 9205222.6857 | 13808322.6857
| x |  |  | X | X | X | [16 empty] | 2025-04-25: 7765.7848; 2025-05-02: 7982.1312; 2025-05-09: 7913.5758; 2025-05-16: 8071.4987; 2025-05-23: 7982.888; 2025-05-30: 7996.8151; 2025-06-06: 8126.6069; 2025-06-13: 8183.5126; 2025-06-20: 8198.157; 2025-06-27: 8122.8377; 2025-07-04: 8035.181
| x |  |  | X | X | X |  | Production Adjustments | [14 empty] | 2024-08-16: 1575
| x |  |  | X | X | X | 1 | 1 | [14 empty] | 2024-11-15: -19; 2024-12-06: 0; 2025-02-14: -12; 2025-02-21: -3; 2025-02-28: -2; 2025-03-07: 17; 2025-03-14: -17; 2025-03-21: 20; 2025-03-28: 2; 2025-04-18: -15; 2025-04-25: -8; 2025-05-02: 7; 2025-05-09: -20; 2025-05-16: -10; 2025-05-23: 0; 2025-05-30: 25; 2025-06-06: -10; 2025-06-27: -10; 2025-07-04: -10; 2025-07-11: -10; 2025-07-25: -10; 2025-08-29: 5; 2025-09-05: 15; 2025-09-12: 10; 2025-09-19: 5
| x |  |  | X | X | X | 2 | 2 | [14 empty] | 2024-11-29: -40; 2024-12-06: -20; 2024-12-13: -30; 2024-12-20: 10; 2024-12-27: 15; 2025-01-03: -10; 2025-01-17: 35; 2025-01-24: -35; 2025-02-07: 10; 2025-02-14: 0; 2025-02-21: 0; 2025-02-28: -23; 2025-03-07: 0; 2025-03-21: 62; 2025-03-28: -27; 2025-04-04: -15; 2025-04-11: 4; 2025-04-18: 29; 2025-04-25: -30; 2025-05-02: 6; 2025-05-23: -40; 2025-06-06: -37; 2025-06-20: -45; 2025-06-27: -40; 2025-07-11: 20; 2025-08-08: -20; 2025-09-05: 60; 2025-09-12: 20; 2025-09-19: 30; 2025-09-26: 30
| x |  |  | X | X | X | 3 | 3 | [14 empty] | 2024-11-22: 40; 2024-12-13: -80; 2024-12-20: 0; 2024-12-27: 0; 2025-01-10: 40; 2025-01-17: 70; 2025-01-24: 50; 2025-01-31: 0; 2025-02-07: -50; 2025-02-14: -100; 2025-02-21: 0; 2025-02-28: -60; 2025-03-07: -50; 2025-03-14: 20; 2025-03-21: -48; 2025-04-11: -40; 2025-04-25: 13; 2025-05-02: 45; 2025-05-30: -20; 2025-06-06: -30; 2025-07-18: -30; 2025-08-01: -4; 2025-08-08: 6; 2025-08-15: -2; 2025-08-22: 5; 2025-08-29: -6; 2025-09-05: 20; 2025-09-12: 65; 2025-09-19: 25; 2025-09-26: 15
| x |  |  | X | X | X | 4 | 4 | [14 empty] | 2025-01-31: -2; 2025-02-14: 2; 2025-02-21: 0; 2025-03-07: -25; 2025-03-14: -11; 2025-03-21: 6; 2025-03-28: 16; 2025-04-04: 15; 2025-04-11: 5; 2025-04-18: -11; 2025-04-25: 15; 2025-05-02: 15; 2025-06-20: 4; 2025-07-04: 6; 2025-07-11: -7; 2025-09-05: -4
| x |  |  | X | X | X | 5 | 5 | [14 empty] | 2024-11-08: 30; 2024-11-15: -50; 2024-11-22: 20; 2024-11-29: -45; 2024-12-06: -2; 2024-12-13: 10; 2024-12-20: 0; 2024-12-27: -50; 2025-01-03: -10; 2025-01-17: 10; 2025-01-24: 0; 2025-01-31: 0; 2025-02-07: -30; 2025-02-14: 0; 2025-02-28: -35; 2025-03-07: 0; 2025-03-14: 40; 2025-03-21: 9; 2025-03-28: 0; 2025-04-18: 6; 2025-04-25: 40; 2025-05-09: 30; 2025-05-30: -50; 2025-07-04: -15; 2025-08-08: 5; 2025-08-15: 5; 2025-09-05: 3
| x |  |  | X | X | X | Overall | Overall | [14 empty] | 2025-01-17: 115; 2025-01-24: 15; 2025-01-31: -2; 2025-02-07: -70; 2025-02-14: -110; 2025-02-21: -3; 2025-02-28: -120; 2025-03-07: -58; 2025-03-14: 32; 2025-03-21: 49; 2025-03-28: -44; 2025-04-04: 0; 2025-04-11: -31; 2025-04-18: 9; 2025-04-25: 0; 2025-05-02: 73; 2025-05-09: 10; 2025-05-16: -10; 2025-05-23: -40; 2025-05-30: -45; 2025-06-06: -77; 2025-06-13: 0; 2025-06-20: -41; 2025-06-27: -50; 2025-07-04: -19
| x |  |  | X | X | X
| x |  |  | X | X | X |  | w/w change with adjustments | [14 empty] | 2023-12-01: 8681.575; 2023-12-08: 8698.2389; 2023-12-15: 8738.125; 2023-12-22: 8681; 2023-12-29: 8746
| x |  |  | X | X | X |  | 1 | [14 empty] | 2023-12-08: 16.6639; 2023-12-15: 39.8861; 2023-12-22: -57.125; 2023-12-29: 65; 2024-04-05: forecasting P3 runs to be 8.91 MBD for week of 5/4 - 5/10; 2025-01-24: -7.25; 2025-01-31: 0.13571; 2025-02-07: -14.5857; 2025-02-14: -26.4486; 2025-02-21: -93.1364; 2025-02-28: 37.0164; 2025-03-07: 23.1286; 2025-03-14: -17; 2025-03-21: 20; 2025-03-28: 2; 2025-04-04: -3.9482; 2025-04-11: 60.1675; 2025-04-18: 38.3457; 2025-04-25: -8; 2025-05-02: 2.9; 2025-05-09: -15; 2025-05-16: -15.5; 2025-05-23: -33; 2025-05-30: 50.9286; 2025-06-06: -40.5571; 2025-06-13: 11.2286; 2025-06-20: 31; 2025-06-27: -66.225; 2025-07-04: 52.7
| x |  |  | X | X | X |  | 2 | [14 empty] | 2025-01-24: -62.0336; 2025-01-31: -23.8264; 2025-02-07: -6.0507; 2025-02-14: -50.3857; 2025-02-21: 91.6143; 2025-02-28: -23; 2025-03-07: -28.3786; 2025-03-14: -33.0307; 2025-03-21: -62.2057; 2025-03-28: -159.33; 2025-04-04: -33.1; 2025-04-11: 11.4318; 2025-04-18: -1.9018; 2025-04-25: 16.5186; 2025-05-02: 25.7493; 2025-05-09: 20.3764; 2025-05-16: 115.6843; 2025-05-23: -81.3707; 2025-05-30: 42.7679; 2025-06-06: 58.4036; 2025-06-13: 56.2393; 2025-06-20: 6.0271; 2025-06-27: -49.3107; 2025-07-04: -1.2014
| x |  |  | X | X | X |  | 3 | [14 empty] | 2023-12-01: 4545; 2023-12-08: 4554.2514; 2023-12-15: 4580; 2023-12-22: 4570; 2025-01-24: -245.1187; 2025-01-31: -4.1643; 2025-02-07: -53.1879; 2025-02-14: -79.1286; 2025-02-21: 51.9436; 2025-02-28: -103.4163; 2025-03-07: 107.7529; 2025-03-14: 158.9084; 2025-03-21: 55.3215; 2025-03-28: 0.35279; 2025-04-04: -72.7218; 2025-04-11: -81.75; 2025-04-18: 71.7714; 2025-04-25: 129.1071; 2025-05-02: 68.4357; 2025-05-09: 0.89143; 2025-05-16: 0.58429; 2025-05-23: -4.9; 2025-05-30: -46.8429; 2025-06-06: 61.3357; 2025-06-13: -55.5693; 2025-06-20: -34.1999; 2025-06-27: 56.4579; 2025-07-04: -79.7554
| x |  |  | X | X | X |  | 4 | [14 empty] | 2025-01-24: 6.6857; 2025-01-31: -2; 2025-02-07: -0.21429; 2025-02-14: -0.15571; 2025-02-21: -8.7107; 2025-02-28: 2.7857; 2025-03-07: -25.3214; 2025-03-14: -22.2143; 2025-03-21: 10.5714; 2025-03-28: 22.9643; 2025-04-04: 4.2586; 2025-04-11: -3.3579; 2025-04-18: -29.5679; 2025-04-25: 13.425; 2025-05-02: 12.9079; 2025-05-09: 0.95393; 2025-05-16: 4.5386; 2025-05-23: 4.4779; 2025-05-30: 28.1164; 2025-06-06: 11.6632; 2025-06-13: 0; 2025-06-20: 0.64857; 2025-06-27: -5.0271; 2025-07-04: -53.8286
| x |  |  | X | X | X |  | 5 | [14 empty] | 2025-01-24: -39.8671; 2025-01-31: -2.55; 2025-02-07: -91.9821; 2025-02-14: 25.7607; 2025-02-21: 40.0679; 2025-02-28: -37.7857; 2025-03-07: 12.3179; 2025-03-14: 78.5607; 2025-03-21: -115.7; 2025-03-28: -71.0143; 2025-04-04: 14.9214; 2025-04-11: -0.91429; 2025-04-18: 61.5929; 2025-04-25: 38.9643; 2025-05-02: 106.3536; 2025-05-09: -75.7771; 2025-05-16: 52.6157; 2025-05-23: 26.1821; 2025-05-30: -61.0429; 2025-06-06: 38.9464; 2025-06-13: 45.0071; 2025-06-20: 11.1686; 2025-06-27: -11.2143; 2025-07-04: -5.5714
| x |  |  | X | X | X |  | Overall | [14 empty] | 2025-01-24: -347.5837; 2025-01-31: -32.405; 2025-02-07: -166.0207; 2025-02-14: -130.3579; 2025-02-21: 81.7786; 2025-02-28: -124.3999; 2025-03-07: 89.4993; 2025-03-14: 165.2241; 2025-03-21: -92.0128; 2025-03-28: -205.0272; 2025-04-04: -90.59; 2025-04-11: -14.4228; 2025-04-18: 140.2403; 2025-04-25: 190.015; 2025-05-02: 216.3464; 2025-05-09: -68.5554; 2025-05-16: 157.9229; 2025-05-23: -88.6107; 2025-05-30: 13.9271; 2025-06-06: 129.7918; 2025-06-13: 56.9057; 2025-06-20: 14.6444; 2025-06-27: -75.3193; 2025-07-04: -87.6568
| x |  |  | X | X | X | [16 empty] | 2024-03-08: 2010; 2024-03-15: 1982; 2024-03-22: 1965; 2024-03-29: 1967
| x |  |  | X | X | X
| x |  |  | X | X | X
|  |  | #N/A | [18 empty] | Missing
[32 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[106 empty] | -1.5 | 1.5
|  | PADD | Winter | Summer
|  | 1 | 480 | 450
|  | 2 | 2400 | 2180
|  | 3 | 4600 | 4380
|  | 4 | 340 | 315
|  | 5 | 1350 | 1300
- P3 last two weeks, decreases w/w have only been 60-75% of expectations
Note on AQ81: Metcalf, Patrick: This is for Secondary units being back up
Note on AR81: Metcalf, Patrick: This is for the CDU (250 kbd) coming back up
Note on AS81: Metcalf, Patrick: This is for Secondary units being back up
Note on AT81: Metcalf, Patrick: This is for the CDU (250 kbd) coming back up
Note on BC177: Arango Castaneda, Erika L: seeing half of the production offline this week
Note on I819: James E Hathorn, III: whats this?
Note on CS821: James E Hathorn, III: Confirm Cenovus Toledo assumption for early TA start
Note on I826: Arango Castaneda, Erika L: Need to update references so that it pull in latest week's EIA. Use CtrlF
Note on Y826: Arango Castaneda, Erika L: Goal Seek these numbers in gasoline balances
Note on AG827: Arango Castaneda, Erika L: from 455
Note on AI827: Arango Castaneda, Erika L: EIA reported 371. Anchoring to our number and taking the w/w changes
Note on BA827: Metcalf, Patrick: Originally had 413 as our number. 406 was EIA reported. Going with reported
Note on I828: Metcalf, Patrick: 4 wk avg from wk ending 12/1 through wk ending 12/22. Past 2 weeks production have been record setting
Note on AG828: Arango Castaneda, Erika L: from 2276
Note on BA828: Metcalf, Patrick: Previously had 33 kbd of Ardmore coming up w/e 5/17 and 13 coming up w/e 5/24. Now have 13 kbd coming up w/e 5/17 and 33 kbd w/e 5/24
Note on BR828: Arango Castaneda, Erika L: butane blending
Note on BA829: Metcalf, Patrick: Originally had 4404. Moved BMT Reformer to back up to full rates w/e3 5/17 vs. spread over the 2 weeks . EIA reported was 4454
Note on I830: Metcalf, Patrick: 267 was the actual for week ending 12/22. Using as anchor
Note on BA830: Metcalf, Patrick: Keeping 295 kbd as anchor. EIA reported 245 kbd which does not feel real
Note on I831: Metcalf, Patrick: 3 wk avg production (wks ending 12/8 through 12/22)
Note on CA834: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Undoing last week’s adjustment
Note on CD834: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added 10 based on expected increase in production
Note on CQ834: James E Hathorn, III: higher yeild assumption
Note on CC835: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Matching EIA data- folks may be marginally sparing due to margins being under pressure
Note on CD836: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Softening ramp based on several outages and uncertainty of startup
Note on CE836: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reliability factor since no outages currently planned Reply: Pulled forward one week Reply: Added 40 kbd reliability factor to keep yields below 50% (historical)
Note on CH836: Metcalf, Patrick: For Lyondell
Note on BZ838: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added 30 because missed low by 60 but don’t want to come all the way up
Note on CA838: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Suspected production issues/come off from last week’s addition
Note on CB838: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 year band solver
Note on CC838: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5 year band
Note on CD838: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Reliability adder
Note on CP838: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Possibly missing some offline capacity

## Offlline Gas by month from Raw (hidden)
Sum of Gasoline Production Offline (KBD) | Column Labels
| <1/1/2024 | <1/1/2024 Total | 2024 | [11 empty] | 2024 Total | 2025 | [11 empty] | 2025 Total | 2026 | [11 empty] | 2026 Total
Row Labels | <1/1/2024 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 |  |  |  | 0 | 44.8533 | 29.0467 | 8.1613 | 0 |  |  | 34.45 | 16.6694 | 2.3333 |  | 135.514 | 0.61935 | 25.4812 | 32.8427 | 6.5983 | 5.575 | 12.3258 |  |  | 1.842 | 1.5845 |  |  | 86.869 |  |  |  | 32.3 | [8 empty] | 32.3
2 |  |  |  | 13.6 | 134.0994 | 343.4723 | 148.0973 |  | 3.9167 | 0 | 212.3433 | 347.7645 | 43.5617 |  | 1246.8552 | 8.6371 | 36.4554 | 280.1621 | 383.5415 | 110.8806 | 45.25 | 36.1935 | 42.25 | 177.5983 | 105.9637 | 4.2933 |  | 1231.2257 |  | 146.7214 | 155.9282 | 148.9717 | 23.0298 |  |  |  | 10.7917 | 64.75 | 6.475 |  | 556.6678
3 |  |  | 343.1177 | 604.0628 | 235.2453 | 78.8083 | 22.755 | 59.1567 | 56.4597 | 107.7579 | 178.73 | 290.5279 | 76.9545 |  | 2053.5758 | 288.6903 | 293.5411 | 222.9802 | 147.2267 | 34.5559 | 17.9333 | 1.8581 |  | 195.6053 | 321.9581 | 40.3383 |  | 1564.6873 | 246.1153 | 386.8268 | 206.4347 | 38.3858 | 9.9395 | 2.75 | 0.91935 | 1.1 |  |  |  |  | 892.4715
4 |  |  |  | 38.1455 | 42.191 | 16.0067 | 5.6667 |  |  | 3 | 12.7213 | 3.162 | 0 |  | 120.8932 | 10.71 | 17.8157 | 8.1952 | 25.1667 | 9.5727 |  |  |  | 5.0583 | 3.8506 |  | 2.9516 | 83.3209 |  | 18.75 | 75.5898 | 64.991 | 3.0142 |  |  |  |  | 6.8871 | 15.25 | 2.9516 | 187.4338
5 |  |  | 33.1887 | 51.1034 | 71.5433 | 105.2433 | 161.9584 | 48.1733 |  | 21.429 | 4.95 | 4.0806 |  | 6.4581 | 508.1283 | 38.5258 | 67.8286 | 180.2065 | 109.6483 | 72.7323 |  | 14.4839 | 2.5742 | 82.6033 | 167.3852 | 149.92 | 93.5745 | 979.4825 | 25.9097 | 8.3725 | 11.34 | 118.5393 | 129.5341 | 117.5567 | 103.05 | 103.05 | 103.05 | 103.05 | 103.05 | 103.05 | 1029.5523
(blank)
Grand Total |  |  | 376.3065 | 706.9118 | 527.9323 | 572.5773 | 346.6386 | 107.33 | 60.3763 | 132.1869 | 443.1947 | 662.2044 | 122.8495 | 6.4581 | 4064.9664 | 347.1826 | 441.122 | 724.3867 | 672.1815 | 233.3165 | 75.5092 | 52.5355 | 44.8242 | 462.7073 | 600.7421 | 194.5517 | 96.5261 | 3945.5854 | 272.025 | 560.6707 | 449.2927 | 403.1879 | 165.5176 | 120.3067 | 103.9694 | 104.15 | 113.8417 | 174.6871 | 124.775 | 106.0016 | 2698.4253
US
Sum of Gasoline Production Offline (KBD) | Column Labels
Row Labels | <1/1/2024 | 2024 | 2024 Jan: 2025; 2024 Feb: 2026; 2024 Mar: Grand Total
<1/1/2024
Jan |  | 376.3065 | 2024 Jan: 347.1826; 2024 Feb: 272.025; 2024 Mar: 995.514
Feb |  | 706.9118 | 2024 Jan: 441.122; 2024 Feb: 560.6707; 2024 Mar: 1708.7044
Mar |  | 527.9323 | 2024 Jan: 724.3867; 2024 Feb: 449.2927; 2024 Mar: 1701.6118
Apr |  | 572.5773 | 2024 Jan: 672.1815; 2024 Feb: 403.1879; 2024 Mar: 1647.9467
May |  | 346.6386 | 2024 Jan: 233.3165; 2024 Feb: 165.5176; 2024 Mar: 745.4728
Jun |  | 107.33 | 2024 Jan: 75.5092; 2024 Feb: 120.3067; 2024 Mar: 303.1458
Jul |  | 60.3763 | 2024 Jan: 52.5355; 2024 Feb: 103.9694; 2024 Mar: 216.8812
Aug |  | 132.1869 | 2024 Jan: 44.8242; 2024 Feb: 104.15; 2024 Mar: 281.1611
Sep |  | 443.1947 | 2024 Jan: 462.7073; 2024 Feb: 113.8417; 2024 Mar: 1019.7437
Oct |  | 662.2044 | 2024 Jan: 600.7421; 2024 Feb: 174.6871; 2024 Mar: 1437.6336
Nov |  | 122.8495 | 2024 Jan: 194.5517; 2024 Feb: 124.775; 2024 Mar: 442.1762
Dec |  | 6.4581 | 2024 Jan: 96.5261; 2024 Feb: 106.0016; 2024 Mar: 208.9858
Grand Total |  | 4064.9664 | 2024 Jan: 3945.5854; 2024 Feb: 2698.4253; 2024 Mar: 10708.9772
PADD | 1
Sum of Gasoline Production Offline (KBD) | Column Labels
Row Labels | 2024 | 2025 | 2024 Jan: 2026; 2024 Feb: Grand Total
Jan |  | 0.61935 | 2024 Feb: 0.61935
Feb | 0 | 25.4812 | 2024 Feb: 25.4812
Mar | 44.8533 | 32.8427 | 2024 Feb: 77.6961
Apr | 29.0467 | 6.5983 | 2024 Jan: 32.3; 2024 Feb: 67.945
May | 8.1613 | 5.575 | 2024 Feb: 13.7363
Jun | 0 | 12.3258 | 2024 Feb: 12.3258
Sep | 34.45 | 1.842 | 2024 Feb: 36.292
Oct | 16.6694 | 1.5845 | 2024 Feb: 18.2539
Nov | 2.3333 |  | 2024 Feb: 2.3333
Grand Total | 135.514 | 86.869 | 2024 Jan: 32.3; 2024 Feb: 254.683
PADD | 2
Sum of Gasoline Production Offline (KBD) | Column Labels
Row Labels | 2024 | 2025 | 2024 Jan: 2026; 2024 Feb: Grand Total
Jan |  | 8.6371 | 2024 Feb: 8.6371
Feb | 13.6 | 36.4554 | 2024 Jan: 146.7214; 2024 Feb: 196.7768
Mar | 134.0994 | 280.1621 | 2024 Jan: 155.9282; 2024 Feb: 570.1898
Apr | 343.4723 | 383.5415 | 2024 Jan: 148.9717; 2024 Feb: 875.9855
May | 148.0973 | 110.8806 | 2024 Jan: 23.0298; 2024 Feb: 282.0077
Jun |  | 45.25 | 2024 Feb: 45.25
Jul | 3.9167 | 36.1935 | 2024 Feb: 40.1102
Aug | 0 | 42.25 | 2024 Feb: 42.25
Sep | 212.3433 | 177.5983 | 2024 Jan: 10.7917; 2024 Feb: 400.7333
Oct | 347.7645 | 105.9637 | 2024 Jan: 64.75; 2024 Feb: 518.4782
Nov | 43.5617 | 4.2933 | 2024 Jan: 6.475; 2024 Feb: 54.33
Grand Total | 1246.8552 | 1231.2257 | 2024 Jan: 556.6678; 2024 Feb: 3034.7487
PADD | 3
Sum of Gasoline Production Offline (KBD) | Column Labels
Row Labels | 2024 | 2025 | 2024 Jan: 2026; 2024 Feb: Grand Total
Jan | 343.1177 | 288.6903 | 2024 Jan: 246.1153; 2024 Feb: 877.9234
Feb | 604.0628 | 293.5411 | 2024 Jan: 386.8268; 2024 Feb: 1284.4307
Mar | 235.2453 | 222.9802 | 2024 Jan: 206.4347; 2024 Feb: 664.6602
Apr | 78.8083 | 147.2267 | 2024 Jan: 38.3858; 2024 Feb: 264.4208
May | 22.755 | 34.5559 | 2024 Jan: 9.9395; 2024 Feb: 67.2504
Jun | 59.1567 | 17.9333 | 2024 Jan: 2.75; 2024 Feb: 79.84
Jul | 56.4597 | 1.8581 | 2024 Jan: 0.91935; 2024 Feb: 59.2371
Aug | 107.7579 |  | 2024 Jan: 1.1; 2024 Feb: 108.8579
Sep | 178.73 | 195.6053 | 2024 Feb: 374.3353
Oct | 290.5279 | 321.9581 | 2024 Feb: 612.486
Nov | 76.9545 | 40.3383 | 2024 Feb: 117.2928
Grand Total | 2053.5758 | 1564.6873 | 2024 Jan: 892.4715; 2024 Feb: 4510.7346
PADD | 4
Sum of Gasoline Production Offline (KBD) | Column Labels
Row Labels | 2024 | 2025 | 2024 Jan: 2026; 2024 Feb: Grand Total
Jan |  | 10.71 | 2024 Feb: 10.71
Feb | 38.1455 | 17.8157 | 2024 Jan: 18.75; 2024 Feb: 74.7112
Mar | 42.191 | 8.1952 | 2024 Jan: 75.5898; 2024 Feb: 125.976
Apr | 16.0067 | 25.1667 | 2024 Jan: 64.991; 2024 Feb: 106.1644
May | 5.6667 | 9.5727 | 2024 Jan: 3.0142; 2024 Feb: 18.2536
Aug | 3 |  | 2024 Feb: 3
Sep | 12.7213 | 5.0583 | 2024 Feb: 17.7797
Oct | 3.162 | 3.8506 | 2024 Jan: 6.8871; 2024 Feb: 13.8997
Nov | 0 |  | 2024 Jan: 15.25; 2024 Feb: 15.25
Dec |  | 2.9516 | 2024 Jan: 2.9516; 2024 Feb: 5.9032
Grand Total | 120.8932 | 83.3209 | 2024 Jan: 187.4338; 2024 Feb: 391.6478
PADD | 3
Sum of Gasoline Production Offline (KBD) | Column Labels
| 2026 |  | 2024 Sep: 2026 Total; 2024 Oct: Grand Total
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Oct | Nov
Alky | 2026 Jan: 0; 2026 Feb: 0; 2026 Mar: 0; 2026 Apr: 0; 2026 May: 0 | 0 | 0
BIG SPRINGS - ALON | 2026 Feb: 0; 2026 Mar: 0 | 0 | 0
EL DORADO REFINERY (DELEK) | 2026 Feb: 0; 2026 Mar: 0; 2026 Apr: 0 | 0 | 0
HOUSTON REFINERY (VALERO) | 2026 Jan: 0; 2026 Feb: 0 | 0 | 0
MARATHON PETROLEUM - TEXAS CITY (GALVESTON BAY) | 2026 Jan: 0; 2026 Feb: 0 | 0 | 0
PORT ALLEN REFINERY | 2026 Apr: 0; 2026 May: 0 | 0 | 0
CCU | 2026 Jan: 124.8629; 2026 Feb: 103.6518; 2026 Mar: 36.1694; 2026 Apr: 14.6142; 2026 May: 3.4492 | 282.7474 | 282.7474
BIG SPRINGS - ALON | 2026 Feb: 8.7054; 2026 Mar: 13.1048 | 21.8102 | 21.8102
EL DORADO REFINERY (DELEK) | 2026 Feb: 12.0714; 2026 Mar: 13; 2026 Apr: 0.86667 | 25.9381 | 25.9381
EXXON - BATON ROUGE | 2026 Jan: 0; 2026 Feb: 0; 2026 Mar: 0 | 0 | 0
Galveston Bay Refinery (GBR) | 2026 Jan: 79.2581; 2026 Feb: 22.75 | 102.0081 | 102.0081
HOUSTON REFINERY (VALERO) | 2026 Jan: 20.4435; 2026 Feb: 21.125 | 41.5685 | 41.5685
MARATHON PETROLEUM - TEXAS CITY (GALVESTON BAY) | 2026 Jan: 25.1613; 2026 Feb: 39; 2026 Mar: 10.0645 | 74.2258 | 74.2258
PORT ALLEN REFINERY | 2026 Apr: 13.7475; 2026 May: 3.4492 | 17.1967 | 17.1967
CDU | 2026 Jan: 100.879; 2026 Feb: 184.1429; 2026 Mar: 113.625; 2026 Apr: 14.45; 2026 May: 1.8065 | 414.9033 | 414.9033
BIG SPRINGS - ALON | 2026 Feb: 3.9107; 2026 Mar: 5.8871 | 9.7978 | 9.7978
EL DORADO REFINERY (DELEK) | 2026 Feb: 7.4286; 2026 Mar: 8; 2026 Apr: 0.53333 | 15.9619 | 15.9619
EXXON - BATON ROUGE | 2026 Jan: 0; 2026 Feb: 0; 2026 Mar: 0 | 0 | 0
EXXONMOBIL - BAYTOWN | 2026 Jan: 4.3548; 2026 Feb: 27; 2026 Mar: 1.7419 | 33.0968 | 33.0968
EXXONMOBIL - BEAUMONT | 2026 Feb: 22.5; 2026 Mar: 34.8387 | 57.3387 | 57.3387
Galveston Bay Refinery (GBR) | 2026 Jan: 23.0806; 2026 Feb: 6.625 | 29.7056 | 29.7056
Lake Charles Refinery (Calcasieu) | 2026 Jan: 20.9677 | 20.9677 | 20.9677
Lake Charles Refinery (CITGO) | 2026 Feb: 38.75 | 38.75 | 38.75
MARATHON - GARYVILLE | 2026 Jan: 46.5726 | 46.5726 | 46.5726
MARATHON PETROLEUM - TEXAS CITY (GALVESTON BAY) | 2026 Jan: 5.4839; 2026 Feb: 8.5; 2026 Mar: 2.1935 | 16.1774 | 16.1774
Mobile Refinery (Vertex) | 2026 Feb: 2.7143; 2026 Mar: 1.9355 | 4.6498 | 4.6498
PORT ALLEN REFINERY | 2026 Apr: 7.2; 2026 May: 1.8065 | 9.0065 | 9.0065
Princeton Refinery | 2026 Jan: 0.41935 | 0.41935 | 0.41935
Sandersville Refinery | 2026 Feb: 1.9643; 2026 Mar: 0.080645 | 2.0449 | 2.0449
Smackover Refinery | 2026 Mar: 0.62097; 2026 Apr: 0.46667 | 1.0876 | 1.0876
Texas City Refinery | 2026 Feb: 31.25; 2026 Mar: 31.25; 2026 Apr: 6.25 | 68.75 | 68.75
VALERO - THREE RIVERS | 2026 Feb: 11.5357; 2026 Mar: 13.0242 | 24.5599 | 24.5599
Valero Corpus Christi West - Bill Greehey Refinery - West | 2026 Feb: 21.9643; 2026 Mar: 14.0524 | 36.0167 | 36.0167
Coker | 2026 Jan: 11.2702; 2026 Feb: 27.875; 2026 Mar: 7.121 | 46.2661 | 46.2661
EXXONMOBIL - BAYTOWN | 2026 Jan: 2.0766; 2026 Feb: 12.875; 2026 Mar: 0.83065 | 15.7823 | 15.7823
Lake Charles Refinery (CITGO) | 2026 Jan: 9.1935; 2026 Feb: 15; 2026 Mar: 6.2903 | 30.4839 | 30.4839
HDC | 2026 May: 2.5726; 2026 Jun: 2.75; 2026 Jul: 0.91935; 2026 Aug: 1.1 | 7.3419 | 7.3419
McKee Refinery | 2026 Jul: 0.91935; 2026 Aug: 1.1 | 2.0194 | 2.0194
Meraux Refinery | 2026 May: 2.5726; 2026 Jun: 2.75 | 5.3226 | 5.3226
HDS | 2026 Feb: 0; 2026 Mar: 0; 2026 Apr: 0 | 0 | 0
Texas City Refinery | 2026 Feb: 0; 2026 Mar: 0; 2026 Apr: 0 | 0 | 0
Reformer | 2026 Jan: 9.1032; 2026 Feb: 71.1571; 2026 Mar: 49.5194; 2026 Apr: 9.3217; 2026 May: 2.1113 | 141.2127 | 141.2127
BIG SPRINGS - ALON | 2026 Feb: 9.5625; 2026 Mar: 14.3952 | 23.9577 | 23.9577
EL DORADO REFINERY (DELEK) | 2026 Feb: 12.6286; 2026 Mar: 13.6; 2026 Apr: 0.90667 | 27.1352 | 27.1352
EXXON - BATON ROUGE | 2026 Jan: 0; 2026 Feb: 0; 2026 Mar: 0 | 0 | 0
MARATHON PETROLEUM - TEXAS CITY (GALVESTON BAY) | 2026 Jan: 5.4839; 2026 Feb: 8.5; 2026 Mar: 2.1935 | 16.1774 | 16.1774
Mobile Refinery (Vertex) | 2026 Feb: 4.0375; 2026 Mar: 2.879 | 6.9165 | 6.9165
Norco Refinery | 2026 Feb: 29.1429; 2026 Mar: 16.4516 | 45.5945 | 45.5945
PORT ALLEN REFINERY | 2026 Apr: 8.415; 2026 May: 2.1113 | 10.5263 | 10.5263
Princeton Refinery | 2026 Jan: 1.4258 | 1.4258 | 1.4258
VALERO - THREE RIVERS | 2026 Jan: 2.1935; 2026 Feb: 7.2857 | 9.4793 | 9.4793
VDU | 2026 Feb: 0; 2026 Mar: 0; 2026 Apr: 0 | 0 | 0
Texas City Refinery | 2026 Feb: 0; 2026 Mar: 0; 2026 Apr: 0 | 0 | 0
REF
EXXONMOBIL - BAYTOWN
Grand Total | 246.1153 | 386.8268 | 206.4347 | 38.3858 | 9.9395 | 2.75 | 0.91935 | 1.1 |  |  | 892.4715 | 892.4715

## 22-24 data (hidden)
2024 Planned Offline Mogas Production (KBD)
Sum of Capacity Offline for Area Chart (KBD) | Column Labels | [12 empty] | Column Labels
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Sep | Oct | Nov | Dec | Grand Total |  | Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Aug-Nov Avg
Chalmette Refining LLC | 220.76 | 77.7457 | [7 empty] | 24.7686 | 323.2743 |  | Chalmette Refining LLC | 55.19 | 19.4364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1921
Chalmette Refinery | 220.76 | 77.7457 | [7 empty] | 24.7686 | 323.2743 |  | Chalmette Refinery | 55.19 | 19.4364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1921
Chevron Corporation |  |  |  | 43.2 | 86.4 | 43.2 |  |  |  |  | 172.8 |  | Chevron Corporation | 0 | 0 | 0 | 10.8 | 21.6 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0
Pasadena Refinery |  |  |  | 43.2 | 86.4 | 43.2 |  |  |  |  | 172.8 |  | Pasadena Refinery | 0 | 0 | 0 | 10.8 | 21.6 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0
CITGO Petroleum Corporation | 19.9429 | 267.2 | 392.14 | 97.8 |  |  | 180.5143 | 187.2 | 33.4286 |  | 1178.2257 |  | CITGO Petroleum Corporation | 4.9857 | 66.8 | 98.035 | 24.45 | 0 | 0 | 0 | 0 | 45.1286 | 46.8 | 8.3571 | 0
Corpus Christi Refinery - West (CITGO) |  |  | 83.7857 | 69.2143 | [6 empty] | 153 |  | Corpus Christi Refinery - West (CITGO) | 0 | 0 | 20.9464 | 17.3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corpus Christi Refinery-East |  |  | 194.3829 | 28.5857 | [6 empty] | 222.9686 |  | Corpus Christi Refinery-East | 0 | 0 | 48.5957 | 7.1464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lake Charles Refinery (CITGO) | 19.9429 | 267.2 | 113.9714 |  |  |  | 180.5143 | 187.2 | 33.4286 |  | 802.2571 |  | Lake Charles Refinery (CITGO) | 4.9857 | 66.8 | 28.4929 | 0 | 0 | 0 | 0 | 0 | 45.1286 | 46.8 | 8.3571 | 0
Deer Park Refining LP | [6 empty] | 27.8679 | 156.06 | 11.1471 |  | 195.075 |  | Deer Park Refining LP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.967 | 39.015 | 2.7868 | 0
Deer Park Refinery | [6 empty] | 27.8679 | 156.06 | 11.1471 |  | 195.075 |  | Deer Park Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.967 | 39.015 | 2.7868 | 0
Delek US Holdings | [7 empty] | 115.3286 | 76.8857 |  | 192.2143 |  | Delek US Holdings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8321 | 19.2214 | 0
Krotz Springs Refinery | [7 empty] | 115.3286 | 76.8857 |  | 192.2143 |  | Krotz Springs Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8321 | 19.2214 | 0
ExxonMobil Corporation | 433.6786 | 413.7357 | [7 empty] | 18.2286 | 865.6429 |  | ExxonMobil Corporation | 108.4196 | 103.4339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5571
Baton Rouge Refinery | 255.2 | 45.5714 | [7 empty] | 18.2286 | 319 |  | Baton Rouge Refinery | 63.8 | 11.3929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5571
Baytown Refinery | 159.1929 | 117.6643 | [8 empty] | 276.8571 |  | Baytown Refinery | 39.7982 | 29.4161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beaumont Refinery | 19.2857 | 250.5 | [8 empty] | 269.7857 |  | Beaumont Refinery | 4.8214 | 62.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flint Hills Resources LLC | 155.8143 | 155.8143 |  |  |  |  | 91.1429 | 68.3571 |  |  | 471.1286 |  | Flint Hills Resources LLC | 38.9536 | 38.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7857 | 17.0893 | 0 | 0
Corpus Christi Refinery - East | [6 empty] | 91.1429 | 68.3571 |  |  | 159.5 |  | Corpus Christi Refinery - East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7857 | 17.0893 | 0 | 0
Corpus Christi Refinery - West (Flint Hills) | 155.8143 | 155.8143 | [8 empty] | 311.6286 |  | Corpus Christi Refinery - West (Flint Hills) | 38.9536 | 38.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marathon Petroleum Corporation | 160.8286 | 49.4857 | [8 empty] | 210.3143 |  | Marathon Petroleum Corporation | 40.2071 | 12.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Texas City Refinery (Bay Plant) | 160.8286 | 49.4857 | [8 empty] | 210.3143 |  | Texas City Refinery (Bay Plant) | 40.2071 | 12.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phillips 66 |  | 9 | 157.5 | 22.5 |  |  | 76.56 | 107.184 | 45.936 |  | 418.68 |  | Phillips 66 | 0 | 2.25 | 39.375 | 5.625 | 0 | 0 | 0 | 0 | 19.14 | 26.796 | 11.484 | 0
Lake Charles Refinery (Phillips 66) | [6 empty] | 76.56 | 107.184 | 45.936 |  | 229.68 |  | Lake Charles Refinery (Phillips 66) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.14 | 26.796 | 11.484 | 0
Sweeny Refinery |  | 9 | 157.5 | 22.5 | [6 empty] | 189 |  | Sweeny Refinery | 0 | 2.25 | 39.375 | 5.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Valero Refining Company | 374.16 | 319.5171 | 51.04 |  |  |  | 19.7943 | 277.12 | 98.9714 | 26.7257 | 1167.3286 |  | Valero Refining Company | 93.54 | 79.8793 | 12.76 | 0 | 0 | 0 | 0 | 0 | 4.9486 | 69.28 | 24.7429 | 6.6814
McKee Refinery | [6 empty] | 19.7943 | 277.12 | 98.9714 |  | 395.8857 |  | McKee Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9486 | 69.28 | 24.7429 | 0
Port Arthur Refinery (Valero) | 170 | 115.3571 | [7 empty] | 12.1429 | 297.5 |  | Port Arthur Refinery (Valero) | 42.5 | 28.8393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0357
Texas City Refinery | 204.16 | 204.16 | 51.04 | [6 empty] | 14.5829 | 473.9429 |  | Texas City Refinery | 51.04 | 51.04 | 12.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6457
Vertex Energy | [6 empty] | 3.2786 | 45.9 | 8.1964 |  | 57.375 |  | Vertex Energy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.81964 | 11.475 | 2.0491 | 0
Mobile Refinery (Vertex) | [6 empty] | 3.2786 | 45.9 | 8.1964 |  | 57.375 |  | Mobile Refinery (Vertex) | Column Labels Jul: 0; Column Labels Aug: 0
Grand Total | 1365.1843 | 1292.4986 | 600.68 | 163.5 | 86.4 | 43.2 | 399.1579 | 957.1497 | 274.5653 | 69.7229 | 5252.0586 | ‘24 Planned vs '22 & '23 Planned & Unplanned | 2024 Plan | 347.9765 | 594.7178 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 231.3717 | 310.0705 | 68.0012 | 0 | 175.6037 | 177.9035
[13 empty] | 2024 Plan + Unplanned | 877.8921 | 1086.9943 | 629.3749 | 500.5928 | 225.1081 | 227.2842 | 211.1127 | 122.9935 | 205.6643 | 381.2633 | 74.4243 |  |  | 196.0864
[13 empty] | 2023 Outages | 417.9482 | 512.316 | 415.3019 | 283.595 | 218.2303 | 236.043 | 127.5926 | 245.7606 | 323.255 | 530.4058 | 239.637 | 58.0006 | 300.6738 | 334.7646
[13 empty] | vs 2024 | -16.74% | 16.08% | -42.73% | -71.61% | -89.55% | -74.68% | -59.24% | -58.43% | -28.42% | -41.54% | -71.62% | -100% | -41.6% | -46.86%
[13 empty] | 2022 Outages | 373.9745 | 530.5779 | 279.184 | 242.6356 | 221.0852 | 87.4437 | 50.7737 | 59.6643 | 104.0363 | 446.5262 | 226.3583 | 391.7325 | 251.166 | 209.1463
[13 empty] | vs 2024 | -6.952% | 12.09% | -14.8% | -66.82% | -89.69% | -31.66% | 2.434% | 71.24% | 122.4% | -30.56% | -69.96% | -100% | -30.08% | -14.94%
[12 empty] | ‘24 Planned vs '22 & '23 Planned ONLY | 2024 Plan | 347.9765 | 594.7178 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 231.3717 | 310.0705 | 68.0012 | 0 | 175.6037 | 177.9035
[13 empty] | 2023 Outages | 238.0785 | 467.7776 | 370.2256 | 218.8543 | 116.5578 | 63.0057 | 1.7407 | 63.729 | 165.4983 | 445.019 | 196.645 | 29.1983 | 198.0275 | 217.7228
[13 empty] | vs 2024 | 46.16% | 27.14% | -35.75% | -63.21% | -80.44% | -5.157% | 2888% | 60.32% | 39.8% | -30.32% | -65.42% | -100% | -11.32% | -18.29%
[13 empty] | 2022 Outages | 166.3708 | 279.693 | 218.8073 | 155.898 | 81.3713 | 2.4267 | 22.8417 | 20.1733 | 68.5497 | 391.1662 | 193.853 | 36.1103 | 136.4384 | 168.4356
[13 empty] | vs 2024 | 109.2% | 112.6% | 8.708% | -48.36% | -71.98% | 2362% | 127.7% | 406.5% | 237.5% | -20.73% | -64.92% | -100% | 28.71% | 5.621%
[13 empty] | 2024 Unplanned Outages | Column Labels Jun: 71; Column Labels Jul: 135; Column Labels Aug: 103; Column Labels Sep: 103; Column Labels Oct: 103; Column Labels Nov: 103; Column Labels Dec: 103 | 103
[13 empty] | 2023 Unplanned Outages | 179.8697 | 44.5384 | 45.0763 | 64.7407 | 101.6725 | 173.0373 | 125.8519 | 182.0316 | 157.7567 | 85.3868 | 42.992 | 28.8023 | 102.6464 | 117.0418
[13 empty] | 2022 Unplanned Outages | 207.6037 | 250.8849 | 60.3767 | 86.7376 | 139.7139 | 85.017 | 27.932 | 39.491 | 35.4867 | 55.36 | 32.5053 | 355.6222 | 114.7276 | 40.7108
300.6738

## 23-26 data (hidden)
2024 Planned Offline Mogas Production (KBD)
Sum of Capacity Offline for Area Chart (KBD) | Column Labels | [12 empty] | Column Labels
Row Labels | Jan | Feb | Mar | Apr | May | Jun | Sep | Oct | Nov | Dec | Grand Total |  | Row Labels | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Aug-Nov Avg
Chalmette Refining LLC | 220.76 | 77.7457 | [7 empty] | 24.7686 | 323.2743 |  | Chalmette Refining LLC | 55.19 | 19.4364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1921
Chalmette Refinery | 220.76 | 77.7457 | [7 empty] | 24.7686 | 323.2743 |  | Chalmette Refinery | 55.19 | 19.4364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.1921
Chevron Corporation |  |  |  | 43.2 | 86.4 | 43.2 |  |  |  |  | 172.8 |  | Chevron Corporation | 0 | 0 | 0 | 10.8 | 21.6 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0
Pasadena Refinery |  |  |  | 43.2 | 86.4 | 43.2 |  |  |  |  | 172.8 |  | Pasadena Refinery | 0 | 0 | 0 | 10.8 | 21.6 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0
CITGO Petroleum Corporation | 19.9429 | 267.2 | 392.14 | 97.8 |  |  | 180.5143 | 187.2 | 33.4286 |  | 1178.2257 |  | CITGO Petroleum Corporation | 4.9857 | 66.8 | 98.035 | 24.45 | 0 | 0 | 0 | 0 | 45.1286 | 46.8 | 8.3571 | 0
Corpus Christi Refinery - West (CITGO) |  |  | 83.7857 | 69.2143 | [6 empty] | 153 |  | Corpus Christi Refinery - West (CITGO) | 0 | 0 | 20.9464 | 17.3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corpus Christi Refinery-East |  |  | 194.3829 | 28.5857 | [6 empty] | 222.9686 |  | Corpus Christi Refinery-East | 0 | 0 | 48.5957 | 7.1464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lake Charles Refinery (CITGO) | 19.9429 | 267.2 | 113.9714 |  |  |  | 180.5143 | 187.2 | 33.4286 |  | 802.2571 |  | Lake Charles Refinery (CITGO) | 4.9857 | 66.8 | 28.4929 | 0 | 0 | 0 | 0 | 0 | 45.1286 | 46.8 | 8.3571 | 0
Deer Park Refining LP | [6 empty] | 27.8679 | 156.06 | 11.1471 |  | 195.075 |  | Deer Park Refining LP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.967 | 39.015 | 2.7868 | 0
Deer Park Refinery | [6 empty] | 27.8679 | 156.06 | 11.1471 |  | 195.075 |  | Deer Park Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.967 | 39.015 | 2.7868 | 0
Delek US Holdings | [7 empty] | 115.3286 | 76.8857 |  | 192.2143 |  | Delek US Holdings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8321 | 19.2214 | 0
Krotz Springs Refinery | [7 empty] | 115.3286 | 76.8857 |  | 192.2143 |  | Krotz Springs Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8321 | 19.2214 | 0
ExxonMobil Corporation | 433.6786 | 413.7357 | [7 empty] | 18.2286 | 865.6429 |  | ExxonMobil Corporation | 108.4196 | 103.4339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5571
Baton Rouge Refinery | 255.2 | 45.5714 | [7 empty] | 18.2286 | 319 |  | Baton Rouge Refinery | 63.8 | 11.3929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5571
Baytown Refinery | 159.1929 | 117.6643 | [8 empty] | 276.8571 |  | Baytown Refinery | 39.7982 | 29.4161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Beaumont Refinery | 19.2857 | 250.5 | [8 empty] | 269.7857 |  | Beaumont Refinery | 4.8214 | 62.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flint Hills Resources LLC | 155.8143 | 155.8143 |  |  |  |  | 91.1429 | 68.3571 |  |  | 471.1286 |  | Flint Hills Resources LLC | 38.9536 | 38.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7857 | 17.0893 | 0 | 0
Corpus Christi Refinery - East | [6 empty] | 91.1429 | 68.3571 |  |  | 159.5 |  | Corpus Christi Refinery - East | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.7857 | 17.0893 | 0 | 0
Corpus Christi Refinery - West (Flint Hills) | 155.8143 | 155.8143 | [8 empty] | 311.6286 |  | Corpus Christi Refinery - West (Flint Hills) | 38.9536 | 38.9536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marathon Petroleum Corporation | 160.8286 | 49.4857 | [8 empty] | 210.3143 |  | Marathon Petroleum Corporation | 40.2071 | 12.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Texas City Refinery (Bay Plant) | 160.8286 | 49.4857 | [8 empty] | 210.3143 |  | Texas City Refinery (Bay Plant) | 40.2071 | 12.3714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phillips 66 |  | 9 | 157.5 | 22.5 |  |  | 76.56 | 107.184 | 45.936 |  | 418.68 |  | Phillips 66 | 0 | 2.25 | 39.375 | 5.625 | 0 | 0 | 0 | 0 | 19.14 | 26.796 | 11.484 | 0
Lake Charles Refinery (Phillips 66) | [6 empty] | 76.56 | 107.184 | 45.936 |  | 229.68 |  | Lake Charles Refinery (Phillips 66) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.14 | 26.796 | 11.484 | 0
Sweeny Refinery |  | 9 | 157.5 | 22.5 | [6 empty] | 189 |  | Sweeny Refinery | 0 | 2.25 | 39.375 | 5.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Valero Refining Company | 374.16 | 319.5171 | 51.04 |  |  |  | 19.7943 | 277.12 | 98.9714 | 26.7257 | 1167.3286 |  | Valero Refining Company | 93.54 | 79.8793 | 12.76 | 0 | 0 | 0 | 0 | 0 | 4.9486 | 69.28 | 24.7429 | 6.6814
McKee Refinery | [6 empty] | 19.7943 | 277.12 | 98.9714 |  | 395.8857 |  | McKee Refinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9486 | 69.28 | 24.7429 | 0
Port Arthur Refinery (Valero) | 170 | 115.3571 | [7 empty] | 12.1429 | 297.5 |  | Port Arthur Refinery (Valero) | 42.5 | 28.8393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0357
Texas City Refinery | 204.16 | 204.16 | 51.04 | [6 empty] | 14.5829 | 473.9429 |  | Texas City Refinery | 51.04 | 51.04 | 12.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6457
Vertex Energy | [6 empty] | 3.2786 | 45.9 | 8.1964 |  | 57.375 |  | Vertex Energy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.81964 | 11.475 | 2.0491 | 0
Mobile Refinery (Vertex) | [6 empty] | 3.2786 | 45.9 | 8.1964 |  | 57.375 |  | Mobile Refinery (Vertex) | Column Labels Jul: 0; Column Labels Aug: 0
Grand Total | 1365.1843 | 1292.4986 | 600.68 | 163.5 | 86.4 | 43.2 | 399.1579 | 957.1497 | 274.5653 | 69.7229 | 5252.0586 | ‘24 Planned vs '22 & '23 Planned & Unplanned | 2026 Plan
[13 empty] | 2024 Plan | 347.9765 | 594.7178 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 231.3717 | 310.0705 | 68.0012 | 0 | 175.6037 | 177.9035
[13 empty] | 2024 Plan + Unplanned | 877.8921 | 1086.9943 | 629.3749 | 500.5928 | 225.1081 | 227.2842 | 211.1127 | 122.9935 | 205.6643 | 381.2633 | 74.4243 |  |  | 196.0864
[13 empty] | 2023 Outages | 417.9482 | 512.316 | 415.3019 | 283.595 | 218.2303 | 236.043 | 127.5926 | 245.7606 | 323.255 | 530.4058 | 239.637 | 58.0006 | 300.6738 | 334.7646
[13 empty] | vs 2024 | -16.74% | 16.08% | -42.73% | -71.61% | -89.55% | -74.68% | -59.24% | -58.43% | -28.42% | -41.54% | -71.62% | -100% | -41.6% | -46.86%
[13 empty] | 2022 Outages | 373.9745 | 530.5779 | 279.184 | 242.6356 | 221.0852 | 87.4437 | 50.7737 | 59.6643 | 104.0363 | 446.5262 | 226.3583 | 391.7325 | 251.166 | 209.1463
[12 empty] | ‘24 Planned vs '22 & '23 Planned ONLY | vs 2024 | -6.952% | 12.09% | -14.8% | -66.82% | -89.69% | -31.66% | 2.434% | 71.24% | 122.4% | -30.56% | -69.96% | -100% | -30.08% | -14.94%
[13 empty] | 2024 Plan | 347.9765 | 594.7178 | 237.8614 | 80.5083 | 22.8002 | 59.7567 | 52.0097 | 102.1708 | 231.3717 | 310.0705 | 68.0012 | 0 | 175.6037 | 177.9035
[13 empty] | 2023 Outages | 238.0785 | 467.7776 | 370.2256 | 218.8543 | 116.5578 | 63.0057 | 1.7407 | 63.729 | 165.4983 | 445.019 | 196.645 | 29.1983 | 198.0275 | 217.7228
[13 empty] | vs 2024 | 46.16% | 27.14% | -35.75% | -63.21% | -80.44% | -5.157% | 2888% | 60.32% | 39.8% | -30.32% | -65.42% | -100% | -11.32% | -18.29%
[13 empty] | 2022 Outages | 166.3708 | 279.693 | 218.8073 | 155.898 | 81.3713 | 2.4267 | 22.8417 | 20.1733 | 68.5497 | 391.1662 | 193.853 | 36.1103 | 136.4384 | 168.4356
[13 empty] | vs 2024 | 109.2% | 112.6% | 8.708% | -48.36% | -71.98% | 2362% | 127.7% | 406.5% | 237.5% | -20.73% | -64.92% | -100% | 28.71% | 5.621%
[13 empty] | 2024 Unplanned Outages | Column Labels Jun: 71; Column Labels Jul: 135; Column Labels Aug: 103; Column Labels Sep: 103; Column Labels Oct: 103; Column Labels Nov: 103; Column Labels Dec: 103 | 103
[13 empty] | 2023 Unplanned Outages | 179.8697 | 44.5384 | 45.0763 | 64.7407 | 101.6725 | 173.0373 | 125.8519 | 182.0316 | 157.7567 | 85.3868 | 42.992 | 28.8023 | 102.6464 | 117.0418
[13 empty] | 2022 Unplanned Outages | 207.6037 | 250.8849 | 60.3767 | 86.7376 | 139.7139 | 85.017 | 27.932 | 39.491 | 35.4867 | 55.36 | 32.5053 | 355.6222 | 114.7276 | 40.7108
300.6738